## Sheet1
LARP CRAB Cavities Estimate through HL-LHC
LARP
YEAR | [5 empty] | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | TOTALS
Rates |  |  | Cost + Escalation FTE |  |  | 0.8% | 2.82% | 5.39% | 8.02% | 10.72% | 13.49% | 16.33% | 19.24% | 22.16% | 25.27%
|  |  | Cost + Escalation Materials |  |  | 2.7% | 5.47% | 8.32% | 11.24% | 14.24% | 17.32% | 20.49% | 23.74% | 27.08% | 30.51%
R&D Compact Crab (Design/Prototype/Test in SPS) |  |  |  | Labor | 300 | 302.4 | 308.46 | 316.17 | 324.06 | 332.16 | 340.47 | 348.99 | 357.72 | 366.48 | 375.81
|  |  |  | Materials | 1 | 1.027 | 1.0547 | 1.0832 | 1.1124 | 1.1424 | 1.1732 | 1.2049 | 1.2374 | 1.2708 | 1.3051
Total Labor | [5 empty] | 937.44 | 1927.875 | 1264.68 | 2754.51 | 2740.32 | 2553.525 | 2530.1775 | 1967.46 | 2748.6 | 2066.955 |  |  | TOTAL ESTIMATED COST
Total Materials | [5 empty] | 500.01 | 1087.01 | 655.515 | 2990.43 | 3120.43 | 3545.43 | 3545.43 | 950.43 | 100.43 | 50.43 |  | Contingency
Total | [5 empty] | 1437.45 | 3014.885 | 1920.195 | 5744.94 | 5860.75 | 6098.955 | 6075.6075 | 2917.89 | 2849.03 | 2117.385 | 38037.0875 | 35% | 51350.0681
| Compact Crab Cavity Design | BNL | Total FTE |  |  | 0.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 2 cavities |  | Materials |  |  | 100 | 262 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 442
|  | Design (Cavity + He tank) | FTE |  |  | LARP FY14: 0.1
|  | Fabrication | Materials |  |  | LARP FY13: 100; LARP FY14: 76
|  |  | FTE |  |  | LARP FY14: 0.5
|  | BCP+HPR | Materials |  |  | LARP FY14: 35; LARP FY15: 30
FTE
|  | Bake + Vert Test | Materials |  |  | LARP FY14: 44
|  | HOM Couplers | FTE |  |  | LARP FY14: 0.2
|  |  | Materials |  |  | LARP FY14: 40; LARP FY15: 30
|  | Tuners | FTE |  |  | LARP FY14: 0.2
|  |  | Materials |  |  | LARP FY14: 28; LARP FY15: 20
|  | Tuner Controls | FTE |  |  | LARP FY14: 0.2
|  |  | Materials |  |  | LARP FY14: 31
|  | Tuner mockup | FTE |  |  | LARP FY14: 0.2
Materials
|  | Pickups | FTE |  |  | LARP FY14: 0.1
|  |  | Materials |  |  | LARP FY14: 8
|  | Traavel + Suppiles | Materials |  |  | LARP FY14: 0.05; LARP FY15: 0.05
| Compact Crab Cavity Design | ODU/SLAC | Total FTE |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| 2 cavities |  | Materials |  |  | 400 | 380 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030
|  | Design (Cavity + He tank) | FTE | bar: LARP FY13 to LARP FY15
Cavity
|  | Tooling | Materials |  |  | LARP FY13: 45
| ODU | Materials | Materials |  |  | LARP FY13: 170
|  | Fabrication | Materials |  |  | LARP FY14: 150; LARP FY15: 120
|  | Processing + Testng | Materials |  |  | LARP FY14: 70
|  | He Tanks | Materials
|  | materials | Materials |  |  | LARP FY13: 80
|  | fabrication | Materials |  |  | LARP FY14: 25; LARP FY15: 25
|  | HOM Couplers | Materials
|  | Design + Materials | Materials |  |  | LARP FY14: 50; LARP FY15: 20
|  | Fabrication | Materials |  |  | LARP FY14: 50; LARP FY15: 50
|  | Tuners | Materials
|  | Design + Materials | Materials |  |  | LARP FY13: 35
|  | Fabrication | Materials |  |  | LARP FY14: 35; LARP FY15: 35
|  | Testing | Materials |  |  | LARP FY13: 70
|  | Traavel + Suppiles | Materials |  |  | LARP FY14: 70
| Cryomodules | FNAL | Total FTE |  |  | 1 | 3.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
| 1 Cryomodule |  | Materials |  |  | 0 | 445 | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 770
|  | Design (Cavity + He tank) | FTE |  |  | LARP FY13: 0.5; LARP FY14: 2.5; LARP FY15: 2.5
Cavity
|  | Engineering Design | Materials |  |  | LARP FY14: 45
| FNAL | Fabrication | Materials |  |  | LARP FY14: 350; LARP FY15: 250
|  | Local testing | Materials
|  | Shipping | Materials |  |  | LARP FY15: 25
|  | SPS Installation Support | Materials
|  | materials | Materials
|  | fabrication | Materials
|  | HOM Couplers | Materials
|  | Design + Materials | Materials
|  | Fabrication | Materials
|  | Tuners | Materials
|  | Design + Materials | Materials
|  | Fabrication | Materials
|  | Testing | Materials
|  | Traavel + Suppiles | Materials |  |  | LARP FY14: 50; LARP FY15: 50
| Cavity Production | FNAL or TBD | Total FTE |  |  | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 17
| 30 Cavities |  | Materials |  |  | 0 | 0 | 0.5 | 2890 | 2320 | 2345 | 2345 | 50 | 0 | 0 | 9950.5
|  | Design (Cavity + He tank) | FTE | [5 empty] | 3 | 3 | 3 | 3 | 2 | 2 | 1
|  | Materials | Materials | 60 |  | LARP FY16: 2100
|  | Fabrication | Materials | 100 |  | LARP FY16: 300; LARP FY17: 900; LARP FY18: 900; LARP FY19: 900
FTE
|  | BCP+HPR | Materials | 35 |  | LARP FY16: 105; LARP FY17: 315; LARP FY18: 315; LARP FY19: 315
|  | bake | Materials | 5 |  | LARP FY16: 15; LARP FY17: 45; LARP FY18: 45; LARP FY19: 45
|  | 2 Vert Test | Materials | 30 |  | LARP FY16: 90; LARP FY17: 270; LARP FY18: 270; LARP FY19: 270
|  | HOM Couplers | FTE
|  |  | Materials | 50 |  | LARP FY16: 150; LARP FY17: 450; LARP FY18: 450; LARP FY19: 450
|  | Tuners | FTE
|  |  | Materials | 35 |  | LARP FY16: 105; LARP FY17: 315; LARP FY18: 315; LARP FY19: 315
|  | Tuner Controls | FTE
Materials
|  | Pickups | FTE | Incl in cavity
Materials
|  | Travel + Suppiles | Materials |  |  | LARP FY16: 25; LARP FY17: 25; LARP FY18: 50; LARP FY19: 50; LARP FY20: 50
| Cryomodule Production | FNAL | Total FTE |  |  | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 16
| 10 CM |  | Materials |  |  | 0 | 0 | 0 | 0.2 | 800.2 | 1200.2 | 1200.2 | 800.2 | 0.2 | 0.2 | 4001.4
|  | Design (Cavity + He tank) | FTE | [5 empty] | 1.5 | 1.5 | 3 | 3 | 3 | 1.5 | 1
|  | Fabrication | Materials |  |  | LARP FY17: 800; LARP FY18: 1200; LARP FY19: 1200; LARP FY20: 800
FTE
|  | Traavel + Suppiles | Materials | [5 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| RF Controls | LBNL | Total FTE |  |  | 0 | 0 | 0 | 1 | 1 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 4
|  |  | Materials |  |  | 0 | 0 | 0 | 100.2 | 0.2 | 0.2 | 0.2 | 100.2 | 100.2 | 50.2 | 351.4
|  | Design and Support | FTE |  |  |  |  | 0.5 | 1 | 1 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5
|  | Fabrication | Materials | [5 empty] | 100 | 0 | 0 | 0 | 100 | 100 | 50
|  | Traavel + Suppiles | Materials | [5 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| Project Support | LBNL/SLAC | Total FTE |  |  | 0.6 | 0.75 | 1 | 1.5 | 1.25 | 1.25 | 1 | 1 | 4 | 3 | 15.35
|  |  | Materials |  |  | 0.01 | 0.01 | 0.015 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.245
|  | Design and Support | FTE | SLAC |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.25 | 0 | 0 | 0 | 0
|  | System Commissioning | FTE | All |  | LARP FY21: 3; LARP FY22: 2
|  | Oversight | FTE | LBNL |  | 0.1 | 0.25 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Traavel + Suppiles | Materials |  |  | 0.01 | 0.01 | 0.015 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03