## Summary
IR Quadrupole (MQXF) Cold Mass Estimate using 150mm aperture, "half-length" (~4m) coils. Includes twenty(20) production cold masses using FNAL Rates. Overall project management not included. At-year dollars and all burdens included. DRAFT 03-Dec-2012 NOTE: LQXF, SQXF, WPDS-LQ-HQ-HQM, LHQ, test facility upgrades, cold mass assembly tooling assumed to be part of LARP R&D and not included here.
| FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | Total w/o Contingency | Contingency % | Total incl. Contingency
Design | 0 | 0 | 3094342.1641 | 4345294.9387 | 0 | 0 | 0 | 0 | 0 | 0 | 7439637.1029 | 30% | 9671528.2337
Production Materials | 0 | 0 | 0 | 11033011.9236 | 11532716.0495 | 19147062.4031 | 15972424.9459 | 2088087.752 | 152991.612 | 0 | 59926294.6861 | 30% | 77904183.092
Production Labor | 0 | 0 | 0 | 0 | 6151915.12 | 7829077.3366 | 9489099.4825 | 8701868.5419 | 5563847.5273 | 724747.4 | 38460555.4084 | 30% | 49998722.0309
Total | 0 | 0 | 3094342.1641 | 15378306.8624 | 17684631.1695 | 26976139.7397 | 25461524.4285 | 10789956.2939 | 5716839.1393 | 724747.4 | 105826487.1974 | 30% | 137574433.3566

## Material
[10 empty] | Phase | Prototype | Production
[10 empty] | CMs complete | 0 | 4 | 8 | 6 | 2
[7 empty] | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | Escalation Table
| FNAL M&S Overhead Rate | 20.39% |  |  |  | Escalation | 102.7% | 105.5% | 108.3% | 111.2% | 114.2% | 117.3% | 120.5% | 123.7% | 127.1%
[17 empty] | FY | Labor | M & S
|  | Base Mtl. | [14 empty] | 2012 | Base Year
Tooling |  | FY12 $ | [13 empty] | NOTES: | 2013 | 0.8% | 2.7%
|  | $ ea | Qty | $ | OH Adder | [11 empty] | 2014 | 2.82% | 5.47%
| Winding and Curing tooling | 214509.0436 | 6 | 1287054.2614 | 120.4% |  | 2016: 1723646.6971 |  | 2015 | 5.39% | 8.32%
| Winding, Curing prototype tooling | 214509.0436 | 0 | 0 | 120.4% |  | 2015: 0 |  | 2016 | 8.02% | 11.24%
| Winding machine | 0 |  | 0 | [12 empty] | 2017 | 10.72% | 14.24%
Curing Mold
| Curing press | 0 |  | 0 | [12 empty] | 2018 | 13.49% | 17.32%
| Coil handling / storage | 181000 | 4 | 724000 | 120.4% |  | 2016: 969594.0926 | BNL Estimate | 2019 | 16.33% | 20.49%
[17 empty] | 2020 | 19.24% | 23.74%
| New Reaction Oven | 600000 | 2 | 1200000 | 120.4% |  | 2016: 1607062.032 | A. Nobrega ($250k in 2006) + ancillary | 2021 | 22.16% | 27.08%
| Impreg station | 100000 | 4 | 400000 | 120.4% |  | 2016: 535687.344 | BNL Estimate | 2022 | 25.27% | 30.51%
| Reaction and Impregnation tooling | 300221.5252 | 6 | 1801329.1512 | 120.4% |  | 2016: 2412373.0717 |  | 2023 | 28.4% | 34.03%
| Reaction, Impregnation prototype tooling | 300221.5252 | 0 | 0 | 120.4% |  | 2015: 0 |  | 2024 | 31.61% | 37.65%
| Cold mass assembly tooling | 70825 | 0 | 0 | 100% |  | 2015: 0 | LBNL Estimate (includes M&S OH) | 2025 | 34.9% | 41.37%
| Collaring fixture | 0 | 0 | 0 | 120.4% |  | 2015: 0 | BNL Estimate
| Yoke alignment fixture | 0 | 0 | 0 | 120.4% |  | 2015: 0 | BNL Estimate
| Test Cryostat | 151018.0883 | 0 | 0 | 120.4% |  | 2015: 0
| Test Facility Modifications | 441934.72 | 0 | 0 | 120.4% |  | 2015: 0
| Subtotal Tooling and Equipment | 2132304.2258 |  | 5412383.4126
[7 empty] | Qty tested |  |  |  | 0 | 4 | 8 | 6 | 2
Parts | [6 empty] | Qty Coils |  | 0 | 5 | 10 | 22 | 32 | 26
[7 empty] | Qty Cold mass |  |  |  | 0 | 4 | 8 | 6 | 2
$
| Coil Parts Production - set | 50580.0911 | 81 | 4096987.382 | 120.4% |  | 2016: 677377.867; 2017: 1530420.9327; 2018: 2286083.3184; 2019: 1907631.0132
| Coil Parts full length Prototype | 50580.0911 | 10 | 505800.9114 | 120.4% |  | 2015: 0; 2016: 0
| Prototype Cable | 277404.1105 | 0 | 0 | 100% |  | 2015: 0
| Cable | 277404.1105 | 81 | 22469732.9517 | 100% |  | 2014: 0; 2016: 3085843.3254; 2017: 6971942.0287; 2018: 10414416.0786; 2019: 8690349.5317 | BNL estimate (Includes OH)
| Mirror parts | 361000 | 0 | 0 | 120.4% | [10 empty] | Mirror in R&D
| Cold mass parts | 663155 | 20 | 13263100 | 100% |  | 2016: 0; 2017: 3030353.088; 2018: 6224107.568; 2019: 4794212.757; 2020: 1641175.994 | LBNL Estimate
| Testing materials production | 34000 | 16 | 544000 | 120.4% |  | 2019: 394557.5179; 2020: 303899.9954; 2021: 104034.2962 | LBNL Estimate (includes M&S OH)
| Testing materials prototype | 68000 | 0 | 0 | 120.4% |  | 2017: 0
| Testing materials first two production units | 46750 | 2 | 93500 | 120.4% |  | 2018: 132060.8474
| Ship to CERN | 16000 | 20 | 320000 | 120.4% |  |  |  | 0 | 21427.4938 | 0 | 90394.5907 | 185674.1261 | 143011.7626 | 48957.3158 | BNL estimate
[6 empty] | Totals |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
|  | Prototype Materials with OH |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Production Material with OH |  | 59926294.6861 | 0 | 0 | 0 | 11033011.9236 | 11532716.0495 | 19147062.4031 | 15972424.9459 | 2088087.752 | 152991.612
|  | Total Material w/o Contingency |  |  |  | 59926294.6861 | 0 | 0 | 0 | 11033011.9236 | 11532716.0495 | 19147062.4031 | 15972424.9459 | 2088087.752 | 152991.612
|  |  |  | Contingency | 30% | 17977888.4058 | 0 | 0 | 0 | 3309903.5771 | 3459814.8148 | 5744118.7209 | 4791727.4838 | 626426.3256 | 45897.4836 | total
|  |  |  | Total Material |  | 77904183.092 | 0 | 0 | 0 | 14342915.5007 | 14992530.8643 | 24891181.124 | 20764152.4297 | 2714514.0776 | 198889.0956 | 77904183.092

## Labor
Labor in FTE
Phase | [5 empty] | Prototype | Production
Quantity of Cold Masses Complete | [5 empty] | 0 | 4 | 8 | 6 | 2
|  | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | Cumulative FTE | Comments
|  | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE | FTE
FTE per Hour | 1768
L2 Management
Scientist |  |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 12 | Doubled from "25%" estimate
Engineer |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 4 | Doubled from "25%" estimate
Design and Infrastructure
Engineer |  | FY15: 4; FY16: 4 | 8 | Same as "25%" estimate
Designer |  | FY15: 1.5; FY16: 2 | 3.5 | Same as "25%" estimate
Drafter |  | FY15: 1.5; FY16: 2 | 3.5 | Same as "25%" estimate
Coil Fabrication
Technician |  |  |  |  | 0 | 12 | 16 | 16 | 16 | 8 | 0 | 68 | Doubled from "25%" estimate
Technician Supervisor |  |  |  |  | 0 | 2 | 2 | 2 | 2 | 2 |  | 10 | Doubled from "25%" estimate
Engineer |  |  |  |  | 0 | 3 | 3 | 3 | 3 | 3 |  | 15 | Doubled from "25%" estimate
Designer |  |  |  |  | 0 | 1 | 0.5 | 0 | 0 | 0 |  | 1.5 | Doubled from "25%" estimate
QA
QC (incoming inspection) |  |  |  | 0 | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.2 |  | 3.4 | Doubled from "25%" estimate
QA (travelers) |  |  |  | 0 | 1.5 | 1.5 | 1 | 1 | 0.5 | 0.5 |  | 6 | Doubled from "25%" estimate
Conductor QC
Tooling
Engineer |  | FY15: 1; FY16: 2; FY17: 1 | 4 | Doubled from "25%" estimate
Designer |  | FY15: 0.5; FY16: 1 | 1.5 | Doubled from "25%" estimate
Drafter |  | FY15: 0.5; FY16: 1 | 1.5 | Doubled from "25%" estimate
CM Assembly |  | FY15: Design; FY16: Tooling
Engineer (FNAL Estimate) |  | FY17: 2; FY18: 2; FY19: 2; FY20: 2; FY21: 2 | 10 | Design same, rest doubled from "25%"
Designer |  |  |  | 0.52778 | 0 | 0 | 0.39683 | 0.79365 | 0.59524 | 0.19841 |  | 2.5119 | Design same, rest doubled from "25%"
Tech |  |  |  | 0 | 0.13492 | 0 | 4.3016 | 8.6032 | 6.4524 | 0 |  | 19.4921 | Design same, rest doubled from "25%"
Engineer (LBNL Estimate) |  |  |  | 0.34127 | 0.0039683 | 0 | 0.69048 | 1.381 | 1.0357 | 0.34524 |  | 3.7976 | Design same, rest doubled from "25%"
Testing
Test Cryostat
Engineer |  | FY15: 0; FY16: 0 | 0 | Assumes all test at FNAL
Design/Drafter |  | FY15: 0; FY16: 0 | 0 | Assumes all test at FNAL
Technician |  | FY16: 0.58824; FY18: 1.9005; FY19: 3.8009; FY20: 2.8507; FY21: 0.95023 | 10.0905 | Assumes all test at FNAL
Test Stand
Engineer | [11 empty] | 0 | Assumes all test at FNAL
Design/Drafter | [11 empty] | 0 | Assumes all test at FNAL
Technician | [11 empty] | 0 | Assumes all test at FNAL
Testing Operations | [11 empty] | 0 | Assumes all test at FNAL
Technician |  | FY17: 0; FY18: 2.1493; FY19: 3.6199; FY20: 2.7149; FY21: 0.90498 | 9.3891 | Assumes all test at FNAL
Shipping Preparation
Technician |  | FY17: 0; FY18: 0.1; FY19: 0.2; FY20: 0.2; FY21: 0.1 | 0.6
Measurement/Analysis
Scientist | [11 empty] | 5 | Doubled from "25%" estimate | bar: FY17 to FY21
TOTAL |  | 0 | 0 | 11.869 | 17.2271 | 26.5 | 37.5387 | 45.8986 | 40.5489 | 21.1989 | 2 | 202.7812
Hourly Rates |  | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22
Engineer (Sr) |  | 177.78 | 182.58 | 187.52 | 192.57 | 197.76 | 203.11 | 208.6 | 214.23 | 220.03 | 225.97
Designer |  | 104.56 | 107.38 | 110.29 | 113.26 | 116.32 | 119.46 | 122.69 | 126 | 129.41 | 132.91
Drafter |  | 61.46 | 63.12 | 64.83 | 66.58 | 68.37 | 70.22 | 72.12 | 74.07 | 76.07 | 78.13
Technician Supervisor |  | 123.5 | 126.83 | 130.26 | 133.77 | 137.38 | 141.09 | 144.9 | 148.82 | 152.84 | 156.97
Technician |  | 75.42 | 77.46 | 79.55 | 81.7 | 83.9 | 86.17 | 88.5 | 90.89 | 93.35 | 95.87
QC |  | 99.34 | 102.02 | 104.78 | 107.61 | 110.51 | 113.5 | 116.56 | 119.71 | 122.95 | 126.27
QA |  | 151.42 | 155.51 | 159.71 | 164.02 | 168.44 | 173 | 177.67 | 182.47 | 187.41 | 192.47
Scientist |  | 155.74 | 159.94 | 164.26 | 168.69 | 173.24 | 177.93 | 182.73 | 187.67 | 192.75 | 197.96
FTE Rates (1768 hour/FTE)
Engineer (Sr) |  | 314315.04 | 322801.44 | 331535.36 | 340463.76 | 349639.68 | 359098.48 | 368804.8 | 378758.64 | 389013.04 | 399514.96
Designer |  | 184862.08 | 189847.84 | 194992.72 | 200243.68 | 205653.76 | 211205.28 | 216915.92 | 222768 | 228796.88 | 234984.88
Drafter |  | 108661.28 | 111596.16 | 114619.44 | 117713.44 | 120878.16 | 124148.96 | 127508.16 | 130955.76 | 134491.76 | 138133.84
Technician Supervisor |  | 218348 | 224235.44 | 230299.68 | 236505.36 | 242887.84 | 249447.12 | 256183.2 | 263113.76 | 270221.12 | 277522.96
Technician |  | 133342.56 | 136949.28 | 140644.4 | 144445.6 | 148335.2 | 152348.56 | 156468 | 160693.52 | 165042.8 | 169498.16
QC |  | 175633.12 | 180371.36 | 185251.04 | 190254.48 | 195381.68 | 200668 | 206078.08 | 211647.28 | 217375.6 | 223245.36
QA |  | 267710.56 | 274941.68 | 282367.28 | 289987.36 | 297801.92 | 305864 | 314120.56 | 322606.96 | 331340.88 | 340286.96
Scientist |  | 275348.32 | 282773.92 | 290411.68 | 298243.92 | 306288.32 | 314580.24 | 323066.64 | 331800.56 | 340782 | 349993.28
Burdened Labor in $AY
Phase |  | FY17: Prototype; FY18: Production
Quantity of Cold Masses Complete |  | FY17: 2; FY18: 4; FY19: 8; FY20: 6; FY21: 2
|  | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | Cumulative | Comments
|  | $AY Incl. Burden | $AY Incl. Burden | $AY Incl. Burden | $AY Incl. Burden | $AY Incl. Burden | $AY Incl. Burden | $AY Incl. Burden | $AY Incl. Burden | $AY Incl. Burden | $AY Incl. Burden | $AY Incl. Burden
FTE per Hour | 1768
L2 Management
Scientist |  | 0 | 0 | 435617.52 | 447365.88 | 459432.48 | 471870.36 | 484599.96 | 497700.84 | 511173 | 524989.92 | 3832749.96
Engineer |  | 0 | 0 | 165767.68 | 170231.88 | 174819.84 | 179549.24 | 184402.4 | 189379.32 | 194506.52 | 199757.48 | 1458414.36
Design
Engineer |  | 0 | 0 | 1326141.44 | 1361855.04 | 0 | 0 | 0 | 0 | 0 | 0 | 2687996.48
Design/Drafter |  | 0 | 0 | 292489.08 | 400487.36 | 0 | 0 | 0 | 0 | 0 | 0 | 692976.44
Drafter |  | 0 | 0 | 171929.16 | 235426.88 | 0 | 0 | 0 | 0 | 0 | 0 | 407356.04
Coil Fabrication
Technician |  | 0 | 0 | 0 | 0 | 1780022.4 | 2437576.96 | 2503488 | 2571096.32 | 1320342.4 | 0 | 10612526.08
Technician Supervisor |  | 0 | 0 | 0 | 0 | 485775.68 | 498894.24 | 512366.4 | 526227.52 | 540442.24 | 0 | 2563706.08
Engineer |  | 0 | 0 | 0 | 0 | 1048919.04 | 1077295.44 | 1106414.4 | 1136275.92 | 1167039.12 | 0 | 5535943.92
Designer |  | 0 | 0 | 0 | 0 | 205653.76 | 105602.64 | 0 | 0 | 0 | 0 | 311256.4
QA
QC (incoming inspection) |  | 0 | 0 | 0 | 190254.48 | 195381.68 | 100334 | 103039.04 | 42329.456 | 43475.12 | 0 | 674813.776
QA (Production) |  | 0 | 0 | 0 | 434981.04 | 446702.88 | 305864 | 314120.56 | 161303.48 | 165670.44 | 0 | 1828642.4
Conductor QC
Tooling
Engineer |  | 0 | 0 | 331535.36 | 680927.52 | 349639.68 | 0 | 0 | 0 | 0 | 0 | 1362102.56
Designer |  | 0 | 0 | 97496.36 | 200243.68 | 0 | 0 | 0 | 0 | 0 | 0 | 297740.04
Drafter |  | 0 | 0 | 57309.72 | 117713.44 | 0 | 0 | 0 | 0 | 0 | 0 | 175023.16
CM Assembly
Engineer (FNAL Estimate) |  | 0 | 0 | 0 | 0 | 699279.36 | 718196.96 | 737609.6 | 757517.28 | 778026.08 | 0 | 3690629.28
Designer (LBNL Estimate) |  | 0 | 0 | 102912.8244 | 0 | 0 | 83811.619 | 172155.4921 | 132600 | 45396.2063 | 0 | 536876.1419
Tech (LBNL Estimate) |  | 0 | 0 | 0 | 19488.6921 | 0 | 655340.6311 | 1346121.5238 | 1036855.8076 | 0 | 0 | 3057806.6546
Engineer (LBNL Estimate) |  | 0 | 0 | 113143.0197 | 1351.0467 | 0 | 247948.9505 | 509301.8667 | 392285.7343 | 134302.121 | 0 | 1398332.7387
Testing
Test Cryostat
Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design/Drafter |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technician |  | 0 | 0 | 0 | 84968 | 0 | 289531.2 | 594720 | 458085.6 | 156828 | 0 | 1584132.8
Test Stand | [11 empty] | 0
Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Converted person-weeks to FTE
Design/Drafter |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Converted person-weeks to FTE
Technician |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Converted person-weeks to FTE
Testing Operations | [11 empty] | 0 | Yr-#Tests - 2018-2, 2019-4, 2020-3, 2021-1
Technician |  | 0 | 0 | 0 | 0 | 0 | 327446 | 566400 | 436272 | 149360 | 0 | 1479478 | Converted person-weeks to FTE
Shipping Preparation
Technician |  | 0 | 0 | 0 | 0 | 0 | 15234.856 | 31293.6 | 32138.704 | 16504.28 | 0 | 95171.44
Measurement/Analysis
Scientist |  | 0 | 0 | 0 | 0 | 306288.32 | 314580.24 | 323066.64 | 331800.56 | 340782 | 0 | 1616517.76
TOTAL |  | 0 | 0 | 3094342.1641 | 4345294.9387 | 6151915.12 | 7829077.3366 | 9489099.4825 | 8701868.5419 | 5563847.5273 | 724747.4 | 45900192.5112
45900192.5112

## FNALLaborRates
Rates by FY for FNAL Resources
| Budget Element/Resource |  | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | Cumulative
AD Accelerator Division
| FNAD.AC.EXP.PHYST Accelerator Physicist Experimental | Rate | 153.25 | 157.39 | 161.64 | 166.01 | 170.49 | 175.09 | 179.82 | 184.68 | 189.67 | 194.8 | 200.06 | 205.46 | 0 | 2138
| FNAD.AC.EXP.RA Accelerator Experimental Research Associate | Rate | 92.95 | 95.47 | 98.04 | 100.69 | 103.41 | 106.2 | 109.07 | 112.01 | 115.04 | 118.15 | 121.35 | 124.62 | 0 | 1297
| FNAD.AC.OPERATOR Accelerator Operator | Rate | 87.66 | 90.03 | 92.46 | 94.96 | 97.52 | 100.15 | 102.86 | 105.64 | 108.49 | 111.43 | 114.44 | 117.53 | 0 | 1223
| FNAD.AC.SYSTM.SPCLST Accelerator Systems Specialist | Rate | 130.3 | 133.82 | 137.43 | 141.15 | 144.95 | 148.86 | 152.89 | 157.02 | 161.26 | 165.62 | 170.1 | 174.69 | 0 | 1818
| FNAD.AC.THY.PHYST Accelerator Physicist Theory | Rate | 168.08 | 172.62 | 177.28 | 182.07 | 186.98 | 192.02 | 197.21 | 202.54 | 208.01 | 213.64 | 219.41 | 225.34 | 0 | 2345
| FNAD.AC.THY.RA Accelerator Theory Research Associate | Rate | 92.95 | 95.47 | 98.04 | 100.69 | 103.41 | 106.2 | 109.07 | 112.01 | 115.04 | 118.15 | 121.35 | 124.62 | 0 | 1297
| FNAD.ACCOUNTANT Accountant | Rate | 123.4 | 126.74 | 130.16 | 133.68 | 137.28 | 140.98 | 144.8 | 148.71 | 152.73 | 156.85 | 161.09 | 165.44 | 0 | 1722
| FNAD.ADMIN.SPPRT Administrative Support | Rate | 75.86 | 77.91 | 80.01 | 82.17 | 84.39 | 86.67 | 89.01 | 91.41 | 93.88 | 96.42 | 99.03 | 101.7 | 0 | 1058
| FNAD.APDEV.SYSTMAYST Applications Development & Systems Analyst | Rate | 140.48 | 144.28 | 148.17 | 152.18 | 156.28 | 160.49 | 164.83 | 169.28 | 173.86 | 178.56 | 183.39 | 188.34 | 0 | 1960
| FNAD.ASIC.DESIGN.EN ASIC Design Engineer | Rate | 140.67 | 144.47 | 148.37 | 152.38 | 156.49 | 160.71 | 165.06 | 169.51 | 174.1 | 178.8 | 183.64 | 188.6 | 0 | 1963
| FNAD.ASIC.DESIGN.SR ASIC Design Engineer Sr | Rate | 197.91 | 203.26 | 208.75 | 214.39 | 220.17 | 226.11 | 232.23 | 238.5 | 244.94 | 251.57 | 258.37 | 265.34 | 0 | 2762
| FNAD.CLERICAL Clerical | Rate | 67.96 | 69.8 | 71.69 | 73.62 | 75.61 | 77.65 | 79.75 | 81.9 | 84.12 | 86.39 | 88.72 | 91.12 | 0 | 948
| FNAD.CONST.COORDNATR Construction Coordinator | Rate | 131 | 134.55 | 138.18 | 141.91 | 145.74 | 149.67 | 153.72 | 157.87 | 162.13 | 166.52 | 171.02 | 175.64 | 0 | 1828
| FNAD.CONST.SAFETY Construction Safety | Rate | 129.98 | 133.49 | 137.1 | 140.8 | 144.6 | 148.5 | 152.51 | 156.63 | 160.87 | 165.22 | 169.68 | 174.26 | 0 | 1814
| FNAD.CRYO.DESIGNER Cryo Designer | Rate | 100 | 102.7 | 105.47 | 108.32 | 111.24 | 114.24 | 117.33 | 120.5 | 123.76 | 127.1 | 130.54 | 134.06 | 0 | 1395
| FNAD.CRYO.EN Cryogenics Engineer | Rate | 144.75 | 148.66 | 152.67 | 156.8 | 161.03 | 165.37 | 169.84 | 174.43 | 179.14 | 183.99 | 188.96 | 194.06 | 0 | 2020
| FNAD.CRYO.SR Cryogenics Engineer Sr | Rate | 198.82 | 204.19 | 209.7 | 215.37 | 221.18 | 227.14 | 233.29 | 239.58 | 246.06 | 252.71 | 259.55 | 266.55 | 0 | 2774
| FNAD.CRYO.TECH Cryo Technician | Rate | 83.87 | 86.14 | 88.46 | 90.85 | 93.3 | 95.82 | 98.41 | 101.07 | 103.8 | 106.61 | 109.49 | 112.45 | 0 | 1170
| FNAD.CT.SRVCS.SPCLST Computing Services Specialist | Rate | 152.52 | 156.65 | 160.88 | 165.22 | 169.68 | 174.26 | 178.97 | 183.8 | 188.77 | 193.87 | 199.11 | 204.49 | 0 | 2128
| FNAD.CTRL.SYSTM.EN Control System Engineer | Rate | 148.18 | 152.19 | 156.29 | 160.52 | 164.85 | 169.29 | 173.87 | 178.56 | 183.39 | 188.35 | 193.44 | 198.66 | 0 | 2068
| FNAD.CTRL.SYSTM.SR Control System Engineer Sr | Rate | 180.84 | 185.73 | 190.74 | 195.9 | 201.18 | 206.61 | 212.2 | 217.93 | 223.82 | 229.87 | 236.08 | 242.46 | 0 | 2523
| FNAD.DATABASE.AYST Database Administration Analyst | Rate | 138.99 | 142.75 | 146.6 | 150.57 | 154.63 | 158.8 | 163.09 | 167.49 | 172.02 | 176.67 | 181.45 | 186.35 | 0 | 1939
| FNAD.ELEC.ASMBY.TECH Electrical Assembly Technician | Rate | 77.4 | 79.5 | 81.64 | 83.85 | 86.11 | 88.43 | 90.82 | 93.28 | 95.8 | 98.39 | 101.05 | 103.78 | 0 | 1080
| FNAD.ELEC.DESIGN.EN Electrical Design Engineer | Rate | 140.65 | 144.46 | 148.36 | 152.37 | 156.48 | 160.69 | 165.04 | 169.5 | 174.08 | 178.78 | 183.62 | 188.57 | 0 | 1963
| FNAD.ELEC.DESIGN.SR Electrical Design Engineer Sr | Rate | 176.17 | 180.93 | 185.81 | 190.83 | 195.98 | 201.27 | 206.71 | 212.29 | 218.03 | 223.92 | 229.97 | 236.18 | 0 | 2458
| FNAD.ELEC.DESIGNER Electrical Designer | Rate | 108.65 | 111.58 | 114.6 | 117.69 | 120.87 | 124.13 | 127.48 | 130.93 | 134.46 | 138.1 | 141.83 | 145.66 | 0 | 1516
| FNAD.ELEC.DRAFTER Electrical Drafter | Rate | 75.93 | 77.98 | 80.09 | 82.25 | 84.47 | 86.75 | 89.1 | 91.5 | 93.97 | 96.52 | 99.12 | 101.8 | 0 | 1059
| FNAD.ELEC.TASK.MNGR Electrical Task Manager | Rate | 131.67 | 135.23 | 138.88 | 142.63 | 146.48 | 150.43 | 154.5 | 158.67 | 162.96 | 167.36 | 171.89 | 176.53 | 0 | 1837
| FNAD.ELEC.TECH Electrical Technician | Rate | 88.62 | 91.01 | 93.47 | 96 | 98.58 | 101.24 | 103.98 | 106.79 | 109.67 | 112.64 | 115.68 | 118.81 | 0 | 1236
| FNAD.ELEC.TECH.MNGR Electrical Technical Manager | Rate | 213.39 | 219.16 | 225.07 | 231.16 | 237.39 | 243.79 | 250.38 | 257.15 | 264.1 | 271.24 | 278.57 | 286.09 | 0 | 2977
| FNAD.ELEC.TECH.SPVSR Electrical Technician Supervisor | Rate | 124.32 | 127.68 | 131.13 | 134.67 | 138.3 | 142.03 | 145.87 | 149.81 | 153.86 | 158.02 | 162.29 | 166.67 | 0 | 1735
| FNAD.ELTN.DESIGN.EN Electronics Design Engineer | Rate | 144.21 | 148.11 | 152.11 | 156.22 | 160.43 | 164.76 | 169.21 | 173.78 | 178.48 | 183.3 | 188.26 | 193.34 | 0 | 2012
| FNAD.ELTN.DESIGN.SR Electronics Design Engineer Sr | Rate | 186.02 | 191.05 | 196.21 | 201.51 | 206.94 | 212.53 | 218.27 | 224.17 | 230.22 | 236.45 | 242.84 | 249.4 | 0 | 2596
| FNAD.ELTN.TECH Electronics Technician | Rate | 95.92 | 98.51 | 101.17 | 103.91 | 106.71 | 109.59 | 112.55 | 115.59 | 118.71 | 121.92 | 125.22 | 128.6 | 0 | 1338
| FNAD.ENGNRING.PHYST Engineering Physicist | Rate | 153.85 | 158.01 | 162.28 | 166.66 | 171.16 | 175.77 | 180.53 | 185.4 | 190.41 | 195.56 | 200.85 | 206.27 | 0 | 2147
| FNAD.FACILITIES.MGMT Facilities Management | Rate | 129.89 | 133.4 | 137 | 140.7 | 144.5 | 148.39 | 152.41 | 156.52 | 160.75 | 165.1 | 169.56 | 174.14 | 0 | 1812
| FNAD.GENERAL.ADMIN General Administrative | Rate | 94.42 | 96.98 | 99.59 | 102.29 | 105.04 | 107.88 | 110.79 | 113.79 | 116.86 | 120.02 | 123.27 | 126.59 | 0 | 1318
| FNAD.GENERAL.ES&H General ES&H | Rate | 148.75 | 152.77 | 156.9 | 161.14 | 165.48 | 169.94 | 174.54 | 179.25 | 184.1 | 189.08 | 194.19 | 199.43 | 0 | 2076
| FNAD.HIGH.VAC.TECH High Vac Technician | Rate | 85.54 | 87.85 | 90.22 | 92.66 | 95.16 | 97.72 | 100.36 | 103.07 | 105.86 | 108.72 | 111.66 | 114.68 | 0 | 1194
| FNAD.INTERLOCK.EN Interlock Engineer | Rate | 140.35 | 144.15 | 148.04 | 152.04 | 156.14 | 160.35 | 164.69 | 169.13 | 173.7 | 178.4 | 183.22 | 188.17 | 0 | 1958
| FNAD.INTERLOCK.SR Interlock Engineer Sr | Rate | 174.35 | 179.06 | 183.89 | 188.86 | 193.95 | 199.19 | 204.57 | 210.09 | 215.77 | 221.61 | 227.6 | 233.74 | 0 | 2433
| FNAD.INTERLOCK.TECH Electrical Interlock Technician | Rate | 106.58 | 109.46 | 112.42 | 115.46 | 118.57 | 121.77 | 125.06 | 128.44 | 131.91 | 135.48 | 139.14 | 142.89 | 0 | 1487
| FNAD.MAGNT.DESIGN.EN Magnet Design Engineer | Rate | 163.07 | 167.48 | 172 | 176.65 | 181.42 | 186.31 | 191.35 | 196.51 | 201.82 | 207.28 | 212.88 | 218.63 | 0 | 2275
| FNAD.MAGNT.DESIGN.SR Magnet Design Engineer Sr | Rate | 179.46 | 184.31 | 189.29 | 194.4 | 199.65 | 205.03 | 210.57 | 216.26 | 222.1 | 228.11 | 234.28 | 240.6 | 0 | 2504
| FNAD.MAGNT.DESIGNER Magnet Designer | Rate | 105.55 | 108.4 | 111.33 | 114.34 | 117.42 | 120.59 | 123.85 | 127.19 | 130.63 | 134.16 | 137.79 | 141.51 | 0 | 1473
| FNAD.MAGNT.RA Magnet Research Associate | Rate | 92.95 | 95.47 | 98.04 | 100.69 | 103.41 | 106.2 | 109.07 | 112.01 | 115.04 | 118.15 | 121.35 | 124.62 | 0 | 1297
| FNAD.MAGNT.SCIENTIST Magnet Scientist | Rate | 157.21 | 161.46 | 165.82 | 170.3 | 174.89 | 179.61 | 184.46 | 189.44 | 194.57 | 199.83 | 205.23 | 210.77 | 0 | 2194
| FNAD.MATRL.EN Materials Engineer | Rate | 89.95 | 92.38 | 94.88 | 97.44 | 100.07 | 102.77 | 105.55 | 108.4 | 111.33 | 114.34 | 117.43 | 120.6 | 0 | 1255
| FNAD.MATRL.SR Materials Engineer Sr | Rate | 89.95 | 92.38 | 94.88 | 97.44 | 100.07 | 102.77 | 105.55 | 108.4 | 111.33 | 114.34 | 117.43 | 120.6 | 0 | 1255
| FNAD.MECH.ANLYSIS.EN Mechanical Analysis Engineer | Rate | 137.03 | 140.73 | 144.53 | 148.44 | 152.44 | 156.55 | 160.78 | 165.13 | 169.59 | 174.18 | 178.88 | 183.71 | 0 | 1912
| FNAD.MECH.ANLYSIS.SR Mechanical Analysis Engineer Sr | Rate | 172.37 | 177.03 | 181.8 | 186.72 | 191.75 | 196.92 | 202.25 | 207.71 | 213.33 | 219.09 | 225.02 | 231.09 | 0 | 2405
| FNAD.MECH.ASMBY.TECH Mechanical Assembly Technician | Rate | 88.13 | 90.52 | 92.96 | 95.47 | 98.05 | 100.69 | 103.41 | 106.21 | 109.08 | 112.03 | 115.05 | 118.16 | 0 | 1230
| FNAD.MECH.DESIGN.EN Mechanical Design Engineer | Rate | 142.55 | 146.41 | 150.36 | 154.42 | 158.59 | 162.86 | 167.27 | 171.78 | 176.43 | 181.2 | 186.1 | 191.12 | 0 | 1989
| FNAD.MECH.DESIGN.SR Mechanical Design Engineer Sr | Rate | 180.42 | 185.3 | 190.3 | 195.44 | 200.71 | 206.13 | 211.7 | 217.42 | 223.29 | 229.33 | 235.53 | 241.89 | 0 | 2517
| FNAD.MECH.DESIGNER Mechanical Designer | Rate | 104.78 | 107.61 | 110.51 | 113.5 | 116.56 | 119.7 | 122.94 | 126.26 | 129.67 | 133.18 | 136.78 | 140.47 | 0 | 1462
| FNAD.MECH.DRAFTER Mechanical Drafter | Rate | 62.05 | 63.72 | 65.44 | 67.21 | 69.02 | 70.89 | 72.8 | 74.77 | 76.79 | 78.87 | 81 | 83.18 | 0 | 866
| FNAD.MECH.SYSTM.TECH Mechanical Systems Technician | Rate | 76.14 | 78.19 | 80.31 | 82.48 | 84.7 | 86.98 | 89.34 | 91.75 | 94.23 | 96.78 | 99.39 | 102.08 | 0 | 1062
| FNAD.MECH.TASK.MNGR Mechanical Task Manager | Rate | 74.01 | 76.01 | 78.06 | 80.17 | 82.33 | 84.55 | 86.84 | 89.18 | 91.59 | 94.07 | 96.61 | 99.22 | 0 | 1033
| FNAD.MECH.TECH.MNGR Mechanical Technical Manager | Rate | 185.92 | 190.94 | 196.1 | 201.4 | 206.83 | 212.41 | 218.15 | 224.04 | 230.1 | 236.32 | 242.71 | 249.26 | 0 | 2594
| FNAD.MECH.TECH.SPVSR Mechanical Technician Supervisor | Rate | 124.66 | 128.03 | 131.49 | 135.04 | 138.69 | 142.42 | 146.28 | 150.23 | 154.29 | 158.46 | 162.74 | 167.14 | 0 | 1739
| FNAD.NETWORK.AYST Network Analyst | Rate | 143.65 | 147.54 | 151.52 | 155.62 | 159.81 | 164.12 | 168.56 | 173.11 | 177.79 | 182.6 | 187.53 | 192.6 | 0 | 2004
| FNAD.OPERTNS.FINANCE Operations Finance | Rate | 135.67 | 139.34 | 143.1 | 146.96 | 150.93 | 155 | 159.19 | 163.49 | 167.91 | 172.45 | 177.11 | 181.89 | 0 | 1893
| FNAD.OPERTNS.MNGR Operations Manager | Rate | 173.17 | 177.85 | 182.65 | 187.59 | 192.65 | 197.85 | 203.19 | 208.68 | 214.32 | 220.12 | 226.07 | 232.17 | 0 | 2416
| FNAD.OPERTNS.SPCLST Operations Specialist | Rate | 128.03 | 131.49 | 135.04 | 138.69 | 142.43 | 146.27 | 150.23 | 154.28 | 158.45 | 162.74 | 167.14 | 171.65 | 0 | 1786
| FNAD.PA.EXP.RA Particle-Astro Experimental Research Associate | Rate | 92.95 | 95.47 | 98.04 | 100.69 | 103.41 | 106.2 | 109.07 | 112.01 | 115.04 | 118.15 | 121.35 | 124.62 | 0 | 1297
| FNAD.PA.THY.RA Particle-Astro Theory Research Associate | Rate | 92.95 | 95.47 | 98.04 | 100.69 | 103.41 | 106.2 | 109.07 | 112.01 | 115.04 | 118.15 | 121.35 | 124.62 | 0 | 1297
| FNAD.PC.CUSTM.SPPRT Computer Customer Support | Rate | 98.25 | 100.91 | 103.63 | 106.43 | 109.3 | 112.25 | 115.28 | 118.4 | 121.6 | 124.89 | 128.26 | 131.72 | 0 | 1371
| FNAD.PC.SECURTY.AYST Computer Security Analyst | Rate | 161.84 | 166.21 | 170.7 | 175.31 | 180.04 | 184.9 | 189.89 | 195.02 | 200.29 | 205.71 | 211.27 | 216.97 | 0 | 2258
| FNAD.PC.SPPRT.ASSOCT PC Support Associate | Rate | 91.79 | 94.27 | 96.81 | 99.43 | 102.11 | 104.86 | 107.7 | 110.61 | 113.6 | 116.67 | 119.82 | 123.06 | 0 | 1281
| FNAD.PRCESS.CTRL.EN Process/Controls Engineer | Rate | 111.42 | 114.43 | 117.52 | 120.7 | 123.96 | 127.3 | 130.74 | 134.27 | 137.9 | 141.63 | 145.46 | 149.38 | 0 | 1555
| FNAD.PRCESS.CTRL.SR Process/Controls Engineer Sr | Rate | 151.97 | 156.08 | 160.29 | 164.63 | 169.07 | 173.63 | 178.32 | 183.14 | 188.09 | 193.17 | 198.39 | 203.75 | 0 | 2121
| FNAD.PRJ.CTRL.LEAD Project Controls Lead | Rate | 138.77 | 142.52 | 146.37 | 150.33 | 154.38 | 158.54 | 162.83 | 167.23 | 171.75 | 176.39 | 181.16 | 186.05 | 0 | 1936
| FNAD.PRJ.CTRL.MNGR Project Controls Manager | Rate | 188.91 | 194.01 | 199.25 | 204.64 | 210.15 | 215.82 | 221.66 | 227.64 | 233.79 | 240.12 | 246.61 | 253.26 | 0 | 2636
| FNAD.PRJ.CTRL.SPCLST Project Controls Specialist | Rate | 116.94 | 120.1 | 123.34 | 126.68 | 130.09 | 133.6 | 137.22 | 140.92 | 144.73 | 148.64 | 152.66 | 156.78 | 0 | 1632
| FNAD.PRJ.FINANCE Project Finance | Rate | 134.41 | 138.04 | 141.77 | 145.6 | 149.53 | 153.56 | 157.71 | 161.97 | 166.35 | 170.85 | 175.47 | 180.2 | 0 | 1875
| FNAD.PRJ.MNGR Project Manager | Rate | 159.01 | 163.31 | 167.72 | 172.25 | 176.9 | 181.67 | 186.58 | 191.62 | 196.8 | 202.12 | 207.58 | 213.18 | 0 | 2219
| FNAD.PRJ.MNGR.EXC Project Manager Exec | Rate | 299.85 | 307.95 | 316.27 | 324.82 | 333.58 | 342.57 | 351.83 | 361.33 | 371.1 | 381.14 | 391.44 | 402.01 | 0 | 4184
| FNAD.PRJ.MNGR.SR Project Manager Sr | Rate | 239.88 | 246.36 | 253.01 | 259.85 | 266.86 | 274.06 | 281.47 | 289.07 | 296.88 | 304.91 | 313.15 | 321.61 | 0 | 3347
| FNAD.PRJ.SPPRT Project Support | Rate | 138.84 | 142.59 | 146.44 | 150.4 | 154.46 | 158.62 | 162.91 | 167.31 | 171.83 | 176.48 | 181.25 | 186.14 | 0 | 1937
| FNAD.PROCUREMENT Procurement | Rate | 114.78 | 117.89 | 121.07 | 124.34 | 127.7 | 131.14 | 134.68 | 138.32 | 142.06 | 145.9 | 149.85 | 153.89 | 0 | 1602
| FNAD.PT.EXP.PHYST Particle Physicist Experimental | Rate | 140.24 | 144.03 | 147.92 | 151.92 | 156.02 | 160.22 | 164.56 | 169 | 173.57 | 178.26 | 183.08 | 188.02 | 0 | 1957
| FNAD.PT.EXP.RA Particle Physics Experimental Research Associate | Rate | 92.95 | 95.47 | 98.04 | 100.69 | 103.41 | 106.2 | 109.07 | 112.01 | 115.04 | 118.15 | 121.35 | 124.62 | 0 | 1297
| FNAD.PT.THY.RA Particle Physics Theory Research Associate | Rate | 92.95 | 95.47 | 98.04 | 100.69 | 103.41 | 106.2 | 109.07 | 112.01 | 115.04 | 118.15 | 121.35 | 124.62 | 0 | 1297
| FNAD.QLTY.ASSRANCE Quality Assurance | Rate | 152.85 | 156.99 | 161.22 | 165.58 | 170.05 | 174.63 | 179.35 | 184.2 | 189.18 | 194.29 | 199.54 | 204.93 | 0 | 2133
| FNAD.RAD.PRTECTON Radiation Protection | Rate | 123.09 | 126.42 | 129.83 | 133.34 | 136.94 | 140.63 | 144.43 | 148.33 | 152.34 | 156.46 | 160.69 | 165.03 | 0 | 1718
| FNAD.RF.DESIGN.EN RF Design Engineer | Rate | 150.84 | 154.91 | 159.1 | 163.4 | 167.8 | 172.33 | 176.99 | 181.77 | 186.68 | 191.73 | 196.91 | 202.23 | 0 | 2105
| FNAD.RF.DESIGN.SR RF Design Engineer Sr | Rate | 185.81 | 190.83 | 195.99 | 201.28 | 206.71 | 212.29 | 218.03 | 223.91 | 229.97 | 236.18 | 242.57 | 249.12 | 0 | 2593
| FNAD.RF.RA RF Research Associate | Rate | 92.95 | 95.47 | 98.04 | 100.69 | 103.41 | 106.2 | 109.07 | 112.01 | 115.04 | 118.15 | 121.35 | 124.62 | 0 | 1297
| FNAD.RF.SCIENTIST RF Scientist | Rate | 173.16 | 177.84 | 182.64 | 187.57 | 192.63 | 197.83 | 203.17 | 208.66 | 214.3 | 220.1 | 226.05 | 232.15 | 0 | 2416
| FNAD.SAFETY Safety | Rate | 132.91 | 136.5 | 140.19 | 143.98 | 147.86 | 151.85 | 155.95 | 160.16 | 164.49 | 168.94 | 173.51 | 178.19 | 0 | 1855
| FNAD.SRF.TECH Mechanical SRF Technician | Rate | 77.44 | 79.54 | 81.68 | 83.89 | 86.16 | 88.48 | 90.87 | 93.32 | 95.85 | 98.44 | 101.1 | 103.83 | 0 | 1081
| FNAD.SYSTM.ADMIN Systems Administrator | Rate | 119.3 | 122.53 | 125.84 | 129.24 | 132.72 | 136.3 | 139.99 | 143.77 | 147.65 | 151.65 | 155.75 | 159.95 | 0 | 1665
| FNAD.TRAINING Training | Rate | 124.73 | 128.1 | 131.56 | 135.12 | 138.76 | 142.5 | 146.36 | 150.31 | 154.37 | 158.54 | 162.83 | 167.23 | 0 | 1740
| FNAD.U.CONST.SAFETY Construction Safety Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAD.U.GENERAL.ES&H General ES&H Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAD.U.PA.EXP.PHYST Particle-Astro Physicist Experimental Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAD.U.PA.EXP.RA Particle-Astro Experimental Research Associate Uncost | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAD.U.PA.THY.RA Particle-Astro Theory Research Associate Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAD.U.PROCUREMENT Procurement Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAD.U.PT.EXP.PHYST Particle Physicist Experimental Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAD.U.PT.EXP.RA Particle Physics Experimental Research Associate Unco | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAD.U.PT.THY.RA Particle Physics Theory Research Associate Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAD.U.RAD.PRTECTON Radiation Protection Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAD.U.RF.RA RF Research Associate Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAD.U.RF.SCIENTIST RF Scientist Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAD.U.SAFETY Safety Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAD.WEB.APPS.DEVLPR Web Applications Developer | Rate | 96.39 | 99 | 101.67 | 104.42 | 107.23 | 110.13 | 113.1 | 116.16 | 119.3 | 122.52 | 125.83 | 129.23 | 0 | 1345
AP Accelerator Physics Center
| FNAP.AC.EXP.PHYST Accelerator Physicist Experimental | Rate | 153.25 | 157.39 | 161.64 | 166.01 | 170.49 | 175.09 | 179.82 | 184.68 | 189.67 | 194.8 | 200.06 | 205.46 | 0 | 2138
| FNAP.AC.EXP.RA Accelerator Experimental Research Associate | Rate | 92.95 | 95.47 | 98.04 | 100.69 | 103.41 | 106.2 | 109.07 | 112.01 | 115.04 | 118.15 | 121.35 | 124.62 | 0 | 1297
| FNAP.AC.THY.PHYST Accelerator Physicist Theory | Rate | 168.08 | 172.62 | 177.28 | 182.07 | 186.98 | 192.02 | 197.21 | 202.54 | 208.01 | 213.64 | 219.41 | 225.34 | 0 | 2345
| FNAP.AC.THY.RA Accelerator Theory Research Associate | Rate | 92.95 | 95.47 | 98.04 | 100.69 | 103.41 | 106.2 | 109.07 | 112.01 | 115.04 | 118.15 | 121.35 | 124.62 | 0 | 1297
| FNAP.ADMIN.SPPRT Administrative Support | Rate | 75.86 | 77.91 | 80.01 | 82.17 | 84.39 | 86.67 | 89.01 | 91.41 | 93.88 | 96.42 | 99.03 | 101.7 | 0 | 1058
| FNAP.ELEC.TECH.MNGR Electrical Technical Manager | Rate | 213.39 | 219.16 | 225.07 | 231.16 | 237.39 | 243.79 | 250.38 | 257.15 | 264.1 | 271.24 | 278.57 | 286.09 | 0 | 2977
| FNAP.ELTN.DESIGN.EN Electronics Design Engineer | Rate | 144.21 | 148.11 | 152.11 | 156.22 | 160.43 | 164.76 | 169.21 | 173.78 | 178.48 | 183.3 | 188.26 | 193.34 | 0 | 2012
| FNAP.ELTN.DESIGN.SR Electronics Design Engineer Sr | Rate | 186.02 | 191.05 | 196.21 | 201.51 | 206.94 | 212.53 | 218.27 | 224.17 | 230.22 | 236.45 | 242.84 | 249.4 | 0 | 2596
| FNAP.ENGNRING.PHYST Engineering Physicist | Rate | 153.85 | 158.01 | 162.28 | 166.66 | 171.16 | 175.77 | 180.53 | 185.4 | 190.41 | 195.56 | 200.85 | 206.27 | 0 | 2147
| FNAP.FACILITIES.MGMT Facilities Management | Rate | 129.89 | 133.4 | 137 | 140.7 | 144.5 | 148.39 | 152.41 | 156.52 | 160.75 | 165.1 | 169.56 | 174.14 | 0 | 1812
| FNAP.GENERAL.ADMIN General Administrative | Rate | 94.42 | 96.98 | 99.59 | 102.29 | 105.04 | 107.88 | 110.79 | 113.79 | 116.86 | 120.02 | 123.27 | 126.59 | 0 | 1318
| FNAP.MAGNT.SCIENTIST Magnet Scientist | Rate | 157.21 | 161.46 | 165.82 | 170.3 | 174.89 | 179.61 | 184.46 | 189.44 | 194.57 | 199.83 | 205.23 | 210.77 | 0 | 2194
| FNAP.MECH.ASMBY.TECH Mechanical Assembly Technician | Rate | 88.13 | 90.52 | 92.96 | 95.47 | 98.05 | 100.69 | 103.41 | 106.21 | 109.08 | 112.03 | 115.05 | 118.16 | 0 | 1230
| FNAP.MECH.DESIGN.EN Mechanical Design Engineer | Rate | 142.55 | 146.41 | 150.36 | 154.42 | 158.59 | 162.86 | 167.27 | 171.78 | 176.43 | 181.2 | 186.1 | 191.12 | 0 | 1989
| FNAP.MECH.DESIGN.SR Mechanical Design Engineer Sr | Rate | 180.42 | 185.3 | 190.3 | 195.44 | 200.71 | 206.13 | 211.7 | 217.42 | 223.29 | 229.33 | 235.53 | 241.89 | 0 | 2517
| FNAP.PA.EXP.RA Particle-Astro Experimental Research Associate | Rate | 92.95 | 95.47 | 98.04 | 100.69 | 103.41 | 106.2 | 109.07 | 112.01 | 115.04 | 118.15 | 121.35 | 124.62 | 0 | 1297
| FNAP.PA.THY.RA Particle-Astro Theory Research Associate | Rate | 92.95 | 95.47 | 98.04 | 100.69 | 103.41 | 106.2 | 109.07 | 112.01 | 115.04 | 118.15 | 121.35 | 124.62 | 0 | 1297
| FNAP.PRJ.MNGR Project Manager | Rate | 159.01 | 163.31 | 167.72 | 172.25 | 176.9 | 181.67 | 186.58 | 191.62 | 196.8 | 202.12 | 207.58 | 213.18 | 0 | 2219
| FNAP.PRJ.MNGR.EXC Project Manager Exec | Rate | 299.85 | 307.95 | 316.27 | 324.82 | 333.58 | 342.57 | 351.83 | 361.33 | 371.1 | 381.14 | 391.44 | 402.01 | 0 | 4184
| FNAP.PRJ.MNGR.SR Project Manager Sr | Rate | 239.88 | 246.36 | 253.01 | 259.85 | 266.86 | 274.06 | 281.47 | 289.07 | 296.88 | 304.91 | 313.15 | 321.61 | 0 | 3347
| FNAP.PT.EXP.PHYST Particle Physicist Experimental | Rate | 140.24 | 144.03 | 147.92 | 151.92 | 156.02 | 160.22 | 164.56 | 169 | 173.57 | 178.26 | 183.08 | 188.02 | 0 | 1957
| FNAP.PT.EXP.RA Particle Physics Experimental Research Associate | Rate | 92.95 | 95.47 | 98.04 | 100.69 | 103.41 | 106.2 | 109.07 | 112.01 | 115.04 | 118.15 | 121.35 | 124.62 | 0 | 1297
| FNAP.PT.THY.RA Particle Physics Theory Research Associate | Rate | 92.95 | 95.47 | 98.04 | 100.69 | 103.41 | 106.2 | 109.07 | 112.01 | 115.04 | 118.15 | 121.35 | 124.62 | 0 | 1297
| FNAP.RF.DESIGN.EN RF Design Engineer | Rate | 150.84 | 154.91 | 159.1 | 163.4 | 167.8 | 172.33 | 176.99 | 181.77 | 186.68 | 191.73 | 196.91 | 202.23 | 0 | 2105
| FNAP.RF.DESIGN.SR RF Design Engineer Sr | Rate | 185.81 | 190.83 | 195.99 | 201.28 | 206.71 | 212.29 | 218.03 | 223.91 | 229.97 | 236.18 | 242.57 | 249.12 | 0 | 2593
| FNAP.RF.RA RF Research Associate | Rate | 92.95 | 95.47 | 98.04 | 100.69 | 103.41 | 106.2 | 109.07 | 112.01 | 115.04 | 118.15 | 121.35 | 124.62 | 0 | 1297
| FNAP.RF.SCIENTIST RF Scientist | Rate | 173.16 | 177.84 | 182.64 | 187.57 | 192.63 | 197.83 | 203.17 | 208.66 | 214.3 | 220.1 | 226.05 | 232.15 | 0 | 2416
| FNAP.SYSTM.ADMIN Systems Administrator | Rate | 119.3 | 122.53 | 125.84 | 129.24 | 132.72 | 136.3 | 139.99 | 143.77 | 147.65 | 151.65 | 155.75 | 159.95 | 0 | 1665
| FNAP.U.PA.EXP.PHYST Particle-Astro Physicist Experimental Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAP.U.PA.EXP.RA Particle-Astro Experimental Research Associate Uncost | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAP.U.PA.THY.RA Particle-Astro Theory Research Associate Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAP.U.PT.EXP.PHYST Particle Physicist Experimental Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAP.U.PT.EXP.RA Particle Physics Experimental Research Associate Unco | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAP.U.PT.THY.RA Particle Physics Theory Research Associate Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAP.U.RF.RA RF Research Associate Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNAP.U.RF.SCIENTIST RF Scientist Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BS Business Services Section
| FNBS.ACCOUNTANT Accountant | Rate | 97.17 | 99.79 | 102.49 | 105.26 | 108.1 | 111.01 | 114.01 | 117.09 | 120.26 | 123.51 | 126.85 | 130.27 | 0 | 1356
| FNBS.ADMIN.SPPRT Administrative Support | Rate | 59.73 | 61.35 | 63 | 64.7 | 66.45 | 68.24 | 70.09 | 71.98 | 73.92 | 75.92 | 77.98 | 80.08 | 0 | 833
| FNBS.BUSINESS.ADMIN Business Administration | Rate | 91.13 | 93.59 | 96.12 | 98.72 | 101.38 | 104.12 | 106.93 | 109.82 | 112.79 | 115.84 | 118.97 | 122.18 | 0 | 1272
| FNBS.CARPENTER Carpenter | Rate | 59.55 | 61.16 | 62.81 | 64.5 | 66.24 | 68.03 | 69.87 | 71.76 | 73.7 | 75.69 | 77.73 | 79.83 | 0 | 831
| FNBS.CLERICAL Clerical | Rate | 53.52 | 54.96 | 56.45 | 57.97 | 59.53 | 61.14 | 62.79 | 64.49 | 66.23 | 68.02 | 69.86 | 71.75 | 0 | 747
| FNBS.CM.DISPATCHER Communications/Dispatcher | Rate | 39.26 | 40.32 | 41.41 | 42.53 | 43.68 | 44.85 | 46.07 | 47.31 | 48.59 | 49.9 | 51.25 | 52.64 | 0 | 548
| FNBS.DATABASE.AYST Database Administration Analyst | Rate | 109.44 | 112.4 | 115.44 | 118.56 | 121.75 | 125.04 | 128.42 | 131.89 | 135.45 | 139.11 | 142.87 | 146.73 | 0 | 1527
| FNBS.DRIVER Driver | Rate | 53.35 | 54.79 | 56.27 | 57.79 | 59.35 | 60.95 | 62.6 | 64.29 | 66.03 | 67.81 | 69.64 | 71.52 | 0 | 744
| FNBS.ELEC.TECH Electrical Technician | Rate | 69.78 | 71.66 | 73.6 | 75.59 | 77.63 | 79.72 | 81.87 | 84.08 | 86.36 | 88.69 | 91.09 | 93.55 | 0 | 974
| FNBS.FACILITIES.MGMT Facilities Management | Rate | 102.27 | 105.04 | 107.87 | 110.79 | 113.78 | 116.85 | 120.01 | 123.25 | 126.58 | 130 | 133.51 | 137.12 | 0 | 1427
| FNBS.FIREFIGHTER Firefighter | Rate | 47.92 | 49.22 | 50.55 | 51.91 | 53.31 | 54.75 | 56.23 | 57.75 | 59.31 | 60.91 | 62.56 | 64.25 | 0 | 669
| FNBS.GENERAL.ADMIN General Administrative | Rate | 74.35 | 76.36 | 78.42 | 80.54 | 82.71 | 84.94 | 87.24 | 89.6 | 92.02 | 94.51 | 97.06 | 99.68 | 0 | 1037
| FNBS.GENERAL.ES&H General ES&H | Rate | 117.13 | 120.29 | 123.54 | 126.88 | 130.3 | 133.81 | 137.43 | 141.14 | 144.96 | 148.88 | 152.9 | 157.03 | 0 | 1634
| FNBS.HOUSING.ACCOM Housing/Accommodations | Rate | 71.71 | 73.64 | 75.63 | 77.68 | 79.77 | 81.92 | 84.14 | 86.41 | 88.74 | 91.14 | 93.61 | 96.13 | 0 | 1001
| FNBS.LIBRARY Library | Rate | 71.7 | 73.64 | 75.63 | 77.67 | 79.77 | 81.92 | 84.13 | 86.4 | 88.74 | 91.14 | 93.6 | 96.13 | 0 | 1000
| FNBS.LOGISTICS Logistics | Rate | 62.84 | 64.54 | 66.28 | 68.07 | 69.91 | 71.79 | 73.73 | 75.72 | 77.77 | 79.87 | 82.03 | 84.25 | 0 | 877
| FNBS.MATRL.SRVCS Material Services | Rate | 65.24 | 67 | 68.81 | 70.67 | 72.57 | 74.53 | 76.55 | 78.61 | 80.74 | 82.92 | 85.16 | 87.46 | 0 | 910
| FNBS.MECHANIC Mechanic | Rate | 69.13 | 71 | 72.92 | 74.89 | 76.91 | 78.98 | 81.12 | 83.31 | 85.56 | 87.87 | 90.25 | 92.69 | 0 | 965
| FNBS.OPERTNS.FINANCE Operations Finance | Rate | 106.83 | 109.71 | 112.67 | 115.72 | 118.84 | 122.05 | 125.35 | 128.73 | 132.21 | 135.78 | 139.45 | 143.22 | 0 | 1491
| FNBS.PROCUREMENT Procurement | Rate | 90.38 | 92.82 | 95.33 | 97.91 | 100.55 | 103.26 | 106.05 | 108.91 | 111.86 | 114.88 | 117.99 | 121.17 | 0 | 1261
| FNBS.SECURTY Security | Rate | 84.01 | 86.28 | 88.61 | 91.01 | 93.46 | 95.98 | 98.58 | 101.24 | 103.98 | 106.79 | 109.67 | 112.64 | 0 | 1172
| FNBS.TELECOMMNCATNS Telecommunication | Rate | 82.65 | 84.88 | 87.17 | 89.53 | 91.94 | 94.42 | 96.97 | 99.59 | 102.29 | 105.05 | 107.89 | 110.8 | 0 | 1153
| FNBS.TRAVEL Travel | Rate | 82.22 | 84.44 | 86.72 | 89.06 | 91.47 | 93.93 | 96.47 | 99.08 | 101.75 | 104.51 | 107.33 | 110.23 | 0 | 1147
| FNBS.U.GENERAL.ES&H General ES&H Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNBS.U.PROCUREMENT Procurement Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNBS.WEB.APPS.DEVLPR Web Applications Developer | Rate | 75.9 | 77.95 | 80.05 | 82.22 | 84.44 | 86.71 | 89.06 | 91.46 | 93.93 | 96.47 | 99.08 | 101.76 | 0 | 1059
CD Computing Division
| FNCD.AC.EXP.RA Accelerator Experimental Research Associate | Rate | 82.19 | 84.42 | 86.69 | 89.04 | 91.44 | 93.9 | 96.44 | 99.05 | 101.73 | 104.48 | 107.3 | 110.2 | 0 | 1147
| FNCD.AC.THY.PHYST Accelerator Physicist Theory | Rate | 148.62 | 152.64 | 156.76 | 161 | 165.34 | 169.8 | 174.39 | 179.1 | 183.94 | 188.91 | 194.02 | 199.26 | 0 | 2074
| FNCD.AC.THY.RA Accelerator Theory Research Associate | Rate | 82.19 | 84.42 | 86.69 | 89.04 | 91.44 | 93.9 | 96.44 | 99.05 | 101.73 | 104.48 | 107.3 | 110.2 | 0 | 1147
| FNCD.ACCOUNTANT Accountant | Rate | 109.12 | 112.07 | 115.09 | 118.2 | 121.39 | 124.67 | 128.04 | 131.49 | 135.05 | 138.7 | 142.45 | 146.29 | 0 | 1523
| FNCD.ADMIN.SPPRT Administrative Support | Rate | 67.08 | 68.89 | 70.75 | 72.66 | 74.62 | 76.63 | 78.71 | 80.83 | 83.02 | 85.26 | 87.57 | 89.93 | 0 | 936
| FNCD.APDEV.SYSTMAYST Applications Development & Systems Analyst | Rate | 124.22 | 127.58 | 131.02 | 134.56 | 138.19 | 141.92 | 145.75 | 149.69 | 153.74 | 157.89 | 162.16 | 166.54 | 0 | 1733
| FNCD.ASIC.DESIGN.EN ASIC Design Engineer | Rate | 124.39 | 127.75 | 131.2 | 134.75 | 138.38 | 142.11 | 145.95 | 149.89 | 153.95 | 158.11 | 162.38 | 166.77 | 0 | 1736
| FNCD.ASIC.DESIGN.SR ASIC Design Engineer Sr | Rate | 175.01 | 179.74 | 184.59 | 189.58 | 194.69 | 199.94 | 205.35 | 210.89 | 216.59 | 222.45 | 228.46 | 234.63 | 0 | 2442
| FNCD.CLERICAL Clerical | Rate | 60.1 | 61.72 | 63.39 | 65.1 | 66.86 | 68.66 | 70.52 | 72.42 | 74.38 | 76.39 | 78.45 | 80.57 | 0 | 839
| FNCD.CM.WB.COORDNATR Communications Website Coordinator | Rate | 122.68 | 126 | 129.4 | 132.9 | 136.48 | 140.16 | 143.95 | 147.84 | 151.83 | 155.94 | 160.15 | 164.48 | 0 | 1712
| FNCD.CONST.COORDNATR Construction Coordinator | Rate | 115.84 | 118.97 | 122.18 | 125.49 | 128.87 | 132.35 | 135.92 | 139.59 | 143.37 | 147.24 | 151.22 | 155.31 | 0 | 1616
| FNCD.CP.PHYCS.DEVLPR Computational Physics Developer | Rate | 113.12 | 116.17 | 119.31 | 122.53 | 125.84 | 129.23 | 132.73 | 136.31 | 139.99 | 143.78 | 147.67 | 151.65 | 0 | 1578
| FNCD.CRYO.EN Cryogenics Engineer | Rate | 127.99 | 131.45 | 135 | 138.65 | 142.39 | 146.23 | 150.18 | 154.24 | 158.41 | 162.69 | 167.09 | 171.6 | 0 | 1786
| FNCD.CRYO.SR Cryogenics Engineer Sr | Rate | 175.8 | 180.56 | 185.43 | 190.44 | 195.58 | 200.85 | 206.28 | 211.85 | 217.58 | 223.46 | 229.5 | 235.7 | 0 | 2453
| FNCD.CT.SRVCS.SPCLST Computing Services Specialist | Rate | 134.87 | 138.52 | 142.25 | 146.1 | 150.04 | 154.09 | 158.25 | 162.53 | 166.92 | 171.43 | 176.07 | 180.82 | 0 | 1882
| FNCD.CTRL.SYSTM.EN Control System Engineer | Rate | 131.03 | 134.57 | 138.2 | 141.94 | 145.77 | 149.7 | 153.74 | 157.9 | 162.16 | 166.55 | 171.05 | 175.67 | 0 | 1828
| FNCD.CTRL.SYSTM.SR Control System Engineer Sr | Rate | 159.91 | 164.23 | 168.67 | 173.23 | 177.9 | 182.69 | 187.63 | 192.7 | 197.91 | 203.26 | 208.76 | 214.39 | 0 | 2231
| FNCD.DATABASE.AYST Database Administration Analyst | Rate | 122.91 | 126.23 | 129.63 | 133.14 | 136.73 | 140.42 | 144.21 | 148.11 | 152.11 | 156.22 | 160.45 | 164.78 | 0 | 1715
| FNCD.DT.CNTR.OPERTNS Data Center Facilities Operations | Rate | 122.91 | 126.23 | 129.63 | 133.14 | 136.73 | 140.42 | 144.21 | 148.11 | 152.11 | 156.22 | 160.45 | 164.78 | 0 | 1715
| FNCD.ELEC.DESIGN.EN Electrical Design Engineer | Rate | 124.37 | 127.74 | 131.18 | 134.73 | 138.36 | 142.09 | 145.94 | 149.88 | 153.93 | 158.09 | 162.36 | 166.75 | 0 | 1735
| FNCD.ELEC.DESIGN.SR Electrical Design Engineer Sr | Rate | 155.77 | 159.99 | 164.3 | 168.75 | 173.3 | 177.97 | 182.78 | 187.72 | 192.79 | 198 | 203.36 | 208.85 | 0 | 2174
| FNCD.ELEC.DESIGNER Electrical Designer | Rate | 96.07 | 98.67 | 101.33 | 104.07 | 106.88 | 109.76 | 112.73 | 115.77 | 118.9 | 122.12 | 125.42 | 128.8 | 0 | 1341
| FNCD.ELEC.DRAFTER Electrical Drafter | Rate | 67.14 | 68.96 | 70.82 | 72.73 | 74.69 | 76.71 | 78.78 | 80.91 | 83.1 | 85.34 | 87.65 | 90.02 | 0 | 937
| FNCD.ELEC.TECH.MNGR Electrical Technical Manager | Rate | 188.69 | 193.79 | 199.02 | 204.4 | 209.91 | 215.57 | 221.4 | 227.38 | 233.53 | 239.84 | 246.33 | 252.98 | 0 | 2633
| FNCD.ELTN.DESIGN.EN Electronics Design Engineer | Rate | 127.52 | 130.96 | 134.5 | 138.14 | 141.86 | 145.69 | 149.62 | 153.66 | 157.82 | 162.09 | 166.47 | 170.96 | 0 | 1779
| FNCD.ELTN.DESIGN.SR Electronics Design Engineer Sr | Rate | 164.49 | 168.94 | 173.5 | 178.19 | 182.99 | 187.93 | 193.01 | 198.22 | 203.58 | 209.08 | 214.73 | 220.53 | 0 | 2295
| FNCD.ELTN.TECH Electronics Technician | Rate | 84.82 | 87.11 | 89.46 | 91.88 | 94.36 | 96.9 | 99.52 | 102.21 | 104.97 | 107.81 | 110.72 | 113.71 | 0 | 1183
| FNCD.ENGNRING.PHYST Engineering Physicist | Rate | 136.04 | 139.72 | 143.49 | 147.37 | 151.35 | 155.43 | 159.63 | 163.94 | 168.37 | 172.93 | 177.6 | 182.39 | 0 | 1898
| FNCD.FACILITIES.MGMT Facilities Management | Rate | 114.85 | 117.96 | 121.14 | 124.42 | 127.77 | 131.22 | 134.77 | 138.4 | 142.15 | 145.99 | 149.94 | 153.98 | 0 | 1603
| FNCD.FUNCTNAL.AYST Functional Analyst | Rate | 113.28 | 116.34 | 119.48 | 122.71 | 126.02 | 129.42 | 132.92 | 136.51 | 140.2 | 143.99 | 147.88 | 151.88 | 0 | 1581
| FNCD.GENERAL.ADMIN General Administrative | Rate | 83.5 | 85.75 | 88.07 | 90.45 | 92.89 | 95.39 | 97.97 | 100.62 | 103.34 | 106.13 | 109 | 111.94 | 0 | 1165
| FNCD.GENERAL.ES&H General ES&H | Rate | 131.53 | 135.09 | 138.74 | 142.49 | 146.33 | 150.27 | 154.34 | 158.5 | 162.79 | 167.19 | 171.71 | 176.35 | 0 | 1835
| FNCD.INTERLOCK.EN Interlock Engineer | Rate | 124.11 | 127.46 | 130.9 | 134.44 | 138.07 | 141.79 | 145.62 | 149.56 | 153.6 | 157.75 | 162.02 | 166.39 | 0 | 1732
| FNCD.INTERLOCK.SR Interlock Engineer Sr | Rate | 154.17 | 158.33 | 162.61 | 167 | 171.51 | 176.13 | 180.89 | 185.78 | 190.8 | 195.96 | 201.25 | 206.69 | 0 | 2151
| FNCD.MAGNT.DESIGN.EN Magnet Design Engineer | Rate | 144.2 | 148.1 | 152.09 | 156.21 | 160.42 | 164.74 | 169.2 | 173.77 | 178.46 | 183.29 | 188.24 | 193.33 | 0 | 2012
| FNCD.MAGNT.DESIGN.SR Magnet Design Engineer Sr | Rate | 158.69 | 162.98 | 167.38 | 171.9 | 176.54 | 181.3 | 186.2 | 191.23 | 196.4 | 201.71 | 207.16 | 212.75 | 0 | 2214
| FNCD.MATRL.EN Materials Engineer | Rate | 79.54 | 81.69 | 83.9 | 86.16 | 88.49 | 90.87 | 93.33 | 95.85 | 98.44 | 101.1 | 103.84 | 106.64 | 0 | 1110
| FNCD.MATRL.SR Materials Engineer Sr | Rate | 79.54 | 81.69 | 83.9 | 86.16 | 88.49 | 90.87 | 93.33 | 95.85 | 98.44 | 101.1 | 103.84 | 106.64 | 0 | 1110
| FNCD.MATRL.SRVCS Material Services | Rate | 73.26 | 75.24 | 77.27 | 79.36 | 81.5 | 83.7 | 85.96 | 88.28 | 90.67 | 93.12 | 95.64 | 98.22 | 0 | 1022
| FNCD.MECH.ANLYSIS.EN Mechanical Analysis Engineer | Rate | 121.17 | 124.44 | 127.8 | 131.26 | 134.8 | 138.43 | 142.17 | 146.01 | 149.96 | 154.02 | 158.18 | 162.45 | 0 | 1691
| FNCD.MECH.ANLYSIS.SR Mechanical Analysis Engineer Sr | Rate | 152.42 | 156.54 | 160.76 | 165.11 | 169.56 | 174.13 | 178.84 | 183.67 | 188.63 | 193.73 | 198.97 | 204.34 | 0 | 2127
| FNCD.MECH.DESIGN.EN Mechanical Design Engineer | Rate | 126.05 | 129.46 | 132.96 | 136.55 | 140.23 | 144.01 | 147.91 | 151.9 | 156.01 | 160.23 | 164.56 | 169 | 0 | 1759
| FNCD.MECH.DESIGN.SR Mechanical Design Engineer Sr | Rate | 159.54 | 163.85 | 168.27 | 172.82 | 177.48 | 182.27 | 187.2 | 192.25 | 197.45 | 202.79 | 208.27 | 213.89 | 0 | 2226
| FNCD.MECH.DESIGNER Mechanical Designer | Rate | 92.65 | 95.15 | 97.72 | 100.36 | 103.07 | 105.85 | 108.71 | 111.65 | 114.66 | 117.77 | 120.95 | 124.21 | 0 | 1293
| FNCD.MECH.DRAFTER Mechanical Drafter | Rate | 54.86 | 56.35 | 57.87 | 59.43 | 61.03 | 62.68 | 64.38 | 66.11 | 67.9 | 69.74 | 71.62 | 73.56 | 0 | 766
| FNCD.MECH.TECH.MNGR Mechanical Technical Manager | Rate | 164.4 | 168.84 | 173.4 | 178.09 | 182.89 | 187.82 | 192.9 | 198.11 | 203.46 | 208.96 | 214.61 | 220.41 | 0 | 2294
| FNCD.NETWORK.AYST Network Analyst | Rate | 127.03 | 130.46 | 133.98 | 137.6 | 141.31 | 145.12 | 149.05 | 153.07 | 157.21 | 161.46 | 165.83 | 170.3 | 0 | 1772
| FNCD.OPERTNS.FINANCE Operations Finance | Rate | 119.96 | 123.21 | 126.53 | 129.95 | 133.46 | 137.06 | 140.76 | 144.56 | 148.47 | 152.49 | 156.61 | 160.84 | 0 | 1674
| FNCD.PA.EXP.PHYST Particle-Astro Physicist Experimental | Rate | 127.92 | 131.38 | 134.93 | 138.58 | 142.31 | 146.15 | 150.1 | 154.16 | 158.32 | 162.6 | 167 | 171.51 | 0 | 1785
| FNCD.PA.EXP.RA Particle-Astro Experimental Research Associate | Rate | 82.19 | 84.42 | 86.69 | 89.04 | 91.44 | 93.9 | 96.44 | 99.05 | 101.73 | 104.48 | 107.3 | 110.2 | 0 | 1147
| FNCD.PA.THY.RA Particle-Astro Theory Research Associate | Rate | 82.19 | 84.42 | 86.69 | 89.04 | 91.44 | 93.9 | 96.44 | 99.05 | 101.73 | 104.48 | 107.3 | 110.2 | 0 | 1147
| FNCD.PC.CUSTM.SPPRT Computer Customer Support | Rate | 86.88 | 89.23 | 91.64 | 94.11 | 96.65 | 99.26 | 101.94 | 104.69 | 107.52 | 110.43 | 113.42 | 116.48 | 0 | 1212
| FNCD.PC.SCI.RESRCHER Computer Science Researcher | Rate | 152.27 | 156.38 | 160.6 | 164.95 | 169.39 | 173.96 | 178.66 | 183.49 | 188.45 | 193.54 | 198.78 | 204.14 | 0 | 2125
| FNCD.PC.SECURTY.AYST Computer Security Analyst | Rate | 143.1 | 146.97 | 150.94 | 155.02 | 159.2 | 163.49 | 167.91 | 172.45 | 177.11 | 181.9 | 186.82 | 191.86 | 0 | 1997
| FNCD.PC.SPPRT.ASSOCT PC Support Associate | Rate | 81.16 | 83.36 | 85.61 | 87.92 | 90.29 | 92.73 | 95.23 | 97.8 | 100.45 | 103.16 | 105.95 | 108.81 | 0 | 1132
| FNCD.PRCESS.CTRL.EN Process/Controls Engineer | Rate | 98.53 | 101.19 | 103.92 | 106.73 | 109.61 | 112.56 | 115.61 | 118.73 | 121.94 | 125.24 | 128.62 | 132.09 | 0 | 1375
| FNCD.PRCESS.CTRL.SR Process/Controls Engineer Sr | Rate | 134.38 | 138.02 | 141.74 | 145.57 | 149.5 | 153.53 | 157.68 | 161.94 | 166.32 | 170.81 | 175.43 | 180.17 | 0 | 1875
| FNCD.PRJ.CTRL.LEAD Project Controls Lead | Rate | 122.71 | 126.02 | 129.43 | 132.93 | 136.51 | 140.19 | 143.98 | 147.87 | 151.87 | 155.97 | 160.19 | 164.51 | 0 | 1712
| FNCD.PRJ.CTRL.MNGR Project Controls Manager | Rate | 167.04 | 171.56 | 176.19 | 180.95 | 185.83 | 190.84 | 196 | 201.29 | 206.73 | 212.32 | 218.06 | 223.95 | 0 | 2331
| FNCD.PRJ.CTRL.SPCLST Project Controls Specialist | Rate | 103.41 | 106.2 | 109.07 | 112.02 | 115.04 | 118.14 | 121.33 | 124.61 | 127.98 | 131.44 | 134.99 | 138.64 | 0 | 1443
| FNCD.PRJ.FINANCE Project Finance | Rate | 118.85 | 122.07 | 125.36 | 128.75 | 132.22 | 135.79 | 139.46 | 143.22 | 147.09 | 151.07 | 155.16 | 159.34 | 0 | 1658
| FNCD.PRJ.MNGR Project Manager | Rate | 140.61 | 144.41 | 148.3 | 152.31 | 156.42 | 160.64 | 164.98 | 169.44 | 174.02 | 178.72 | 183.55 | 188.51 | 0 | 1962
| FNCD.PRJ.MNGR.EXC Project Manager Exec | Rate | 265.14 | 272.31 | 279.66 | 287.22 | 294.96 | 302.92 | 311.11 | 319.51 | 328.15 | 337.02 | 346.13 | 355.48 | 0 | 3700
| FNCD.PRJ.MNGR.SR Project Manager Sr | Rate | 212.11 | 217.85 | 223.73 | 229.78 | 235.97 | 242.34 | 248.89 | 255.61 | 262.52 | 269.62 | 276.9 | 284.38 | 0 | 2960
| FNCD.PRJ.SPPRT Project Support | Rate | 122.77 | 126.09 | 129.49 | 132.99 | 136.58 | 140.26 | 144.06 | 147.94 | 151.94 | 156.05 | 160.27 | 164.6 | 0 | 1713
| FNCD.PROCUREMENT Procurement | Rate | 101.5 | 104.24 | 107.06 | 109.95 | 112.91 | 115.96 | 119.09 | 122.31 | 125.62 | 129.01 | 132.5 | 136.08 | 0 | 1416
| FNCD.PT.EXP.PHYST Particle Physicist Experimental | Rate | 124.01 | 127.36 | 130.8 | 134.34 | 137.96 | 141.68 | 145.51 | 149.44 | 153.48 | 157.63 | 161.89 | 166.26 | 0 | 1730
| FNCD.PT.EXP.RA Particle Physics Experimental Research Associate | Rate | 82.19 | 84.42 | 86.69 | 89.04 | 91.44 | 93.9 | 96.44 | 99.05 | 101.73 | 104.48 | 107.3 | 110.2 | 0 | 1147
| FNCD.PT.THY.PHYST Particle Physicist Theory | Rate | 146.73 | 150.7 | 154.76 | 158.95 | 163.23 | 167.63 | 172.17 | 176.82 | 181.6 | 186.51 | 191.55 | 196.72 | 0 | 2047
| FNCD.PT.THY.RA Particle Physics Theory Research Associate | Rate | 82.19 | 84.42 | 86.69 | 89.04 | 91.44 | 93.9 | 96.44 | 99.05 | 101.73 | 104.48 | 107.3 | 110.2 | 0 | 1147
| FNCD.PUBLIC.RELTIONS Public Relations | Rate | 92.44 | 94.94 | 97.51 | 100.14 | 102.84 | 105.61 | 108.47 | 111.4 | 114.41 | 117.5 | 120.68 | 123.94 | 0 | 1290
| FNCD.RF.DESIGN.EN RF Design Engineer | Rate | 133.38 | 136.98 | 140.68 | 144.48 | 148.38 | 152.38 | 156.5 | 160.73 | 165.07 | 169.54 | 174.12 | 178.82 | 0 | 1861
| FNCD.RF.DESIGN.SR RF Design Engineer Sr | Rate | 164.3 | 168.75 | 173.3 | 177.99 | 182.78 | 187.71 | 192.79 | 197.99 | 203.35 | 208.85 | 214.49 | 220.28 | 0 | 2293
| FNCD.SYSTM.ADMIN Systems Administrator | Rate | 105.5 | 108.35 | 111.27 | 114.28 | 117.36 | 120.53 | 123.78 | 127.13 | 130.56 | 134.09 | 137.72 | 141.44 | 0 | 1472
| FNCD.TRAINING Training | Rate | 110.29 | 113.27 | 116.33 | 119.48 | 122.7 | 126.01 | 129.41 | 132.91 | 136.5 | 140.19 | 143.98 | 147.87 | 0 | 1539
| FNCD.U.GENERAL.ES&H General ES&H Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNCD.U.PA.EXP.PHYST Particle-Astro Physicist Experimental Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNCD.U.PA.EXP.RA Particle-Astro Experimental Research Associate Uncost | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNCD.U.PA.THY.RA Particle-Astro Theory Research Associate Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNCD.U.PROCUREMENT Procurement Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNCD.U.PT.EXP.PHYST Particle Physicist Experimental Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNCD.U.PT.EXP.RA Particle Physics Experimental Research Associate Unco | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNCD.U.PT.THY.PHYST Particle Physicist Theory Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNCD.U.PT.THY.RA Particle Physics Theory Research Associate Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNCD.WEB.APPS.DEVLPR Web Applications Developer | Rate | 85.23 | 87.54 | 89.9 | 92.33 | 94.82 | 97.38 | 100.01 | 102.71 | 105.49 | 108.34 | 111.27 | 114.27 | 0 | 1189
CM CMS - Compact Muon Solenoid Center
| FNCM.AC.EXP.RA Accelerator Experimental Research Associate | Rate | 85.49 | 87.8 | 90.17 | 92.61 | 95.1 | 97.67 | 100.31 | 103.02 | 105.8 | 108.66 | 111.6 | 114.61 | 0 | 1193
| FNCM.AC.THY.RA Accelerator Theory Research Associate | Rate | 85.49 | 87.8 | 90.17 | 92.61 | 95.1 | 97.67 | 100.31 | 103.02 | 105.8 | 108.66 | 111.6 | 114.61 | 0 | 1193
| FNCM.ADMIN.SPPRT Administrative Support | Rate | 69.77 | 71.65 | 73.59 | 75.57 | 77.61 | 79.71 | 81.86 | 84.07 | 86.34 | 88.68 | 91.08 | 93.53 | 0 | 973
| FNCM.FACILITIES.MGMT Facilities Management | Rate | 119.46 | 122.69 | 126 | 129.4 | 132.89 | 136.48 | 140.17 | 143.95 | 147.84 | 151.84 | 155.94 | 160.15 | 0 | 1667
| FNCM.GENERAL.ADMIN General Administrative | Rate | 86.84 | 89.19 | 91.6 | 94.07 | 96.61 | 99.21 | 101.9 | 104.65 | 107.48 | 110.38 | 113.37 | 116.43 | 0 | 1212
| FNCM.PA.EXP.PHYST Particle-Astro Physicist Experimental | Rate | 133.05 | 136.65 | 140.34 | 144.13 | 148.02 | 152.01 | 156.12 | 160.33 | 164.67 | 169.12 | 173.69 | 178.38 | 0 | 1857
| FNCM.PA.EXP.RA Particle-Astro Experimental Research Associate | Rate | 85.49 | 87.8 | 90.17 | 92.61 | 95.1 | 97.67 | 100.31 | 103.02 | 105.8 | 108.66 | 111.6 | 114.61 | 0 | 1193
| FNCM.PA.THY.RA Particle-Astro Theory Research Associate | Rate | 85.49 | 87.8 | 90.17 | 92.61 | 95.1 | 97.67 | 100.31 | 103.02 | 105.8 | 108.66 | 111.6 | 114.61 | 0 | 1193
| FNCM.PT.EXP.PHYST Particle Physicist Experimental | Rate | 128.98 | 132.47 | 136.04 | 139.72 | 143.49 | 147.36 | 151.34 | 155.43 | 159.63 | 163.94 | 168.38 | 172.92 | 0 | 1800
| FNCM.PT.EXP.RA Particle Physics Experimental Research Associate | Rate | 85.49 | 87.8 | 90.17 | 92.61 | 95.1 | 97.67 | 100.31 | 103.02 | 105.8 | 108.66 | 111.6 | 114.61 | 0 | 1193
| FNCM.PT.THY.RA Particle Physics Theory Research Associate | Rate | 85.49 | 87.8 | 90.17 | 92.61 | 95.1 | 97.67 | 100.31 | 103.02 | 105.8 | 108.66 | 111.6 | 114.61 | 0 | 1193
| FNCM.U.PA.EXP.PHYST Particle-Astro Physicist Experimental Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNCM.U.PA.EXP.RA Particle-Astro Experimental Research Associate Uncost | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNCM.U.PA.THY.RA Particle-Astro Theory Research Associate Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNCM.U.PT.EXP.PHYST Particle Physicist Experimental Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNCM.U.PT.EXP.RA Particle Physics Experimental Research Associate Unco | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNCM.U.PT.THY.RA Particle Physics Theory Research Associate Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DO Directorate
| FNDO.ACCOUNTANT Accountant | Rate | 97.17 | 99.79 | 102.49 | 105.26 | 108.1 | 111.01 | 114.01 | 117.09 | 120.26 | 123.51 | 126.85 | 130.27 | 0 | 1356
| FNDO.ADMIN.SPPRT Administrative Support | Rate | 59.73 | 61.35 | 63 | 64.7 | 66.45 | 68.24 | 70.09 | 71.98 | 73.92 | 75.92 | 77.98 | 80.08 | 0 | 833
| FNDO.AUDITOR Audit | Rate | 113.08 | 116.14 | 119.27 | 122.5 | 125.8 | 129.19 | 132.69 | 136.27 | 139.95 | 143.74 | 147.62 | 151.61 | 0 | 1578
| FNDO.CLERICAL Clerical | Rate | 53.52 | 54.96 | 56.45 | 57.97 | 59.53 | 61.14 | 62.79 | 64.49 | 66.23 | 68.02 | 69.86 | 71.75 | 0 | 747
| FNDO.EXECUTIVE.DIRCT Executive Direction | Rate | 309.93 | 318.31 | 326.9 | 335.74 | 344.79 | 354.09 | 363.66 | 373.48 | 383.58 | 393.95 | 404.6 | 415.52 | 0 | 4325
| FNDO.FACILITIES.MGMT Facilities Management | Rate | 102.27 | 105.04 | 107.87 | 110.79 | 113.78 | 116.85 | 120.01 | 123.25 | 126.58 | 130 | 133.51 | 137.12 | 0 | 1427
| FNDO.GENERAL.ADMIN General Administrative | Rate | 74.35 | 76.36 | 78.42 | 80.54 | 82.71 | 84.94 | 87.24 | 89.6 | 92.02 | 94.51 | 97.06 | 99.68 | 0 | 1037
| FNDO.LEGAL Legal | Rate | 157.62 | 161.88 | 166.25 | 170.74 | 175.35 | 180.08 | 184.95 | 189.94 | 195.07 | 200.35 | 205.76 | 211.32 | 0 | 2199
| FNDO.MECH.DESIGN.EN Mechanical Design Engineer | Rate | 112.25 | 115.28 | 118.39 | 121.59 | 124.87 | 128.24 | 131.71 | 135.26 | 138.92 | 142.68 | 146.53 | 150.49 | 0 | 1566
| FNDO.MECH.DESIGN.SR Mechanical Design Engineer Sr | Rate | 142.06 | 145.9 | 149.84 | 153.89 | 158.04 | 162.3 | 166.69 | 171.19 | 175.82 | 180.58 | 185.46 | 190.46 | 0 | 1982
| FNDO.MEDIA.SRVCS Media Services | Rate | 75.12 | 77.15 | 79.23 | 81.38 | 83.57 | 85.82 | 88.15 | 90.53 | 92.97 | 95.49 | 98.07 | 100.72 | 0 | 1048
| FNDO.OPERTNS.FINANCE Operations Finance | Rate | 106.83 | 109.71 | 112.67 | 115.72 | 118.84 | 122.05 | 125.35 | 128.73 | 132.21 | 135.78 | 139.45 | 143.22 | 0 | 1491
| FNDO.PRJ.CTRL.LEAD Project Controls Lead | Rate | 109.27 | 112.22 | 115.25 | 118.37 | 121.56 | 124.84 | 128.21 | 131.67 | 135.23 | 138.89 | 142.64 | 146.5 | 0 | 1525
| FNDO.PRJ.CTRL.MNGR Project Controls Manager | Rate | 148.74 | 152.76 | 156.89 | 161.13 | 165.47 | 169.94 | 174.53 | 179.24 | 184.09 | 189.07 | 194.18 | 199.42 | 0 | 2075
| FNDO.PRJ.CTRL.SPCLST Project Controls Specialist | Rate | 92.08 | 94.57 | 97.12 | 99.75 | 102.44 | 105.2 | 108.04 | 110.96 | 113.96 | 117.04 | 120.21 | 123.45 | 0 | 1285
| FNDO.PRJ.FINANCE Project Finance | Rate | 105.83 | 108.7 | 111.63 | 114.65 | 117.74 | 120.91 | 124.18 | 127.54 | 130.98 | 134.53 | 138.16 | 141.89 | 0 | 1477
| FNDO.PRJ.MNGR Project Manager | Rate | 125.21 | 128.59 | 132.06 | 135.63 | 139.29 | 143.04 | 146.91 | 150.88 | 154.96 | 159.15 | 163.45 | 167.86 | 0 | 1747
| FNDO.PRJ.MNGR.EXC Project Manager Exec | Rate | 236.1 | 242.48 | 249.03 | 255.76 | 262.66 | 269.74 | 277.03 | 284.51 | 292.21 | 300.11 | 308.22 | 316.54 | 0 | 3294
| FNDO.PRJ.MNGR.SR Project Manager Sr | Rate | 188.88 | 193.99 | 199.22 | 204.61 | 210.13 | 215.79 | 221.63 | 227.61 | 233.76 | 240.09 | 246.57 | 253.23 | 0 | 2636
| FNDO.PRJ.SPPRT Project Support | Rate | 109.32 | 112.28 | 115.31 | 118.43 | 121.62 | 124.9 | 128.28 | 131.74 | 135.3 | 138.96 | 142.72 | 146.57 | 0 | 1525
| FNDO.PT.EXP.PHYST Particle Physicist Experimental | Rate | 110.43 | 113.41 | 116.47 | 119.62 | 122.85 | 126.16 | 129.57 | 133.07 | 136.67 | 140.36 | 144.16 | 148.05 | 0 | 1541
| FNDO.PUBLIC.RELTIONS Public Relations | Rate | 82.32 | 84.54 | 86.83 | 89.17 | 91.58 | 94.05 | 96.59 | 99.2 | 101.88 | 104.63 | 107.46 | 110.36 | 0 | 1149
| FNDO.QLTY.ASSRANCE Quality Assurance | Rate | 120.36 | 123.61 | 126.95 | 130.38 | 133.89 | 137.51 | 141.22 | 145.04 | 148.96 | 152.99 | 157.12 | 161.36 | 0 | 1679
| FNDO.U.PT.EXP.PHYST Particle Physicist Experimental Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNDO.WEB.APPS.DEVLPR Web Applications Developer | Rate | 75.9 | 77.95 | 80.05 | 82.22 | 84.44 | 86.71 | 89.06 | 91.46 | 93.93 | 96.47 | 99.08 | 101.76 | 0 | 1059
ES ES&H
| FNES.ACCOUNTANT Accountant | Rate | 97.17 | 99.79 | 102.49 | 105.26 | 108.1 | 111.01 | 114.01 | 117.09 | 120.26 | 123.51 | 126.85 | 130.27 | 0 | 1356
| FNES.ADMIN.SPPRT Administrative Support | Rate | 59.73 | 61.35 | 63 | 64.7 | 66.45 | 68.24 | 70.09 | 71.98 | 73.92 | 75.92 | 77.98 | 80.08 | 0 | 833
| FNES.CLERICAL Clerical | Rate | 53.52 | 54.96 | 56.45 | 57.97 | 59.53 | 61.14 | 62.79 | 64.49 | 66.23 | 68.02 | 69.86 | 71.75 | 0 | 747
| FNES.CONST.SAFETY Construction Safety | Rate | 102.35 | 105.11 | 107.95 | 110.87 | 113.86 | 116.93 | 120.09 | 123.33 | 126.67 | 130.09 | 133.61 | 137.22 | 0 | 1428
| FNES.DATABASE.AYST Database Administration Analyst | Rate | 109.44 | 112.4 | 115.44 | 118.56 | 121.75 | 125.04 | 128.42 | 131.89 | 135.45 | 139.11 | 142.87 | 146.73 | 0 | 1527
| FNES.DRIVER Driver | Rate | 53.35 | 54.79 | 56.27 | 57.79 | 59.35 | 60.95 | 62.6 | 64.29 | 66.03 | 67.81 | 69.64 | 71.52 | 0 | 744
| FNES.ELEC.DESIGN.EN Electrical Design Engineer | Rate | 110.75 | 113.75 | 116.82 | 119.97 | 123.21 | 126.53 | 129.95 | 133.46 | 137.07 | 140.78 | 144.58 | 148.48 | 0 | 1545
| FNES.ELEC.DESIGN.SR Electrical Design Engineer Sr | Rate | 138.71 | 142.46 | 146.31 | 150.26 | 154.31 | 158.48 | 162.76 | 167.16 | 171.67 | 176.32 | 181.08 | 185.97 | 0 | 1935
| FNES.ELEC.SAFETY Electrical Safety | Rate | 104.65 | 107.48 | 110.38 | 113.37 | 116.42 | 119.56 | 122.8 | 126.11 | 129.52 | 133.02 | 136.62 | 140.31 | 0 | 1460
| FNES.ELTN.DESIGN.EN Electronics Design Engineer | Rate | 113.55 | 116.62 | 119.77 | 123.01 | 126.32 | 129.73 | 133.24 | 136.83 | 140.53 | 144.33 | 148.23 | 152.24 | 0 | 1584
| FNES.ELTN.DESIGN.SR Electronics Design Engineer Sr | Rate | 146.47 | 150.43 | 154.49 | 158.67 | 162.95 | 167.34 | 171.87 | 176.51 | 181.28 | 186.18 | 191.21 | 196.38 | 0 | 2044
| FNES.ELTN.TECH Electronics Technician | Rate | 75.53 | 77.57 | 79.66 | 81.82 | 84.02 | 86.29 | 88.62 | 91.01 | 93.47 | 96 | 98.6 | 101.26 | 0 | 1054
| FNES.EMRGNCY.PLANNER Emergency Planner | Rate | 101.17 | 103.9 | 106.71 | 109.59 | 112.55 | 115.58 | 118.71 | 121.91 | 125.21 | 128.59 | 132.07 | 135.63 | 0 | 1412
| FNES.ENVIRNMENTAL Environmental | Rate | 105.74 | 108.6 | 111.53 | 114.54 | 117.63 | 120.8 | 124.07 | 127.42 | 130.87 | 134.4 | 138.04 | 141.76 | 0 | 1475
| FNES.FACILITIES.MGMT Facilities Management | Rate | 102.27 | 105.04 | 107.87 | 110.79 | 113.78 | 116.85 | 120.01 | 123.25 | 126.58 | 130 | 133.51 | 137.12 | 0 | 1427
| FNES.GENERAL.ADMIN General Administrative | Rate | 74.35 | 76.36 | 78.42 | 80.54 | 82.71 | 84.94 | 87.24 | 89.6 | 92.02 | 94.51 | 97.06 | 99.68 | 0 | 1037
| FNES.GENERAL.ES&H General ES&H | Rate | 117.13 | 120.29 | 123.54 | 126.88 | 130.3 | 133.81 | 137.43 | 141.14 | 144.96 | 148.88 | 152.9 | 157.03 | 0 | 1634
| FNES.INDSTRL.HYGT Industrial Hygienist | Rate | 103.25 | 106.04 | 108.91 | 111.85 | 114.87 | 117.96 | 121.15 | 124.42 | 127.79 | 131.24 | 134.79 | 138.43 | 0 | 1441
| FNES.LABORTY.ANLYSIS Laboratory Analysis | Rate | 99.51 | 102.2 | 104.96 | 107.8 | 110.7 | 113.69 | 116.76 | 119.91 | 123.15 | 126.48 | 129.9 | 133.41 | 0 | 1388
| FNES.OCCUP.NURSE Occupational Medicine Nurse | Rate | 67.93 | 69.77 | 71.65 | 73.59 | 75.57 | 77.61 | 79.71 | 81.86 | 84.08 | 86.35 | 88.68 | 91.08 | 0 | 948
| FNES.OCCUP.PHYSICIAN Occupational Medicine Physician | Rate | 228.81 | 234.99 | 241.33 | 247.86 | 254.54 | 261.41 | 268.47 | 275.72 | 283.18 | 290.83 | 298.69 | 306.76 | 0 | 3193
| FNES.OPERTNS.FINANCE Operations Finance | Rate | 106.83 | 109.71 | 112.67 | 115.72 | 118.84 | 122.05 | 125.35 | 128.73 | 132.21 | 135.78 | 139.45 | 143.22 | 0 | 1491
| FNES.PA.EXP.PHYST Particle-Astro Physicist Experimental | Rate | 113.91 | 116.99 | 120.15 | 123.4 | 126.73 | 130.14 | 133.66 | 137.27 | 140.98 | 144.79 | 148.71 | 152.72 | 0 | 1589
| FNES.RAD.PRTECTON Radiation Protection | Rate | 96.92 | 99.54 | 102.23 | 104.99 | 107.82 | 110.73 | 113.72 | 116.8 | 119.95 | 123.2 | 126.53 | 129.94 | 0 | 1352
| FNES.SAFETY Safety | Rate | 104.65 | 107.48 | 110.38 | 113.37 | 116.42 | 119.56 | 122.8 | 126.11 | 129.52 | 133.02 | 136.62 | 140.31 | 0 | 1460
| FNES.SYSTM.ADMIN Systems Administrator | Rate | 93.94 | 96.48 | 99.08 | 101.76 | 104.51 | 107.32 | 110.23 | 113.2 | 116.26 | 119.41 | 122.63 | 125.95 | 0 | 1311
| FNES.TRAINING Training | Rate | 98.21 | 100.87 | 103.59 | 106.39 | 109.26 | 112.21 | 115.24 | 118.35 | 121.55 | 124.84 | 128.21 | 131.67 | 0 | 1370
| FNES.U.CONST.SAFETY Construction Safety Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNES.U.ENVIRNMENTAL Environmental Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNES.U.GENERAL.ES&H General ES&H Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNES.U.INDSTRL.HYGT Industrial Hygienist Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNES.U.RAD.PRTECTON Radiation Protection Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNES.U.SAFETY Safety Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNES.WASTE.MANAGEMNT Waste Management | Rate | 72.53 | 74.49 | 76.5 | 78.57 | 80.69 | 82.86 | 85.1 | 87.4 | 89.76 | 92.19 | 94.68 | 97.24 | 0 | 1012
FE FESS
| FNFE.ACCOUNTANT Accountant | Rate | 97.17 | 99.79 | 102.49 | 105.26 | 108.1 | 111.01 | 114.01 | 117.09 | 120.26 | 123.51 | 126.85 | 130.27 | 0 | 1356
| FNFE.ADMIN.SPPRT Administrative Support | Rate | 59.73 | 61.35 | 63 | 64.7 | 66.45 | 68.24 | 70.09 | 71.98 | 73.92 | 75.92 | 77.98 | 80.08 | 0 | 833
| FNFE.APDEV.SYSTMAYST Applications Development & Systems Analyst | Rate | 110.61 | 113.6 | 116.67 | 119.82 | 123.05 | 126.37 | 129.79 | 133.29 | 136.9 | 140.6 | 144.4 | 148.3 | 0 | 1543
| FNFE.BUILDING.SRVCS Building Services | Rate | 76.4 | 78.47 | 80.58 | 82.76 | 84.99 | 87.29 | 89.65 | 92.07 | 94.56 | 97.11 | 99.74 | 102.43 | 0 | 1066
| FNFE.BUSINESS.ADMIN Business Administration | Rate | 91.13 | 93.59 | 96.12 | 98.72 | 101.38 | 104.12 | 106.93 | 109.82 | 112.79 | 115.84 | 118.97 | 122.18 | 0 | 1272
| FNFE.CFS.DESIGN.EN CFS Design Engineer | Rate | 159.17 | 163.47 | 167.88 | 172.42 | 177.07 | 181.85 | 186.76 | 191.81 | 196.99 | 202.32 | 207.79 | 213.4 | 0 | 2221
| FNFE.CFS.OPERTNS.EN CFS Operations Engineer | Rate | 94.31 | 96.86 | 99.48 | 102.17 | 104.92 | 107.75 | 110.66 | 113.65 | 116.72 | 119.88 | 123.12 | 126.44 | 0 | 1316
| FNFE.CFS.OPERTNS.SR CFS Operations Engineer Sr | Rate | 103.59 | 106.4 | 109.27 | 112.22 | 115.25 | 118.35 | 121.55 | 124.84 | 128.21 | 131.68 | 135.24 | 138.89 | 0 | 1445
| FNFE.CFS.TECH.MNGR CFS Technical Manager | Rate | 169.9 | 174.49 | 179.2 | 184.05 | 189.01 | 194.11 | 199.35 | 204.74 | 210.27 | 215.96 | 221.79 | 227.78 | 0 | 2371
| FNFE.CLERICAL Clerical | Rate | 53.52 | 54.96 | 56.45 | 57.97 | 59.53 | 61.14 | 62.79 | 64.49 | 66.23 | 68.02 | 69.86 | 71.75 | 0 | 747
| FNFE.CONST.COORDNATR Construction Coordinator | Rate | 159.17 | 163.47 | 167.88 | 172.42 | 177.07 | 181.85 | 186.76 | 191.81 | 196.99 | 202.32 | 207.79 | 213.4 | 0 | 2221
| FNFE.CONST.SAFETY Construction Safety | Rate | 102.35 | 105.11 | 107.95 | 110.87 | 113.86 | 116.93 | 120.09 | 123.33 | 126.67 | 130.09 | 133.61 | 137.22 | 0 | 1428
| FNFE.FACILITIES.MGMT Facilities Management | Rate | 102.27 | 105.04 | 107.87 | 110.79 | 113.78 | 116.85 | 120.01 | 123.25 | 126.58 | 130 | 133.51 | 137.12 | 0 | 1427
| FNFE.GENERAL.ADMIN General Administrative | Rate | 74.35 | 76.36 | 78.42 | 80.54 | 82.71 | 84.94 | 87.24 | 89.6 | 92.02 | 94.51 | 97.06 | 99.68 | 0 | 1037
| FNFE.GENERAL.ES&H General ES&H | Rate | 117.13 | 120.29 | 123.54 | 126.88 | 130.3 | 133.81 | 137.43 | 141.14 | 144.96 | 148.88 | 152.9 | 157.03 | 0 | 1634
| FNFE.GEOG.INFO.SYSTM Geographic Information System | Rate | 71.72 | 73.66 | 75.65 | 77.69 | 79.79 | 81.94 | 84.16 | 86.43 | 88.77 | 91.17 | 93.63 | 96.16 | 0 | 1001
| FNFE.GROUNDS.KEEPER Groundskeeping | Rate | 55.92 | 57.43 | 58.98 | 60.57 | 62.21 | 63.88 | 65.61 | 67.38 | 69.2 | 71.07 | 73 | 74.97 | 0 | 780
| FNFE.MAINTENANCE Maintenance | Rate | 72.9 | 74.87 | 76.89 | 78.97 | 81.1 | 83.28 | 85.53 | 87.84 | 90.22 | 92.66 | 95.16 | 97.73 | 0 | 1017
| FNFE.MATRL.SRVCS Material Services | Rate | 65.24 | 67 | 68.81 | 70.67 | 72.57 | 74.53 | 76.55 | 78.61 | 80.74 | 82.92 | 85.16 | 87.46 | 0 | 910
| FNFE.MECHANIC Mechanic | Rate | 69.13 | 71 | 72.92 | 74.89 | 76.91 | 78.98 | 81.12 | 83.31 | 85.56 | 87.87 | 90.25 | 92.69 | 0 | 965
| FNFE.OPERTNS.FINANCE Operations Finance | Rate | 106.83 | 109.71 | 112.67 | 115.72 | 118.84 | 122.05 | 125.35 | 128.73 | 132.21 | 135.78 | 139.45 | 143.22 | 0 | 1491
| FNFE.PRJ.CTRL.LEAD Project Controls Lead | Rate | 109.27 | 112.22 | 115.25 | 118.37 | 121.56 | 124.84 | 128.21 | 131.67 | 135.23 | 138.89 | 142.64 | 146.5 | 0 | 1525
| FNFE.PRJ.CTRL.MNGR Project Controls Manager | Rate | 148.74 | 152.76 | 156.89 | 161.13 | 165.47 | 169.94 | 174.53 | 179.24 | 184.09 | 189.07 | 194.18 | 199.42 | 0 | 2075
| FNFE.PRJ.CTRL.SPCLST Project Controls Specialist | Rate | 92.08 | 94.57 | 97.12 | 99.75 | 102.44 | 105.2 | 108.04 | 110.96 | 113.96 | 117.04 | 120.21 | 123.45 | 0 | 1285
| FNFE.PRJ.FINANCE Project Finance | Rate | 105.83 | 108.7 | 111.63 | 114.65 | 117.74 | 120.91 | 124.18 | 127.54 | 130.98 | 134.53 | 138.16 | 141.89 | 0 | 1477
| FNFE.PRJ.MNGR Project Manager | Rate | 125.21 | 128.59 | 132.06 | 135.63 | 139.29 | 143.04 | 146.91 | 150.88 | 154.96 | 159.15 | 163.45 | 167.86 | 0 | 1747
| FNFE.PRJ.MNGR.EXC Project Manager Exec | Rate | 236.1 | 242.48 | 249.03 | 255.76 | 262.66 | 269.74 | 277.03 | 284.51 | 292.21 | 300.11 | 308.22 | 316.54 | 0 | 3294
| FNFE.PRJ.MNGR.SR Project Manager Sr | Rate | 188.88 | 193.99 | 199.22 | 204.61 | 210.13 | 215.79 | 221.63 | 227.61 | 233.76 | 240.09 | 246.57 | 253.23 | 0 | 2636
| FNFE.PRJ.SPPRT Project Support | Rate | 109.32 | 112.28 | 115.31 | 118.43 | 121.62 | 124.9 | 128.28 | 131.74 | 135.3 | 138.96 | 142.72 | 146.57 | 0 | 1525
| FNFE.SAFETY Safety | Rate | 104.65 | 107.48 | 110.38 | 113.37 | 116.42 | 119.56 | 122.8 | 126.11 | 129.52 | 133.02 | 136.62 | 140.31 | 0 | 1460
| FNFE.U.CONST.SAFETY Construction Safety Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNFE.U.GENERAL.ES&H General ES&H Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNFE.U.SAFETY Safety Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FI Finance
| FNFI.ACCOUNTANT Accountant | Rate | 97.17 | 99.79 | 102.49 | 105.26 | 108.1 | 111.01 | 114.01 | 117.09 | 120.26 | 123.51 | 126.85 | 130.27 | 0 | 1356
| FNFI.ADMIN.SPPRT Administrative Support | Rate | 59.73 | 61.35 | 63 | 64.7 | 66.45 | 68.24 | 70.09 | 71.98 | 73.92 | 75.92 | 77.98 | 80.08 | 0 | 833
| FNFI.CLERICAL Clerical | Rate | 53.52 | 54.96 | 56.45 | 57.97 | 59.53 | 61.14 | 62.79 | 64.49 | 66.23 | 68.02 | 69.86 | 71.75 | 0 | 747
| FNFI.EXECUTIVE.DIRCT Executive Direction | Rate | 309.93 | 318.31 | 326.9 | 335.74 | 344.79 | 354.09 | 363.66 | 373.48 | 383.58 | 393.95 | 404.6 | 415.52 | 0 | 4325
| FNFI.FACILITIES.MGMT Facilities Management | Rate | 102.27 | 105.04 | 107.87 | 110.79 | 113.78 | 116.85 | 120.01 | 123.25 | 126.58 | 130 | 133.51 | 137.12 | 0 | 1427
| FNFI.FUNCTNAL.AYST Functional Analyst | Rate | 100.87 | 103.6 | 106.4 | 109.27 | 112.22 | 115.25 | 118.36 | 121.56 | 124.84 | 128.22 | 131.68 | 135.24 | 0 | 1408
| FNFI.GENERAL.ADMIN General Administrative | Rate | 74.35 | 76.36 | 78.42 | 80.54 | 82.71 | 84.94 | 87.24 | 89.6 | 92.02 | 94.51 | 97.06 | 99.68 | 0 | 1037
| FNFI.OPERTNS.FINANCE Operations Finance | Rate | 106.83 | 109.71 | 112.67 | 115.72 | 118.84 | 122.05 | 125.35 | 128.73 | 132.21 | 135.78 | 139.45 | 143.22 | 0 | 1491
FN Fermi Escalated Values
| FN.S.PRJ.CTRL.ENTRY Project Controls Entry | Rate | 107.29 | 110.19 | 113.17 | 116.22 | 119.36 | 122.58 | 125.89 | 129.29 | 132.79 | 136.38 | 140.06 | 143.84 | 0 | 1497
| FN.S.PRJ.CTRL.MID Project Controls Mid | Rate | 137.09 | 140.8 | 144.6 | 148.51 | 152.51 | 156.63 | 160.86 | 165.2 | 169.67 | 174.26 | 178.97 | 183.8 | 0 | 1913
| FN.S.PRJ.CTRL.SR Project Controls Sr | Rate | 166.9 | 171.41 | 176.03 | 180.79 | 185.67 | 190.68 | 195.83 | 201.12 | 206.56 | 212.14 | 217.87 | 223.76 | 0 | 2329
LB LBNE Project
| FNLB.CFS.TECH.MNGR CFS Technical Manager | Rate | 169.9 | 174.49 | 179.2 | 184.05 | 189.01 | 194.11 | 199.35 | 204.74 | 210.27 | 215.96 | 221.79 | 227.78 | 0 | 2371
| FNLB.ELEC.DESIGN.EN Electrical Design Engineer | Rate | 110.75 | 113.75 | 116.82 | 119.97 | 123.21 | 126.53 | 129.95 | 133.46 | 137.07 | 140.78 | 144.58 | 148.48 | 0 | 1545
| FNLB.ELEC.DESIGN.SR Electrical Design Engineer Sr | Rate | 138.71 | 142.46 | 146.31 | 150.26 | 154.31 | 158.48 | 162.76 | 167.16 | 171.67 | 176.32 | 181.08 | 185.97 | 0 | 1935
| FNLB.PRJ.CTRL.LEAD Project Controls Lead | Rate | 109.27 | 112.22 | 115.25 | 118.37 | 121.56 | 124.84 | 128.21 | 131.67 | 135.23 | 138.89 | 142.64 | 146.5 | 0 | 1525
| FNLB.PRJ.CTRL.MNGR Project Controls Manager | Rate | 148.74 | 152.76 | 156.89 | 161.13 | 165.47 | 169.94 | 174.53 | 179.24 | 184.09 | 189.07 | 194.18 | 199.42 | 0 | 2075
| FNLB.PRJ.CTRL.SPCLST Project Controls Specialist | Rate | 92.08 | 94.57 | 97.12 | 99.75 | 102.44 | 105.2 | 108.04 | 110.96 | 113.96 | 117.04 | 120.21 | 123.45 | 0 | 1285
| FNLB.PRJ.FINANCE Project Finance | Rate | 105.84 | 108.71 | 111.64 | 114.66 | 117.75 | 120.92 | 124.19 | 127.55 | 131 | 134.54 | 138.17 | 141.91 | 0 | 1477
| FNLB.PRJ.MNGR Project Manager | Rate | 125.21 | 128.59 | 132.06 | 135.63 | 139.29 | 143.04 | 146.91 | 150.88 | 154.96 | 159.15 | 163.45 | 167.86 | 0 | 1747
| FNLB.PRJ.MNGR.EXC Project Manager Exec | Rate | 236.1 | 242.48 | 249.03 | 255.76 | 262.66 | 269.74 | 277.03 | 284.51 | 292.21 | 300.11 | 308.22 | 316.54 | 0 | 3294
| FNLB.PRJ.MNGR.SR Project Manager Sr | Rate | 188.88 | 193.99 | 199.22 | 204.61 | 210.13 | 215.79 | 221.63 | 227.61 | 233.76 | 240.09 | 246.57 | 253.23 | 0 | 2636
| FNLB.PRJ.SPPRT Project Support | Rate | 109.32 | 112.27 | 115.3 | 118.42 | 121.61 | 124.89 | 128.27 | 131.73 | 135.29 | 138.95 | 142.71 | 146.56 | 0 | 1525
OF Office of the CIO
| FNOF.ADMIN.SPPRT Administrative Support | Rate | 59.73 | 61.35 | 63 | 64.7 | 66.45 | 68.24 | 70.09 | 71.98 | 73.92 | 75.92 | 77.98 | 80.08 | 0 | 833
| FNOF.APDEV.SYSTMAYST Applications Development & Systems Analyst | Rate | 110.61 | 113.6 | 116.67 | 119.82 | 123.05 | 126.37 | 129.79 | 133.29 | 136.9 | 140.6 | 144.4 | 148.3 | 0 | 1543
| FNOF.CT.SRVCS.SPCLST Computing Services Specialist | Rate | 120.1 | 123.34 | 126.67 | 130.1 | 133.61 | 137.21 | 140.92 | 144.72 | 148.64 | 152.66 | 156.78 | 161.01 | 0 | 1676
| FNOF.FUNCTNAL.AYST Functional Analyst | Rate | 100.87 | 103.6 | 106.4 | 109.27 | 112.22 | 115.25 | 118.36 | 121.56 | 124.84 | 128.22 | 131.68 | 135.24 | 0 | 1408
| FNOF.OPERTNS.FINANCE Operations Finance | Rate | 106.83 | 109.71 | 112.67 | 115.72 | 118.84 | 122.05 | 125.35 | 128.73 | 132.21 | 135.78 | 139.45 | 143.22 | 0 | 1491
| FNOF.PC.SCI.RESRCHER Computer Science Researcher | Rate | 135.59 | 139.25 | 143.01 | 146.88 | 150.84 | 154.91 | 159.1 | 163.39 | 167.81 | 172.35 | 177 | 181.78 | 0 | 1892
| FNOF.PC.SECURTY.AYST Computer Security Analyst | Rate | 127.43 | 130.88 | 134.41 | 138.04 | 141.76 | 145.59 | 149.52 | 153.56 | 157.71 | 161.98 | 166.35 | 170.85 | 0 | 1778
| FNOF.PRJ.MNGR Project Manager | Rate | 125.21 | 128.59 | 132.06 | 135.63 | 139.29 | 143.04 | 146.91 | 150.88 | 154.96 | 159.15 | 163.45 | 167.86 | 0 | 1747
| FNOF.PRJ.MNGR.EXC Project Manager Exec | Rate | 236.1 | 242.48 | 249.03 | 255.76 | 262.66 | 269.74 | 277.03 | 284.51 | 292.21 | 300.11 | 308.22 | 316.54 | 0 | 3294
| FNOF.PRJ.MNGR.SR Project Manager Sr | Rate | 188.88 | 193.99 | 199.22 | 204.61 | 210.13 | 215.79 | 221.63 | 227.61 | 233.76 | 240.09 | 246.57 | 253.23 | 0 | 2636
| FNOF.PT.EXP.PHYST Particle Physicist Experimental | Rate | 110.43 | 113.41 | 116.47 | 119.62 | 122.85 | 126.16 | 129.57 | 133.07 | 136.67 | 140.36 | 144.16 | 148.05 | 0 | 1541
| FNOF.PUBLIC.RELTIONS Public Relations | Rate | 82.32 | 84.54 | 86.83 | 89.17 | 91.58 | 94.05 | 96.59 | 99.2 | 101.88 | 104.63 | 107.46 | 110.36 | 0 | 1149
| FNOF.U.PT.EXP.PHYST Particle Physicist Experimental Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNOF.WEB.APPS.DEVLPR Web Applications Developer | Rate | 75.9 | 77.95 | 80.05 | 82.22 | 84.44 | 86.71 | 89.06 | 91.46 | 93.93 | 96.47 | 99.08 | 101.76 | 0 | 1059
PA Center for Particle Astrophysics
| FNPA.AC.EXP.RA Accelerator Experimental Research Associate | Rate | 85.49 | 87.8 | 90.17 | 92.61 | 95.1 | 97.67 | 100.31 | 103.02 | 105.8 | 108.66 | 111.6 | 114.61 | 0 | 1193
| FNPA.AC.THY.RA Accelerator Theory Research Associate | Rate | 85.49 | 87.8 | 90.17 | 92.61 | 95.1 | 97.67 | 100.31 | 103.02 | 105.8 | 108.66 | 111.6 | 114.61 | 0 | 1193
| FNPA.ADMIN.SPPRT Administrative Support | Rate | 69.77 | 71.65 | 73.59 | 75.57 | 77.61 | 79.71 | 81.86 | 84.07 | 86.34 | 88.68 | 91.08 | 93.53 | 0 | 973
| FNPA.FACILITIES.MGMT Facilities Management | Rate | 119.46 | 122.69 | 126 | 129.4 | 132.89 | 136.48 | 140.17 | 143.95 | 147.84 | 151.84 | 155.94 | 160.15 | 0 | 1667
| FNPA.GENERAL.ADMIN General Administrative | Rate | 86.84 | 89.19 | 91.6 | 94.07 | 96.61 | 99.21 | 101.9 | 104.65 | 107.48 | 110.38 | 113.37 | 116.43 | 0 | 1212
| FNPA.PA.EXP.PHYST Particle-Astro Physicist Experimental | Rate | 133.05 | 136.65 | 140.34 | 144.13 | 148.02 | 152.01 | 156.12 | 160.33 | 164.67 | 169.12 | 173.69 | 178.38 | 0 | 1857
| FNPA.PA.EXP.RA Particle-Astro Experimental Research Associate | Rate | 85.49 | 87.8 | 90.17 | 92.61 | 95.1 | 97.67 | 100.31 | 103.02 | 105.8 | 108.66 | 111.6 | 114.61 | 0 | 1193
| FNPA.PA.THY.RA Particle-Astro Theory Research Associate | Rate | 85.49 | 87.8 | 90.17 | 92.61 | 95.1 | 97.67 | 100.31 | 103.02 | 105.8 | 108.66 | 111.6 | 114.61 | 0 | 1193
| FNPA.PT.EXP.RA Particle Physics Experimental Research Associate | Rate | 85.49 | 87.8 | 90.17 | 92.61 | 95.1 | 97.67 | 100.31 | 103.02 | 105.8 | 108.66 | 111.6 | 114.61 | 0 | 1193
| FNPA.PT.THY.RA Particle Physics Theory Research Associate | Rate | 85.49 | 87.8 | 90.17 | 92.61 | 95.1 | 97.67 | 100.31 | 103.02 | 105.8 | 108.66 | 111.6 | 114.61 | 0 | 1193
| FNPA.U.PA.EXP.RA Particle-Astro Experimental Research Associate Uncost | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNPA.U.PA.THY.RA Particle-Astro Theory Research Associate Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNPA.U.PT.EXP.RA Particle Physics Experimental Research Associate Unco | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNPA.U.PT.THY.RA Particle Physics Theory Research Associate Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PD Particle Physics Division
| FNPD.AC.EXP.RA Accelerator Experimental Research Associate | Rate | 85.49 | 87.8 | 90.17 | 92.61 | 95.1 | 97.67 | 100.31 | 103.02 | 105.8 | 108.66 | 111.6 | 114.61 | 0 | 1193
| FNPD.AC.SYSTM.SPCLST Accelerator Systems Specialist | Rate | 119.83 | 123.07 | 126.39 | 129.81 | 133.31 | 136.91 | 140.61 | 144.4 | 148.31 | 152.32 | 156.44 | 160.66 | 0 | 1672
| FNPD.AC.THY.RA Accelerator Theory Research Associate | Rate | 85.49 | 87.8 | 90.17 | 92.61 | 95.1 | 97.67 | 100.31 | 103.02 | 105.8 | 108.66 | 111.6 | 114.61 | 0 | 1193
| FNPD.ACCOUNTANT Accountant | Rate | 113.49 | 116.56 | 119.7 | 122.94 | 126.26 | 129.66 | 133.17 | 136.76 | 140.46 | 144.26 | 148.16 | 152.16 | 0 | 1584
| FNPD.ADMIN.SPPRT Administrative Support | Rate | 69.77 | 71.65 | 73.59 | 75.57 | 77.61 | 79.71 | 81.86 | 84.07 | 86.34 | 88.68 | 91.08 | 93.53 | 0 | 973
| FNPD.APDEV.SYSTMAYST Applications Development & Systems Analyst | Rate | 129.2 | 132.69 | 136.27 | 139.95 | 143.73 | 147.6 | 151.59 | 155.69 | 159.9 | 164.22 | 168.66 | 173.21 | 0 | 1803
| FNPD.ASIC.DESIGN.EN ASIC Design Engineer | Rate | 129.37 | 132.87 | 136.46 | 140.14 | 143.92 | 147.8 | 151.8 | 155.9 | 160.11 | 164.44 | 168.89 | 173.45 | 0 | 1805
| FNPD.ASIC.DESIGN.SR ASIC Design Engineer Sr | Rate | 182.02 | 186.94 | 191.98 | 197.18 | 202.49 | 207.95 | 213.57 | 219.34 | 225.27 | 231.36 | 237.62 | 244.03 | 0 | 2540
| FNPD.BUILDING.SRVCS Building Services | Rate | 89.24 | 91.65 | 94.12 | 96.67 | 99.27 | 101.95 | 104.71 | 107.53 | 110.44 | 113.43 | 116.49 | 119.64 | 0 | 1245
| FNPD.CHEMIST Chemist | Rate | 94.49 | 97.04 | 99.66 | 102.36 | 105.12 | 107.95 | 110.87 | 113.87 | 116.94 | 120.11 | 123.35 | 126.68 | 0 | 1318
| FNPD.CLERICAL Clerical | Rate | 62.51 | 64.2 | 65.93 | 67.71 | 69.54 | 71.41 | 73.34 | 75.32 | 77.36 | 79.45 | 81.6 | 83.8 | 0 | 872
| FNPD.CONST.COORDNATR Construction Coordinator | Rate | 120.48 | 123.74 | 127.08 | 130.52 | 134.03 | 137.65 | 141.37 | 145.19 | 149.11 | 153.14 | 157.28 | 161.53 | 0 | 1681
| FNPD.CP.PHYCS.DEVLPR Computational Physics Developer | Rate | 117.65 | 120.83 | 124.09 | 127.44 | 130.88 | 134.41 | 138.04 | 141.77 | 145.6 | 149.54 | 153.58 | 157.73 | 0 | 1642
| FNPD.CRYO.EN Cryogenics Engineer | Rate | 133.12 | 136.72 | 140.41 | 144.21 | 148.09 | 152.09 | 156.2 | 160.42 | 164.75 | 169.21 | 173.78 | 178.48 | 0 | 1857
| FNPD.CRYO.SR Cryogenics Engineer Sr | Rate | 182.85 | 187.79 | 192.86 | 198.07 | 203.42 | 208.9 | 214.55 | 220.34 | 226.3 | 232.42 | 238.7 | 245.15 | 0 | 2551
| FNPD.CRYO.TECH Cryo Technician | Rate | 77.13 | 79.22 | 81.36 | 83.56 | 85.81 | 88.12 | 90.51 | 92.95 | 95.46 | 98.05 | 100.7 | 103.41 | 0 | 1076
| FNPD.CT.SRVCS.SPCLST Computing Services Specialist | Rate | 140.27 | 144.07 | 147.95 | 151.95 | 156.05 | 160.26 | 164.59 | 169.04 | 173.61 | 178.3 | 183.12 | 188.07 | 0 | 1957
| FNPD.CTRL.SYSTM.EN Control System Engineer | Rate | 136.28 | 139.96 | 143.74 | 147.63 | 151.61 | 155.7 | 159.91 | 164.22 | 168.66 | 173.22 | 177.91 | 182.71 | 0 | 1902
| FNPD.CTRL.SYSTM.SR Control System Engineer Sr | Rate | 166.32 | 170.81 | 175.43 | 180.17 | 185.03 | 190.02 | 195.15 | 200.42 | 205.84 | 211.41 | 217.12 | 222.98 | 0 | 2321
| FNPD.DATABASE.AYST Database Administration Analyst | Rate | 127.83 | 131.29 | 134.83 | 138.47 | 142.21 | 146.04 | 149.99 | 154.04 | 158.21 | 162.48 | 166.88 | 171.38 | 0 | 1784
| FNPD.ELEC.ASMBY.TECH Electrical Assembly Technician | Rate | 71.19 | 73.11 | 75.09 | 77.12 | 79.19 | 81.33 | 83.53 | 85.78 | 88.1 | 90.49 | 92.93 | 95.44 | 0 | 993
| FNPD.ELEC.DESIGN.EN Electrical Design Engineer | Rate | 129.36 | 132.85 | 136.44 | 140.13 | 143.91 | 147.79 | 151.78 | 155.88 | 160.1 | 164.43 | 168.87 | 173.43 | 0 | 1805
| FNPD.ELEC.DESIGN.SR Electrical Design Engineer Sr | Rate | 162.02 | 166.4 | 170.89 | 175.51 | 180.24 | 185.1 | 190.11 | 195.24 | 200.52 | 205.94 | 211.5 | 217.22 | 0 | 2261
| FNPD.ELEC.DESIGNER Electrical Designer | Rate | 99.92 | 102.62 | 105.39 | 108.24 | 111.16 | 114.16 | 117.24 | 120.41 | 123.67 | 127.01 | 130.44 | 133.96 | 0 | 1394
| FNPD.ELEC.DRAFTER Electrical Drafter | Rate | 69.83 | 71.72 | 73.66 | 75.65 | 77.69 | 79.78 | 81.94 | 84.15 | 86.43 | 88.76 | 91.16 | 93.62 | 0 | 974
| FNPD.ELEC.TASK.MNGR Electrical Task Manager | Rate | 121.1 | 124.37 | 127.73 | 131.18 | 134.72 | 138.35 | 142.09 | 145.93 | 149.87 | 153.92 | 158.08 | 162.35 | 0 | 1690
| FNPD.ELEC.TECH Electrical Technician | Rate | 81.5 | 83.7 | 85.96 | 88.29 | 90.67 | 93.11 | 95.63 | 98.21 | 100.87 | 103.59 | 106.39 | 109.27 | 0 | 1137
| FNPD.ELEC.TECH.MNGR Electrical Technical Manager | Rate | 196.25 | 201.56 | 207 | 212.59 | 218.33 | 224.21 | 230.28 | 236.49 | 242.89 | 249.45 | 256.2 | 263.11 | 0 | 2738
| FNPD.ELEC.TECH.SPVSR Electrical Technician Supervisor | Rate | 114.34 | 117.43 | 120.6 | 123.86 | 127.19 | 130.63 | 134.16 | 137.78 | 141.5 | 145.33 | 149.26 | 153.29 | 0 | 1595
| FNPD.ELTN.DESIGN.EN Electronics Design Engineer | Rate | 132.63 | 136.21 | 139.89 | 143.67 | 147.54 | 151.52 | 155.62 | 159.82 | 164.14 | 168.58 | 173.14 | 177.81 | 0 | 1851
| FNPD.ELTN.DESIGN.SR Electronics Design Engineer Sr | Rate | 171.08 | 175.71 | 180.45 | 185.33 | 190.32 | 195.46 | 200.74 | 206.16 | 211.73 | 217.46 | 223.34 | 229.37 | 0 | 2387
| FNPD.ELTN.TECH Electronics Technician | Rate | 88.22 | 90.6 | 93.05 | 95.56 | 98.14 | 100.78 | 103.51 | 106.3 | 109.18 | 112.13 | 115.16 | 118.27 | 0 | 1231
| FNPD.ENGNRING.PHYST Engineering Physicist | Rate | 141.5 | 145.32 | 149.24 | 153.28 | 157.41 | 161.66 | 166.03 | 170.51 | 175.12 | 179.85 | 184.72 | 189.7 | 0 | 1974
| FNPD.EXECUTIVE.DIRCT Executive Direction | Rate | 362 | 371.78 | 381.82 | 392.14 | 402.72 | 413.58 | 424.76 | 436.23 | 448.02 | 460.13 | 472.57 | 485.33 | 0 | 5051
| FNPD.FABRCATN.SPCLST Fabrication Specialist | Rate | 104.36 | 107.18 | 110.08 | 113.05 | 116.1 | 119.23 | 122.46 | 125.76 | 129.16 | 132.65 | 136.24 | 139.92 | 0 | 1456
| FNPD.FACILITIES.MGMT Facilities Management | Rate | 119.46 | 122.69 | 126 | 129.4 | 132.89 | 136.48 | 140.17 | 143.95 | 147.84 | 151.84 | 155.94 | 160.15 | 0 | 1667
| FNPD.GENERAL.ADMIN General Administrative | Rate | 86.84 | 89.19 | 91.6 | 94.07 | 96.61 | 99.21 | 101.9 | 104.65 | 107.48 | 110.38 | 113.37 | 116.43 | 0 | 1212
| FNPD.GENERAL.ES&H General ES&H | Rate | 136.8 | 140.5 | 144.29 | 148.2 | 152.19 | 156.3 | 160.52 | 164.86 | 169.31 | 173.89 | 178.59 | 183.41 | 0 | 1909
| FNPD.GEODEIST Geodesist | Rate | 134.31 | 137.94 | 141.67 | 145.5 | 149.42 | 153.45 | 157.6 | 161.85 | 166.23 | 170.72 | 175.34 | 180.07 | 0 | 1874
| FNPD.HIGH.VAC.TECH High Vac Technician | Rate | 78.67 | 80.79 | 82.97 | 85.22 | 87.51 | 89.87 | 92.3 | 94.8 | 97.36 | 99.99 | 102.69 | 105.47 | 0 | 1098
| FNPD.INSTRUMENT.TECH Mechanical Instrument Technician | Rate | 86.5 | 88.83 | 91.23 | 93.7 | 96.22 | 98.82 | 101.49 | 104.23 | 107.05 | 109.94 | 112.92 | 115.96 | 0 | 1207
| FNPD.INTERLOCK.EN Interlock Engineer | Rate | 129.08 | 132.57 | 136.15 | 139.83 | 143.6 | 147.47 | 151.46 | 155.55 | 159.75 | 164.07 | 168.51 | 173.06 | 0 | 1801
| FNPD.INTERLOCK.SR Interlock Engineer Sr | Rate | 160.34 | 164.68 | 169.12 | 173.69 | 178.38 | 183.19 | 188.14 | 193.22 | 198.44 | 203.81 | 209.32 | 214.97 | 0 | 2237
| FNPD.MAGNT.DESIGN.EN Magnet Design Engineer | Rate | 149.98 | 154.03 | 158.19 | 162.46 | 166.85 | 171.34 | 175.98 | 180.73 | 185.61 | 190.63 | 195.79 | 201.07 | 0 | 2093
| FNPD.MAGNT.DESIGN.SR Magnet Design Engineer Sr | Rate | 165.05 | 169.51 | 174.08 | 178.79 | 183.61 | 188.56 | 193.66 | 198.89 | 204.27 | 209.79 | 215.46 | 221.28 | 0 | 2303
| FNPD.MATRL.EN Materials Engineer | Rate | 82.73 | 84.96 | 87.26 | 89.62 | 92.03 | 94.51 | 97.07 | 99.69 | 102.39 | 105.15 | 108 | 110.91 | 0 | 1154
| FNPD.MATRL.SR Materials Engineer Sr | Rate | 82.73 | 84.96 | 87.26 | 89.62 | 92.03 | 94.51 | 97.07 | 99.69 | 102.39 | 105.15 | 108 | 110.91 | 0 | 1154
| FNPD.MECH.ANLYSIS.EN Mechanical Analysis Engineer | Rate | 126.02 | 129.43 | 132.92 | 136.52 | 140.2 | 143.98 | 147.87 | 151.86 | 155.97 | 160.19 | 164.52 | 168.96 | 0 | 1758
| FNPD.MECH.ANLYSIS.SR Mechanical Analysis Engineer Sr | Rate | 158.52 | 162.81 | 167.2 | 171.72 | 176.35 | 181.11 | 186.01 | 191.03 | 196.19 | 201.5 | 206.94 | 212.53 | 0 | 2212
| FNPD.MECH.ASMBY.TECH Mechanical Assembly Technician | Rate | 81.06 | 83.25 | 85.49 | 87.81 | 90.17 | 92.6 | 95.11 | 97.68 | 100.32 | 103.03 | 105.81 | 108.67 | 0 | 1131
| FNPD.MECH.DESIGN.EN Mechanical Design Engineer | Rate | 131.1 | 134.65 | 138.28 | 142.02 | 145.85 | 149.78 | 153.83 | 157.99 | 162.26 | 166.65 | 171.15 | 175.77 | 0 | 1829
| FNPD.MECH.DESIGN.SR Mechanical Design Engineer Sr | Rate | 165.93 | 170.42 | 175.02 | 179.75 | 184.59 | 189.57 | 194.7 | 199.95 | 205.36 | 210.91 | 216.61 | 222.46 | 0 | 2315
| FNPD.MECH.DESIGNER Mechanical Designer | Rate | 96.36 | 98.97 | 101.64 | 104.39 | 107.2 | 110.09 | 113.07 | 116.12 | 119.26 | 122.48 | 125.79 | 129.19 | 0 | 1345
| FNPD.MECH.DRAFTER Mechanical Drafter | Rate | 57.06 | 58.6 | 60.19 | 61.81 | 63.48 | 65.19 | 66.96 | 68.76 | 70.62 | 72.53 | 74.49 | 76.5 | 0 | 796
| FNPD.MECH.TECH.MNGR Mechanical Technical Manager | Rate | 170.99 | 175.61 | 180.35 | 185.22 | 190.22 | 195.35 | 200.63 | 206.05 | 211.62 | 217.34 | 223.21 | 229.24 | 0 | 2386
| FNPD.MECH.TECH.SPVSR Mechanical Technician Supervisor | Rate | 114.65 | 117.75 | 120.93 | 124.2 | 127.55 | 130.99 | 134.53 | 138.16 | 141.89 | 145.73 | 149.67 | 153.71 | 0 | 1600
| FNPD.METROLOGIST Metrologist | Rate | 87.03 | 89.38 | 91.79 | 94.27 | 96.81 | 99.43 | 102.11 | 104.87 | 107.71 | 110.62 | 113.61 | 116.68 | 0 | 1214
| FNPD.OPERTNS.FINANCE Operations Finance | Rate | 124.77 | 128.14 | 131.6 | 135.16 | 138.81 | 142.55 | 146.4 | 150.36 | 154.42 | 158.6 | 162.88 | 167.28 | 0 | 1741
| FNPD.PA.EXP.PHYST Particle-Astro Physicist Experimental | Rate | 133.05 | 136.65 | 140.34 | 144.13 | 148.02 | 152.01 | 156.12 | 160.33 | 164.67 | 169.12 | 173.69 | 178.38 | 0 | 1857
| FNPD.PA.EXP.RA Particle-Astro Experimental Research Associate | Rate | 85.49 | 87.8 | 90.17 | 92.61 | 95.1 | 97.67 | 100.31 | 103.02 | 105.8 | 108.66 | 111.6 | 114.61 | 0 | 1193
| FNPD.PA.THY.PHYST Particle-Astro Physicist Theory | Rate | 127.02 | 130.46 | 133.98 | 137.6 | 141.31 | 145.12 | 149.05 | 153.07 | 157.21 | 161.46 | 165.82 | 170.3 | 0 | 1772
| FNPD.PA.THY.RA Particle-Astro Theory Research Associate | Rate | 85.49 | 87.8 | 90.17 | 92.61 | 95.1 | 97.67 | 100.31 | 103.02 | 105.8 | 108.66 | 111.6 | 114.61 | 0 | 1193
| FNPD.PRCESS.CTRL.EN Process/Controls Engineer | Rate | 102.47 | 105.24 | 108.08 | 111.01 | 114 | 117.07 | 120.24 | 123.49 | 126.82 | 130.25 | 133.77 | 137.39 | 0 | 1430
| FNPD.PRCESS.CTRL.SR Process/Controls Engineer Sr | Rate | 139.77 | 143.55 | 147.42 | 151.41 | 155.49 | 159.68 | 164 | 168.43 | 172.98 | 177.66 | 182.46 | 187.39 | 0 | 1950
| FNPD.PRJ.CTRL.LEAD Project Controls Lead | Rate | 127.63 | 131.07 | 134.61 | 138.25 | 141.98 | 145.81 | 149.75 | 153.79 | 157.95 | 162.22 | 166.61 | 171.11 | 0 | 1781
| FNPD.PRJ.CTRL.MNGR Project Controls Manager | Rate | 173.73 | 178.43 | 183.25 | 188.2 | 193.27 | 198.49 | 203.85 | 209.36 | 215.02 | 220.83 | 226.8 | 232.92 | 0 | 2424
| FNPD.PRJ.CTRL.SPCLST Project Controls Specialist | Rate | 107.55 | 110.46 | 113.44 | 116.5 | 119.65 | 122.87 | 126.19 | 129.6 | 133.11 | 136.7 | 140.4 | 144.19 | 0 | 1501
| FNPD.PRJ.FINANCE Project Finance | Rate | 123.62 | 126.96 | 130.38 | 133.91 | 137.52 | 141.23 | 145.05 | 148.96 | 152.99 | 157.13 | 161.37 | 165.73 | 0 | 1725
| FNPD.PRJ.MNGR Project Manager | Rate | 146.24 | 150.19 | 154.25 | 158.42 | 162.69 | 167.07 | 171.59 | 176.23 | 180.99 | 185.88 | 190.91 | 196.06 | 0 | 2041
| FNPD.PRJ.MNGR.EXC Project Manager Exec | Rate | 275.77 | 283.22 | 290.87 | 298.73 | 306.78 | 315.06 | 323.58 | 332.31 | 341.3 | 350.52 | 360 | 369.72 | 0 | 3848
| FNPD.PRJ.MNGR.SR Project Manager Sr | Rate | 220.61 | 226.58 | 232.69 | 238.98 | 245.43 | 252.05 | 258.86 | 265.85 | 273.04 | 280.42 | 288 | 295.78 | 0 | 3078
| FNPD.PRJ.SPPRT Project Support | Rate | 127.69 | 131.14 | 134.68 | 138.32 | 142.05 | 145.88 | 149.83 | 153.87 | 158.03 | 162.31 | 166.69 | 171.19 | 0 | 1782
| FNPD.PROCUREMENT Procurement | Rate | 105.57 | 108.42 | 111.35 | 114.36 | 117.44 | 120.61 | 123.87 | 127.21 | 130.65 | 134.18 | 137.81 | 141.53 | 0 | 1473
| FNPD.PT.EXP.PHYST Particle Physicist Experimental | Rate | 128.98 | 132.47 | 136.04 | 139.72 | 143.49 | 147.36 | 151.34 | 155.43 | 159.63 | 163.94 | 168.38 | 172.92 | 0 | 1800
| FNPD.PT.EXP.RA Particle Physics Experimental Research Associate | Rate | 85.49 | 87.8 | 90.17 | 92.61 | 95.1 | 97.67 | 100.31 | 103.02 | 105.8 | 108.66 | 111.6 | 114.61 | 0 | 1193
| FNPD.PT.THY.PHYST Particle Physicist Theory | Rate | 152.61 | 156.73 | 160.96 | 165.32 | 169.77 | 174.35 | 179.07 | 183.9 | 188.87 | 193.98 | 199.22 | 204.6 | 0 | 2129
| FNPD.PT.THY.RA Particle Physics Theory Research Associate | Rate | 85.49 | 87.8 | 90.17 | 92.61 | 95.1 | 97.67 | 100.31 | 103.02 | 105.8 | 108.66 | 111.6 | 114.61 | 0 | 1193
| FNPD.RAD.PRTECTON Radiation Protection | Rate | 113.2 | 116.26 | 119.4 | 122.63 | 125.94 | 129.33 | 132.83 | 136.42 | 140.1 | 143.89 | 147.78 | 151.77 | 0 | 1580
| FNPD.SAFETY Safety | Rate | 122.23 | 125.54 | 128.93 | 132.41 | 135.98 | 139.65 | 143.43 | 147.3 | 151.28 | 155.37 | 159.57 | 163.88 | 0 | 1706
| FNPD.SYSTM.ADMIN Systems Administrator | Rate | 109.72 | 112.69 | 115.73 | 118.86 | 122.06 | 125.36 | 128.75 | 132.22 | 135.8 | 139.47 | 143.24 | 147.1 | 0 | 1531
| FNPD.TRAINING Training | Rate | 114.71 | 117.81 | 120.99 | 124.27 | 127.62 | 131.06 | 134.6 | 138.24 | 141.97 | 145.81 | 149.75 | 153.8 | 0 | 1601
| FNPD.U.GENERAL.ES&H General ES&H Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNPD.U.PA.EXP.PHYST Particle-Astro Physicist Experimental Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNPD.U.PA.EXP.RA Particle-Astro Experimental Research Associate Uncost | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNPD.U.PA.THY.PHYST Particle-Astro Physicist Theory Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNPD.U.PA.THY.RA Particle-Astro Theory Research Associate Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNPD.U.PROCUREMENT Procurement Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNPD.U.PT.EXP.PHYST Particle Physicist Experimental Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNPD.U.PT.EXP.RA Particle Physics Experimental Research Associate Unco | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNPD.U.PT.THY.PHYST Particle Physicist Theory Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNPD.U.PT.THY.RA Particle Physics Theory Research Associate Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNPD.U.RAD.PRTECTON Radiation Protection Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNPD.U.SAFETY Safety Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TD Technical Division
| FNTD.AC.EXP.PHYST Accelerator Physicist Experimental | Rate | 147.82 | 151.82 | 155.92 | 160.13 | 164.45 | 168.88 | 173.45 | 178.13 | 182.95 | 187.89 | 192.97 | 198.18 | 0 | 2063
| FNTD.AC.EXP.RA Accelerator Experimental Research Associate | Rate | 89.66 | 92.08 | 94.57 | 97.13 | 99.74 | 102.43 | 105.2 | 108.04 | 110.97 | 113.97 | 117.05 | 120.21 | 0 | 1251
| FNTD.AC.THY.PHYST Accelerator Physicist Theory | Rate | 162.12 | 166.5 | 171 | 175.62 | 180.35 | 185.22 | 190.23 | 195.36 | 200.64 | 206.07 | 211.64 | 217.35 | 0 | 2262
| FNTD.AC.THY.RA Accelerator Theory Research Associate | Rate | 89.66 | 92.08 | 94.57 | 97.13 | 99.74 | 102.43 | 105.2 | 108.04 | 110.97 | 113.97 | 117.05 | 120.21 | 0 | 1251
| FNTD.ACCOUNTANT Accountant | Rate | 119.03 | 122.25 | 125.55 | 128.94 | 132.42 | 135.99 | 139.67 | 143.44 | 147.31 | 151.3 | 155.39 | 159.58 | 0 | 1661
| FNTD.ADMIN.SPPRT Administrative Support | Rate | 73.17 | 75.15 | 77.18 | 79.26 | 81.4 | 83.6 | 85.86 | 88.17 | 90.56 | 93.01 | 95.52 | 98.1 | 0 | 1021
| FNTD.APDEV.SYSTMAYST Applications Development & Systems Analyst | Rate | 135.5 | 139.16 | 142.92 | 146.78 | 150.74 | 154.81 | 158.99 | 163.29 | 167.7 | 172.23 | 176.89 | 181.67 | 0 | 1891
| FNTD.ASIC.DESIGN.EN ASIC Design Engineer | Rate | 135.69 | 139.35 | 143.11 | 146.98 | 150.95 | 155.02 | 159.21 | 163.51 | 167.93 | 172.47 | 177.13 | 181.91 | 0 | 1893
| FNTD.ASIC.DESIGN.SR ASIC Design Engineer Sr | Rate | 190.9 | 196.06 | 201.35 | 206.8 | 212.37 | 218.1 | 224 | 230.05 | 236.26 | 242.65 | 249.21 | 255.94 | 0 | 2664
| FNTD.CHEMIST Chemist | Rate | 99.1 | 101.78 | 104.53 | 107.35 | 110.25 | 113.22 | 116.28 | 119.42 | 122.65 | 125.97 | 129.37 | 132.86 | 0 | 1383
| FNTD.CLERICAL Clerical | Rate | 65.56 | 67.33 | 69.15 | 71.02 | 72.93 | 74.9 | 76.92 | 79 | 81.13 | 83.33 | 85.58 | 87.89 | 0 | 915
| FNTD.CONST.COORDNATR Construction Coordinator | Rate | 126.36 | 129.78 | 133.28 | 136.88 | 140.58 | 144.37 | 148.27 | 152.27 | 156.39 | 160.62 | 164.96 | 169.41 | 0 | 1763
| FNTD.CONST.MNGR Construction Manager | Rate | 126.38 | 129.79 | 133.3 | 136.9 | 140.59 | 144.38 | 148.29 | 152.29 | 156.41 | 160.64 | 164.98 | 169.43 | 0 | 1763
| FNTD.CRYO.DESIGNER Cryo Designer | Rate | 96.45 | 99.06 | 101.73 | 104.48 | 107.3 | 110.2 | 113.18 | 116.23 | 119.37 | 122.6 | 125.91 | 129.31 | 0 | 1346
| FNTD.CRYO.EN Cryogenics Engineer | Rate | 139.62 | 143.39 | 147.26 | 151.24 | 155.32 | 159.51 | 163.82 | 168.25 | 172.79 | 177.47 | 182.26 | 187.18 | 0 | 1948
| FNTD.CRYO.SR Cryogenics Engineer Sr | Rate | 191.77 | 196.96 | 202.27 | 207.74 | 213.34 | 219.1 | 225.02 | 231.1 | 237.34 | 243.76 | 250.35 | 257.11 | 0 | 2676
| FNTD.CRYO.TECH Cryo Technician | Rate | 80.9 | 83.09 | 85.33 | 87.64 | 90 | 92.43 | 94.92 | 97.49 | 100.12 | 102.83 | 105.61 | 108.46 | 0 | 1129
| FNTD.CTRL.SYSTM.EN Control System Engineer | Rate | 142.93 | 146.79 | 150.76 | 154.83 | 159.01 | 163.29 | 167.71 | 172.24 | 176.89 | 181.68 | 186.59 | 191.63 | 0 | 1994
| FNTD.CTRL.SYSTM.SR Control System Engineer Sr | Rate | 174.44 | 179.15 | 183.99 | 188.96 | 194.06 | 199.29 | 204.68 | 210.2 | 215.89 | 221.72 | 227.72 | 233.86 | 0 | 2434
| FNTD.ELEC.ASMBY.TECH Electrical Assembly Technician | Rate | 74.66 | 76.68 | 78.75 | 80.88 | 83.06 | 85.3 | 87.61 | 89.97 | 92.4 | 94.9 | 97.47 | 100.1 | 0 | 1042
| FNTD.ELEC.DESIGN.EN Electrical Design Engineer | Rate | 135.67 | 139.34 | 143.1 | 146.97 | 150.93 | 155 | 159.19 | 163.49 | 167.91 | 172.45 | 177.11 | 181.89 | 0 | 1893
| FNTD.ELEC.DESIGN.SR Electrical Design Engineer Sr | Rate | 169.92 | 174.52 | 179.23 | 184.07 | 189.04 | 194.13 | 199.38 | 204.77 | 210.3 | 215.99 | 221.83 | 227.82 | 0 | 2371
| FNTD.ELEC.DESIGNER Electrical Designer | Rate | 104.8 | 107.63 | 110.54 | 113.52 | 116.58 | 119.73 | 122.97 | 126.29 | 129.7 | 133.21 | 136.81 | 140.5 | 0 | 1462
| FNTD.ELEC.DRAFTER Electrical Drafter | Rate | 73.24 | 75.22 | 77.25 | 79.34 | 81.48 | 83.68 | 85.94 | 88.26 | 90.65 | 93.1 | 95.61 | 98.19 | 0 | 1022
| FNTD.ELEC.TECH Electrical Technician | Rate | 85.48 | 87.79 | 90.16 | 92.59 | 95.09 | 97.65 | 100.3 | 103 | 105.79 | 108.65 | 111.59 | 114.6 | 0 | 1193
| FNTD.ELEC.TECH.MNGR Electrical Technical Manager | Rate | 205.83 | 211.39 | 217.1 | 222.97 | 228.98 | 235.15 | 241.51 | 248.03 | 254.74 | 261.63 | 268.7 | 275.95 | 0 | 2872
| FNTD.ELEC.TECH.SPVSR Electrical Technician Supervisor | Rate | 119.91 | 123.16 | 126.48 | 129.9 | 133.4 | 137 | 140.7 | 144.5 | 148.41 | 152.42 | 156.54 | 160.77 | 0 | 1673
| FNTD.ELTN.DESIGN.EN Electronics Design Engineer | Rate | 139.1 | 142.86 | 146.72 | 150.68 | 154.74 | 158.92 | 163.21 | 167.62 | 172.15 | 176.81 | 181.59 | 186.49 | 0 | 1941
| FNTD.ELTN.DESIGN.SR Electronics Design Engineer Sr | Rate | 179.43 | 184.28 | 189.25 | 194.37 | 199.61 | 204.99 | 210.54 | 216.22 | 222.07 | 228.07 | 234.24 | 240.56 | 0 | 2504
| FNTD.ELTN.TECH Electronics Technician | Rate | 92.52 | 95.02 | 97.59 | 100.22 | 102.93 | 105.7 | 108.56 | 111.49 | 114.51 | 117.6 | 120.78 | 124.04 | 0 | 1291
| FNTD.ENGNRING.PHYST Engineering Physicist | Rate | 148.4 | 152.41 | 156.53 | 160.76 | 165.09 | 169.55 | 174.13 | 178.83 | 183.67 | 188.63 | 193.73 | 198.96 | 0 | 2071
| FNTD.FABRCATN.SPCLST Fabrication Specialist | Rate | 109.46 | 112.41 | 115.45 | 118.57 | 121.77 | 125.05 | 128.43 | 131.9 | 135.46 | 139.13 | 142.89 | 146.75 | 0 | 1527
| FNTD.FACILITIES.MGMT Facilities Management | Rate | 125.29 | 128.67 | 132.15 | 135.72 | 139.38 | 143.14 | 147.01 | 150.98 | 155.06 | 159.25 | 163.55 | 167.97 | 0 | 1748
| FNTD.GENERAL.ADMIN General Administrative | Rate | 91.08 | 93.54 | 96.07 | 98.66 | 101.32 | 104.06 | 106.87 | 109.75 | 112.72 | 115.77 | 118.9 | 122.11 | 0 | 1271
| FNTD.GENERAL.ES&H General ES&H | Rate | 143.48 | 147.36 | 151.34 | 155.43 | 159.62 | 163.92 | 168.36 | 172.9 | 177.58 | 182.38 | 187.31 | 192.36 | 0 | 2002
| FNTD.HIGH.VAC.TECH High Vac Technician | Rate | 82.5 | 84.73 | 87.02 | 89.37 | 91.78 | 94.26 | 96.81 | 99.42 | 102.11 | 104.87 | 107.71 | 110.61 | 0 | 1151
| FNTD.INSTRUMENT.TECH Mechanical Instrument Technician | Rate | 90.72 | 93.17 | 95.68 | 98.27 | 100.92 | 103.64 | 106.44 | 109.32 | 112.27 | 115.31 | 118.43 | 121.62 | 0 | 1266
| FNTD.INTERLOCK.EN Interlock Engineer | Rate | 135.38 | 139.04 | 142.79 | 146.65 | 150.61 | 154.67 | 158.85 | 163.14 | 167.55 | 172.08 | 176.73 | 181.5 | 0 | 1889
| FNTD.INTERLOCK.SR Interlock Engineer Sr | Rate | 168.17 | 172.71 | 177.38 | 182.17 | 187.08 | 192.13 | 197.32 | 202.65 | 208.13 | 213.76 | 219.53 | 225.46 | 0 | 2346
| FNTD.MACHINIST Machinist | Rate | 109.62 | 112.58 | 115.62 | 118.74 | 121.95 | 125.23 | 128.62 | 132.09 | 135.66 | 139.33 | 143.1 | 146.96 | 0 | 1530
| FNTD.MAGNT.DESIGN.EN Magnet Design Engineer | Rate | 157.3 | 161.55 | 165.91 | 170.39 | 174.99 | 179.71 | 184.57 | 189.55 | 194.67 | 199.94 | 205.34 | 210.88 | 0 | 2195
| FNTD.MAGNT.DESIGN.SR Magnet Design Engineer Sr | Rate | 173.1 | 177.78 | 182.58 | 187.52 | 192.57 | 197.76 | 203.11 | 208.6 | 214.23 | 220.03 | 225.97 | 232.08 | 0 | 2415
| FNTD.MAGNT.DESIGNER Magnet Designer | Rate | 101.81 | 104.56 | 107.38 | 110.29 | 113.26 | 116.32 | 119.46 | 122.69 | 126 | 129.41 | 132.91 | 136.5 | 0 | 1421
| FNTD.MAGNT.RA Magnet Research Associate | Rate | 89.66 | 92.08 | 94.57 | 97.13 | 99.74 | 102.43 | 105.2 | 108.04 | 110.97 | 113.97 | 117.05 | 120.21 | 0 | 1251
| FNTD.MAGNT.SCIENTIST Magnet Scientist | Rate | 151.64 | 155.74 | 159.94 | 164.26 | 168.69 | 173.24 | 177.93 | 182.73 | 187.67 | 192.75 | 197.96 | 203.3 | 0 | 2116
| FNTD.MATRL.EN Materials Engineer | Rate | 86.76 | 89.11 | 91.52 | 93.99 | 96.52 | 99.13 | 101.81 | 104.56 | 107.38 | 110.29 | 113.27 | 116.32 | 0 | 1211
| FNTD.MATRL.RA Material Research Associate | Rate | 89.66 | 92.08 | 94.57 | 97.13 | 99.74 | 102.43 | 105.2 | 108.04 | 110.97 | 113.97 | 117.05 | 120.21 | 0 | 1251
| FNTD.MATRL.SCIENTIST Material Scientist | Rate | 184.86 | 189.85 | 194.98 | 200.25 | 205.65 | 211.19 | 216.9 | 222.76 | 228.78 | 234.97 | 241.32 | 247.83 | 0 | 2579
| FNTD.MATRL.SR Materials Engineer Sr | Rate | 86.76 | 89.11 | 91.52 | 93.99 | 96.52 | 99.13 | 101.81 | 104.56 | 107.38 | 110.29 | 113.27 | 116.32 | 0 | 1211
| FNTD.MECH.ANLYSIS.EN Mechanical Analysis Engineer | Rate | 132.17 | 135.75 | 139.41 | 143.18 | 147.04 | 151 | 155.09 | 159.28 | 163.58 | 168 | 172.54 | 177.2 | 0 | 1844
| FNTD.MECH.ANLYSIS.SR Mechanical Analysis Engineer Sr | Rate | 166.26 | 170.75 | 175.36 | 180.1 | 184.96 | 189.95 | 195.08 | 200.35 | 205.77 | 211.33 | 217.04 | 222.9 | 0 | 2320
| FNTD.MECH.ASMBY.TECH Mechanical Assembly Technician | Rate | 85.01 | 87.31 | 89.67 | 92.09 | 94.57 | 97.12 | 99.75 | 102.44 | 105.21 | 108.06 | 110.98 | 113.97 | 0 | 1186
| FNTD.MECH.DESIGN.EN Mechanical Design Engineer | Rate | 137.5 | 141.22 | 145.03 | 148.95 | 152.97 | 157.09 | 161.34 | 165.7 | 170.18 | 174.78 | 179.5 | 184.35 | 0 | 1919
| FNTD.MECH.DESIGN.SR Mechanical Design Engineer Sr | Rate | 174.03 | 178.73 | 183.56 | 188.52 | 193.6 | 198.82 | 204.2 | 209.71 | 215.38 | 221.21 | 227.18 | 233.32 | 0 | 2428
| FNTD.MECH.DESIGNER Mechanical Designer | Rate | 101.06 | 103.8 | 106.6 | 109.48 | 112.43 | 115.46 | 118.59 | 121.79 | 125.08 | 128.46 | 131.93 | 135.5 | 0 | 1410
| FNTD.MECH.DRAFTER Mechanical Drafter | Rate | 59.85 | 61.46 | 63.12 | 64.83 | 66.58 | 68.37 | 70.22 | 72.12 | 74.07 | 76.07 | 78.13 | 80.24 | 0 | 835
| FNTD.MECH.SYSTM.TECH Mechanical Systems Technician | Rate | 73.44 | 75.42 | 77.46 | 79.55 | 81.7 | 83.9 | 86.17 | 88.5 | 90.89 | 93.35 | 95.87 | 98.46 | 0 | 1025
| FNTD.MECH.TECH.MNGR Mechanical Technical Manager | Rate | 179.33 | 184.18 | 189.15 | 194.26 | 199.5 | 204.88 | 210.42 | 216.1 | 221.94 | 227.94 | 234.11 | 240.43 | 0 | 2502
| FNTD.MECH.TECH.SPVSR Mechanical Technician Supervisor | Rate | 120.25 | 123.5 | 126.83 | 130.26 | 133.77 | 137.38 | 141.09 | 144.9 | 148.82 | 152.84 | 156.97 | 161.21 | 0 | 1678
| FNTD.OPERTNS.FINANCE Operations Finance | Rate | 130.86 | 134.4 | 138.03 | 141.76 | 145.58 | 149.51 | 153.55 | 157.69 | 161.96 | 166.34 | 170.83 | 175.44 | 0 | 1826
| FNTD.PA.EXP.PHYST Particle-Astro Physicist Experimental | Rate | 139.54 | 143.32 | 147.18 | 151.16 | 155.24 | 159.43 | 163.74 | 168.16 | 172.7 | 177.37 | 182.17 | 187.09 | 0 | 1947
| FNTD.PA.EXP.RA Particle-Astro Experimental Research Associate | Rate | 89.66 | 92.08 | 94.57 | 97.13 | 99.74 | 102.43 | 105.2 | 108.04 | 110.97 | 113.97 | 117.05 | 120.21 | 0 | 1251
| FNTD.PA.THY.RA Particle-Astro Theory Research Associate | Rate | 89.66 | 92.08 | 94.57 | 97.13 | 99.74 | 102.43 | 105.2 | 108.04 | 110.97 | 113.97 | 117.05 | 120.21 | 0 | 1251
| FNTD.PRCESS.CTRL.EN Process/Controls Engineer | Rate | 107.48 | 110.38 | 113.36 | 116.42 | 119.56 | 122.79 | 126.11 | 129.51 | 133.01 | 136.61 | 140.3 | 144.09 | 0 | 1500
| FNTD.PRCESS.CTRL.SR Process/Controls Engineer Sr | Rate | 146.59 | 150.55 | 154.61 | 158.79 | 163.08 | 167.47 | 172 | 176.65 | 181.42 | 186.33 | 191.36 | 196.53 | 0 | 2045
| FNTD.PRJ.CTRL.LEAD Project Controls Lead | Rate | 133.85 | 137.47 | 141.18 | 145 | 148.91 | 152.92 | 157.06 | 161.3 | 165.66 | 170.14 | 174.74 | 179.46 | 0 | 1868
| FNTD.PRJ.CTRL.MNGR Project Controls Manager | Rate | 182.21 | 187.14 | 192.19 | 197.38 | 202.71 | 208.17 | 213.8 | 219.57 | 225.51 | 231.61 | 237.87 | 244.29 | 0 | 2542
| FNTD.PRJ.CTRL.SPCLST Project Controls Specialist | Rate | 112.8 | 115.85 | 118.97 | 122.19 | 125.48 | 128.87 | 132.35 | 135.93 | 139.6 | 143.38 | 147.25 | 151.23 | 0 | 1574
| FNTD.PRJ.FINANCE Project Finance | Rate | 129.65 | 133.15 | 136.75 | 140.44 | 144.23 | 148.12 | 152.12 | 156.23 | 160.46 | 164.79 | 169.25 | 173.82 | 0 | 1809
| FNTD.PRJ.MNGR Project Manager | Rate | 153.38 | 157.52 | 161.77 | 166.15 | 170.63 | 175.23 | 179.97 | 184.83 | 189.82 | 194.95 | 200.22 | 205.63 | 0 | 2140
| FNTD.PRJ.MNGR.EXC Project Manager Exec | Rate | 289.23 | 297.04 | 305.06 | 313.31 | 321.76 | 330.43 | 339.37 | 348.53 | 357.95 | 367.63 | 377.57 | 387.76 | 0 | 4036
| FNTD.PRJ.MNGR.SR Project Manager Sr | Rate | 231.38 | 237.63 | 244.05 | 250.65 | 257.4 | 264.35 | 271.49 | 278.82 | 286.36 | 294.1 | 302.05 | 310.21 | 0 | 3228
| FNTD.PRJ.SPPRT Project Support | Rate | 133.92 | 137.54 | 141.25 | 145.07 | 148.98 | 153 | 157.14 | 161.38 | 165.74 | 170.23 | 174.83 | 179.55 | 0 | 1869
| FNTD.PROCUREMENT Procurement | Rate | 110.72 | 113.71 | 116.78 | 119.94 | 123.17 | 126.49 | 129.91 | 133.42 | 137.03 | 140.73 | 144.54 | 148.44 | 0 | 1545
| FNTD.PT.EXP.PHYST Particle Physicist Experimental | Rate | 135.27 | 138.93 | 142.68 | 146.54 | 150.49 | 154.55 | 158.73 | 163.01 | 167.42 | 171.95 | 176.59 | 181.36 | 0 | 1888
| FNTD.PT.EXP.RA Particle Physics Experimental Research Associate | Rate | 89.66 | 92.08 | 94.57 | 97.13 | 99.74 | 102.43 | 105.2 | 108.04 | 110.97 | 113.97 | 117.05 | 120.21 | 0 | 1251
| FNTD.PT.THY.RA Particle Physics Theory Research Associate | Rate | 89.66 | 92.08 | 94.57 | 97.13 | 99.74 | 102.43 | 105.2 | 108.04 | 110.97 | 113.97 | 117.05 | 120.21 | 0 | 1251
| FNTD.QC.TECHNICAL QC Technical | Rate | 96.73 | 99.34 | 102.02 | 104.78 | 107.61 | 110.51 | 113.5 | 116.56 | 119.71 | 122.95 | 126.27 | 129.68 | 0 | 1350
| FNTD.QLTY.ASSRANCE Quality Assurance | Rate | 147.44 | 151.42 | 155.51 | 159.71 | 164.02 | 168.44 | 173 | 177.67 | 182.47 | 187.41 | 192.47 | 197.67 | 0 | 2057
| FNTD.RF.DESIGN.EN RF Design Engineer | Rate | 145.49 | 149.43 | 153.46 | 157.61 | 161.86 | 166.22 | 170.72 | 175.33 | 180.06 | 184.93 | 189.93 | 195.06 | 0 | 2030
| FNTD.RF.DESIGN.SR RF Design Engineer Sr | Rate | 179.23 | 184.07 | 189.04 | 194.15 | 199.39 | 204.76 | 210.3 | 215.98 | 221.82 | 227.81 | 233.97 | 240.29 | 0 | 2501
| FNTD.RF.RA RF Research Associate | Rate | 89.66 | 92.08 | 94.57 | 97.13 | 99.74 | 102.43 | 105.2 | 108.04 | 110.97 | 113.97 | 117.05 | 120.21 | 0 | 1251
| FNTD.RF.SCIENTIST RF Scientist | Rate | 167.02 | 171.53 | 176.16 | 180.93 | 185.81 | 190.82 | 195.98 | 201.27 | 206.71 | 212.3 | 218.04 | 223.92 | 0 | 2330
| FNTD.SRF.TECH Mechanical SRF Technician | Rate | 74.7 | 76.72 | 78.79 | 80.92 | 83.1 | 85.34 | 87.65 | 90.02 | 92.45 | 94.95 | 97.52 | 100.15 | 0 | 1042
| FNTD.TRAINING Training | Rate | 120.31 | 123.56 | 126.9 | 130.33 | 133.84 | 137.45 | 141.17 | 144.98 | 148.9 | 152.93 | 157.06 | 161.3 | 0 | 1679
| FNTD.U.GENERAL.ES&H General ES&H Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNTD.U.MATRL.RA Material Research Associate Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNTD.U.PA.EXP.PHYST Particle-Astro Physicist Experimental Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNTD.U.PA.EXP.RA Particle-Astro Experimental Research Associate Uncost | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNTD.U.PA.THY.RA Particle-Astro Theory Research Associate Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNTD.U.PROCUREMENT Procurement Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNTD.U.PT.EXP.PHYST Particle Physicist Experimental Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNTD.U.PT.EXP.RA Particle Physics Experimental Research Associate Unco | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNTD.U.PT.THY.RA Particle Physics Theory Research Associate Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNTD.U.RF.RA RF Research Associate Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNTD.U.RF.SCIENTIST RF Scientist Uncosted | Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FNTD.WEB.APPS.DEVLPR Web Applications Developer | Rate | 92.98 | 95.49 | 98.07 | 100.72 | 103.43 | 106.22 | 109.1 | 112.04 | 115.07 | 118.18 | 121.38 | 124.65 | 0 | 1297
| FNTD.WELDER Welder | Rate | 109.62 | 112.58 | 115.62 | 118.74 | 121.95 | 125.23 | 128.62 | 132.09 | 135.66 | 139.33 | 143.1 | 146.96 | 0 | 1530
WD Work Force Develoment
| FNWD.ACCOUNTANT Accountant | Rate | 97.17 | 99.79 | 102.49 | 105.26 | 108.1 | 111.01 | 114.01 | 117.09 | 120.26 | 123.51 | 126.85 | 130.27 | 0 | 1356
| FNWD.ADMIN.SPPRT Administrative Support | Rate | 59.73 | 61.35 | 63 | 64.7 | 66.45 | 68.24 | 70.09 | 71.98 | 73.92 | 75.92 | 77.98 | 80.08 | 0 | 833
| FNWD.APDEV.SYSTMAYST Applications Development & Systems Analyst | Rate | 110.61 | 113.6 | 116.67 | 119.82 | 123.05 | 126.37 | 129.79 | 133.29 | 136.9 | 140.6 | 144.4 | 148.3 | 0 | 1543
| FNWD.BENEFITS Benefits | Rate | 77 | 79.08 | 81.22 | 83.41 | 85.66 | 87.97 | 90.35 | 92.79 | 95.3 | 97.88 | 100.52 | 103.23 | 0 | 1074
| FNWD.CLERICAL Clerical | Rate | 53.52 | 54.96 | 56.45 | 57.97 | 59.53 | 61.14 | 62.79 | 64.49 | 66.23 | 68.02 | 69.86 | 71.75 | 0 | 747
| FNWD.COMPENSATION Compensation | Rate | 80.61 | 82.79 | 85.03 | 87.33 | 89.68 | 92.1 | 94.59 | 97.14 | 99.77 | 102.47 | 105.24 | 108.08 | 0 | 1125
| FNWD.EDUCATION Education | Rate | 80.35 | 82.52 | 84.75 | 87.04 | 89.39 | 91.8 | 94.28 | 96.83 | 99.44 | 102.13 | 104.89 | 107.73 | 0 | 1121
| FNWD.EL.CH.EDUCATION Early Childhood Education | Rate | 35.31 | 36.27 | 37.25 | 38.26 | 39.29 | 40.35 | 41.44 | 42.56 | 43.71 | 44.89 | 46.1 | 47.35 | 0 | 493
| FNWD.EMPLY.LABOR.REL Employee/Labor Relations | Rate | 109.47 | 112.43 | 115.47 | 118.59 | 121.79 | 125.07 | 128.45 | 131.92 | 135.49 | 139.15 | 142.91 | 146.77 | 0 | 1528
| FNWD.EQ.OPPORTUNITY Equal Opportunity | Rate | 100.1 | 102.8 | 105.58 | 108.43 | 111.36 | 114.36 | 117.45 | 120.62 | 123.88 | 127.23 | 130.67 | 134.2 | 0 | 1397
| FNWD.FACILITIES.MGMT Facilities Management | Rate | 102.27 | 105.04 | 107.87 | 110.79 | 113.78 | 116.85 | 120.01 | 123.25 | 126.58 | 130 | 133.51 | 137.12 | 0 | 1427
| FNWD.GENERAL.ADMIN General Administrative | Rate | 74.35 | 76.36 | 78.42 | 80.54 | 82.71 | 84.94 | 87.24 | 89.6 | 92.02 | 94.51 | 97.06 | 99.68 | 0 | 1037
| FNWD.HR.GENERALIST Human Resources Generalist | Rate | 127.04 | 130.47 | 133.99 | 137.62 | 141.33 | 145.14 | 149.06 | 153.09 | 157.22 | 161.48 | 165.84 | 170.32 | 0 | 1773
| FNWD.HRIS HRIS | Rate | 82.48 | 84.71 | 87 | 89.35 | 91.76 | 94.23 | 96.78 | 99.4 | 102.08 | 104.84 | 107.68 | 110.58 | 0 | 1151
| FNWD.INTERNATIONL.HR International Human Resources | Rate | 89.52 | 91.94 | 94.42 | 96.97 | 99.59 | 102.27 | 105.04 | 107.87 | 110.79 | 113.78 | 116.86 | 120.02 | 0 | 1249
| FNWD.OPERTNS.FINANCE Operations Finance | Rate | 106.83 | 109.71 | 112.67 | 115.72 | 118.84 | 122.05 | 125.35 | 128.73 | 132.21 | 135.78 | 139.45 | 143.22 | 0 | 1491
| FNWD.RECRUITMENT Recruitment | Rate | 75.24 | 77.27 | 79.36 | 81.5 | 83.7 | 85.96 | 88.28 | 90.67 | 93.12 | 95.64 | 98.22 | 100.87 | 0 | 1050
| FNWD.TRAINING Training | Rate | 98.21 | 100.87 | 103.59 | 106.39 | 109.26 | 112.21 | 115.24 | 118.35 | 121.55 | 124.84 | 128.21 | 131.67 | 0 | 1370

## CoilTechLaborfromP6
Program: |  | Description: |  |  |  | Approval:
MAG1 |  | Magnet Production 1 |  |  |  |  | Program Manager
Run Date: |  | Status Date: |  |  |  |  | Functional Manager
2012-10-11 10:56 |  | 2009-09-30 |  |  |  |  | Cost Account Manager
Cost Account |  | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | Cumulative
| BCWS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192005 | 653127 | 1006086 | 941943 | 1332 | 0 | 0 | 2794493
Grand Totals:
| BCWS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192005 | 653127 | 1006086 | 941943 | 1332 | 0 | 0 | 2794493
Program: |  | 2009-09-30 FY09: Description:; 2009-09-30 FY13: Approval:
MAG1 |  | 2009-09-30 FY09: Magnet Production 1; Cost Account Manager FY14: Program Manager
Run Date: |  | 2009-09-30 FY09: Status Date:; Cost Account Manager FY14: Functional Manager
2012-10-11 11:02 |  | 2009-09-30 FY09: 2009-09-30; Cost Account Manager FY14: Cost Account Manager
Cost Account |  |  | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | Cumulative
18 SRF
| HOURS | BCWS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1908 | 6332 | 9516 | 8692 | 12 | 0 | 0 | 26460
Cost Account Totals: |  | BCWS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1908 | 6332 | 9516 | 8692 | 12 | 0 | 0 | 26460
Grand Totals:
|  | BCWS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1908 | 6332 | 9516 | 8692 | 12 | 0 | 0 | 26460

## M&S Cost Estimate for MQXF
M & S and Inspection Cost | Qty | 3.3 m long | 4.5 m long | 4.5 m long
Curing Mold | 1 | 83948.825 | 0 | 0
Curing Mold Labor+QC | 1 | 29964 | 0 | 0
Winding and Curing Tooling | 1 | 127610.825 | 178221.0436 | 178221.0436
W & C Tooling QC | 1 | 38880 | 36288 | 36288
Reaction and Impregnation Tooling | 1 | 192103.47 | 276029.5252 | 100129.2484
R & I Tooling QC | 1 | 24192 | 24192 | 15552
Tooling Total |  | 496699.12 | 514730.5688 | 330190.2919
Coil Parts + QC | 1 | 39431.93 | 50580.0911 | 50580.0911
Tooling + Coil Total |  | 536131.05 | 565310.6599 | 380770.3831
Reference: if reuse 3.3 m long tooling, procure additional to make up 4.5 m long tooling

## Cable cost MQXF
150 mm Prototype Conductor Cost Estimate for 3 m Magnet
|  | Aperture increase factor |  |  | 1.25
ALL in FY12$ |  | Cable thickness increase factor |  |  | 0.92
|  | Length of magnet factor |  |  | 1.3333
|  | UL of cable |  |  | 485 |  |  | scaled from LHQ UL +25 m
|  | Wire diam increase factor |  |  | 1.1937
|  | Total strand length in cable |  |  | 20370 | meters
|  | With 10% Waste in Mapping |  |  | 22407 | meters
|  | Weight of strand /UL |  |  | 134.1418 | kg | Total Req. | 0
|  | Strand-Present cost W/OH |  |  | 200797.3703
|  | Cabling Cost at LBNL |  |  | 18782.6087
|  | Insulation cost at NEWTC |  |  | 7605.576
|  | Total Cost of UL |  |  | 227185.555 |  | Total Cost xx UL | 0
|  | QA | 10% |  | 22718.5555 |  | Total QA | 318059.777
|  | Witness Samples/coil reaction |  |  | 27500 |  | Total Witness | 0
|  |  |  | Total per coil | 277404.1105 |  |  | 318059.777
| 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | Total
Number of coils |  | 0 | 0 | 0 | 0 | 0 | 0
Wire Requirement in Kg |  | 0 | 0 | 0 | 0 | 0 | 0
PO placed, Kg | [6 empty] | 0

## Coil Parts
| LHC-MQXF COIL | Coil Length |  | Aperture Ratio MQXF/LHQ | [6 empty] | Coil Length |  | Length ratio
|  | 3.3m long |  | 1.25 | [6 empty] | 4.5m long |  | 1.3636
| Name | Unit Cost | Coating Cost | Material | Reference Drawing # | Qty/coil | Part Cost | Part Cost + Coating |  | Name | Unit Cost | Coating Cost | Material | Reference Drawing # | Qty/coil | Part Cost | Part Cost + Coating
| L1_LE_KEY | 1852.4375 | 193.75 | 6AL-4V Ti | 484122 | 1 | 1852.4375 | 2252.4375 |  | L1_LE_KEY | 1852.4375 | 193.75 | 6AL-4V Ti | 484122 | 1 | 1852.4375 | 2252.4375
| L2_LE_KEY |  | 206.25 | 6AL-4V Ti | 484135 | 1 |  |  |  | L2_LE_KEY |  | 206.25 | 6AL-4V Ti | 484135 | 1
| L1_RE_KEY | 662.0625 | 193.75 | 6AL-4V Ti | 484123 | 1 | 662.0625 | 855.8125 |  | L1_RE_KEY | 662.0625 | 193.75 | 6AL-4V Ti | 484123 | 1 | 662.0625 | 855.8125
| L2_RE_KEY | 642 | 206.25 | 6AL-4V Ti | 484132 | 1 | 642 | 848.25 |  | L2_RE_KEY | 642 | 206.25 | 6AL-4V Ti | 484132 | 1 | 642 | 848.25
| L1_KEY-1 | 407.9375 | 193.75 | 6AL-4V Ti | 484120 | 6 | 2447.625 | 3610.125 |  | L1_KEY-1 | 407.9375 | 193.75 | 6AL-4V Ti | 484120 | 11 | 4487.3125 | 6618.5625
| L1_KEY-2 | 528.25 | 193.75 | 6AL-4V Ti | 484121 | 1 | 528.25 | 722 |  | L1_KEY-2 | 528.25 | 193.75 | 6AL-4V Ti | 484121 | 1 | 528.25 | 722
| L2_KEY-1 | 454.75 | 206.25 | 6AL-4V Ti | 484130 | 6 | 2728.5 | 3966 |  | L2_KEY-1 | 454.75 | 206.25 | 6AL-4V Ti | 484130 | 11 | 5002.25 | 7271
| L2_KEY-2 | 601.875 | 206.25 | 6AL-4V Ti | 484131 | 1 | 601.875 | 808.125 |  | L2_KEY-2 | 601.875 | 206.25 | 6AL-4V Ti | 484131 | 1 | 601.875 | 808.125
| L1_LE_Spliceblk | 656.25 | 218.75 | SS 304 | 484129 | 1 | 656.25 | 875 |  | L1_LE_Spliceblk | 656.25 | 218.75 | SS 304 | 484129 | 1 | 656.25 | 875
| L1_LE_saddle | 682.125 | 206.25 | SS 304 | 484128 | 1 | 682.125 | 888.375 |  | L1_LE_saddle | 682.125 | 206.25 | SS 304 | 484128 | 1 | 682.125 | 888.375
| L1_LE_spacer-2 | 581.8125 | 193.75 | SS 304 | 484127 | 1 | 581.8125 | 775.5625 |  | L1_LE_spacer-2 | 581.8125 | 193.75 | SS 304 | 484127 | 1 | 581.8125 | 775.5625
| L1_LE_spacer-1 | 561.75 | 193.75 | SS 304 | 484126 | 1 | 561.75 | 755.5 |  | L1_LE_spacer-1 | 561.75 | 193.75 | SS 304 | 484126 | 1 | 561.75 | 755.5
| L1_RE_saddle | 800 | 206.25 | SS 304 | 484125 | 1 | 800 | 1006.25 |  | L1_RE_saddle | 800 | 206.25 | SS 304 | 484125 | 1 | 800 | 1006.25
| L1_RE_spacer | 588.5 | 206.25 | SS 304 | 484124 | 1 | 588.5 | 794.75 |  | L1_RE_spacer | 588.5 | 206.25 | SS 304 | 484124 | 1 | 588.5 | 794.75
| L2_RE_saddle | 815.875 | 206.25 | SS 304 | 484133 | 1 | 815.875 | 1022.125 |  | L2_RE_saddle | 815.875 | 206.25 | SS 304 | 484133 | 1 | 815.875 | 1022.125
| L2_RE_spacer | 795.8125 | 206.25 | SS 304 | 484134 | 1 | 795.8125 | 1002.0625 |  | L2_RE_spacer | 795.8125 | 206.25 | SS 304 | 484134 | 1 | 795.8125 | 1002.0625
| L2_LE_spliceblk | 1037.5 | 218.75 | SS 304 | 484139 | 1 | 1037.5 | 1256.25 |  | L2_LE_spliceblk | 1037.5 | 218.75 | SS 304 | 484139 | 1 | 1037.5 | 1256.25
| L2_LE_saddle | 575.125 | 206.25 | SS 304 | 484138 | 1 | 575.125 | 781.375 |  | L2_LE_saddle | 575.125 | 206.25 | SS 304 | 484138 | 1 | 575.125 | 781.375
| L2_LE_spacer-2 | 662.0625 | 206.25 | SS 304 | 484137 | 1 | 662.0625 | 868.3125 |  | L2_LE_spacer-2 | 662.0625 | 206.25 | SS 304 | 484137 | 1 | 662.0625 | 868.3125
| L2_LE_spacer-1 | 595.1875 | 206.25 | SS 304 | 484136 | 1 | 595.1875 | 801.4375 |  | L2_LE_spacer-1 | 595.1875 | 206.25 | SS 304 | 484136 | 1 | 595.1875 | 801.4375
| Layer 1 wedge | 670.4375 |  | Bronze | 483470 | 2 | 1340.875 | 1340.875 |  | Layer 1 wedge | 670.4375 |  | Bronze | 483470 | 4 | 2681.75 | 2681.75
| Layer 2 wedge | 676.0625 |  | Bronze | 483472 | 2 | 1352.125 | 1352.125 |  | Layer 2 wedge | 676.0625 |  | Bronze | 483472 | 4 | 2704.25 | 2704.25
| 20mil Ceramic(ft) | 89.62 | - |  |  | 27 | 2419.74 | 2419.74 |  | 20mil Ceramic(ft) | 89.62 | - |  |  | 36.8182 | 3299.6455 | 3299.6455
| Other insulation | 500 | - |  |  | 1 | 500 | 500 |  | Other insulation | 681.8182 | - |  |  | 1 | 681.8182 | 681.8182
| Ceramic Binder (lb) | 117.04 |  | CTD1202 |  | 1 | 117.04 | 117.04 |  | Ceramic Binder (lb) | 117.04 |  | CTD1202 |  | 1 | 117.04 | 117.04
| Epoxy (kit) | 2190.8 |  | CTD101K |  | 2 | 4381.6 | 4381.6 |  | Epoxy (kit) | 2190.8 |  | CTD101K |  | 3 | 6572.4 | 6572.4
| Total/coil |  | 3868.75 |  |  |  | 30116.93 | 36191.93 |  | Total/coil |  | 3275 |  |  |  | 38185.0911 | 46260.0911
| Rate/hr | # of part | # of FTE | hr/part | Total | Comment |  |  |  | Rate/hr | # of part | # of FTE | hr/part | Total | Comment
QC | 108 | 30 | 1 | 1 | 3240 |  |  |  | QC | 108 | 40 | 1 | 1 | 4320
Reference
| LHC-LARP LHQ COIL | 3.3m long |  | 120 mm Aperture | [5 empty] | LHC-LARP HQ COIL | 1m long
| Name | Unit Cost | Coating Cost | Material | Drawing # | Qty/coil | Part Cost | Part Cost + Coating |  | Name | Unit Cost | Coating Cost | Material | Drawing # | Qty/coil | Part Cost | Part Cost + Coating
| L1_LE_KEY | 1481.95 | 155 | 6AL-4V Ti | 484122 | 1 | 1481.95 | 1801.95 |  | L1_LE_KEY | 628.3 | 155 | 6AL-4V Ti | 484242 | 1 | 628.3 | 783.3
| L2_LE_KEY |  | 165 | 6AL-4V Ti | 484135 | 1 |  |  |  | L2_LE_KEY | 679.8 | 165 | 6AL-4V Ti | 484246 | 1 | 679.8 | 844.8
| L1_RE_KEY | 529.65 | 155 | 6AL-4V Ti | 484123 | 1 | 529.65 | 684.65 |  | L1_RE_KEY | 484.1 | 155 | 6AL-4V Ti | 484244 | 1 | 484.1 | 639.1
| L2_RE_KEY | 513.6 | 165 | 6AL-4V Ti | 484132 | 1 | 513.6 | 678.6 |  | L2_RE_KEY | 494.4 | 165 | 6AL-4V Ti | 484248 | 1 | 494.4 | 659.4
| L1_KEY-1 | 326.35 | 155 | 6AL-4V Ti | 484120 | 6 | 1958.1 | 2888.1 |  | L1_LE_Spliceblk | 406.85 | 175 | SS 304 | 484243 | 1 | 406.85 | 581.85
| L1_KEY-2 | 422.6 | 155 | 6AL-4V Ti | 484121 | 1 | 422.6 | 577.6 |  | L1_LE_saddle | 545.7 | 165 | SS 304 | 484128 | 1 | 545.7 | 710.7
| L2_KEY-1 | 363.8 | 165 | 6AL-4V Ti | 484130 | 6 | 2182.8 | 3172.8 |  | L1_LE_spacer-2 | 465.45 | 155 | SS 304 | 484127 | 1 | 465.45 | 620.45
| L2_KEY-2 | 481.5 | 165 | 6AL-4V Ti | 484131 | 1 | 481.5 | 646.5 |  | L1_LE_spacer-1 | 449.4 | 155 | SS 304 | 484126 | 1 | 449.4 | 604.4
| L1_LE_Spliceblk | 525 | 175 | SS 304 | 484129 | 1 | 525 | 700 |  | L1_RE_saddle | 640 | 165 | SS 304 | 484245 | 1 | 640 | 805
| L1_LE_saddle | 545.7 | 165 | SS 304 | 484128 | 1 | 545.7 | 710.7 |  | L1_RE_spacer | 470.8 | 165 | SS 304 | 484124 | 1 | 470.8 | 635.8
| L1_LE_spacer-2 | 465.45 | 155 | SS 304 | 484127 | 1 | 465.45 | 620.45 |  | L2_RE_saddle | 417.15 | 165 | SS 304 | 484249 | 1 | 417.15 | 582.15
| L1_LE_spacer-1 | 449.4 | 155 | SS 304 | 484126 | 1 | 449.4 | 604.4 |  | L2_RE_spacer | 636.65 | 165 | SS 304 | 484134 | 1 | 636.65 | 801.65
| L1_RE_saddle | 640 | 165 | SS 304 | 484125 | 1 | 640 | 805 |  | L2_LE_spliceblk | 556.2 | 175 | SS 304 | 484247 | 1 | 556.2 | 731.2
| L1_RE_spacer | 470.8 | 165 | SS 304 | 484124 | 1 | 470.8 | 635.8 |  | L2_LE_saddle | 460.1 | 165 | SS 304 | 484138 | 1 | 460.1 | 625.1
| L2_RE_saddle | 652.7 | 165 | SS 304 | 484133 | 1 | 652.7 | 817.7 |  | L2_LE_spacer-2 | 529.65 | 165 | SS 304 | 484137 | 1 | 529.65 | 694.65
| L2_RE_spacer | 636.65 | 165 | SS 304 | 484134 | 1 | 636.65 | 801.65 |  | L2_LE_spacer-1 | 476.15 | 165 | SS 304 | 484136 | 1 | 476.15 | 641.15
| L2_LE_spliceblk | 830 | 175 | SS 304 | 484139 | 1 | 830 | 1005 |  | Layer 1 Bronze wedge | 536.35 |  | Bronze | 483470 | 0.5 | 268.175 | 268.175
| L2_LE_saddle | 460.1 | 165 | SS 304 | 484138 | 1 | 460.1 | 625.1 |  | Layer 2 Bronze wedge | 540.85 |  | Bronze | 483472 | 0.5 | 270.425 | 270.425
| L2_LE_spacer-2 | 529.65 | 165 | SS 304 | 484137 | 1 | 529.65 | 694.65 |  | Total/coil |  | 2620 |  |  |  | 8879.3 | 11499.3
| L2_LE_spacer-1 | 476.15 | 165 | SS 304 | 484136 | 1 | 476.15 | 641.15
| Layer 1 wedge | 536.35 |  | Bronze | 483470 | 2 | 1072.7 | 1072.7
| Layer 2 wedge | 540.85 |  | Bronze | 483472 | 2 | 1081.7 | 1081.7
| 20mil Ceramic(ft) | 89.62 | - |  |  | 24 | 2150.88 | 2150.88
| Other insulation | 500 | - |  |  | 1 | 500 | 500
| Ceramic Binder (lb) | 117.04 |  | CTD1202 |  | 1 | 117.04 | 117.04
| Epoxy (kit) | 2190.8 |  | CTD101K |  | 2 | 4381.6 | 4381.6
| Total/coil |  | 3260 |  |  |  | 23555.72 | 28415.72
Scale Up

## Winding and Curing Tooling
| LHC-MQXF Reaction and Impregnation Tooling | Coil Length |  | Aperture Ratio MQXF/LHQ |  |  |  | LHC-MQXF Reaction and Impregnation Tooling | Coil Length | Length Ratio |  |  | LHC-MQXF Reaction and Impregnation Tooling | Coil Length | Length Ratio
| 1 set | 3.3m long |  | 1.25 |  |  |  | 1 set | 4.5m long | 1.3636 |  |  | 1 set | 4.5m long | 1.3636
| Curing Mold | [6 empty] | Curing Mold | Use the same one as 3.3 m |  |  |  | Curing Mold | Use the same one as 3.3 m
| P/N | Description | Qty | Cost Per | Total | PO | Vendor
| ME 483304 | End Block | 2 | 3118.75 | 6237.5 | 602597 | Medco
| ME 483305 D | Lamination | 5600 | 5.6125 | 31430 | 603978 | Larsen Mfg
|  | Die | 1 |  | 39062.5 | 603978 | Larsen Mfg
| MB 483306 | Lifting Bar | 8 | 47.5 | 380 | 602129 | J Marcs
| MB 483307 | Lifting Bar Spacer | 8 | 107.5 | 860 | 602129 | J Marcs
| MB 483909 | Upper Ring Insert | 3 |  | 1095 | MSV 3226 | VMS
| MB 483928 | Cover Layer 1-1 | 2 | 212.5 | 425 | 605430 | J Marcs
| MB 483929 | Cover Layer 1-2 | 2 | 155 | 310 | 605430 | J Marcs
| MB 483930 | Cover Layer 2-1 | 2 | 253.75 | 507.5 | 605430 | J Marcs
| MB 483931 | Cover Layer 2-2 | 2 | 158.75 | 317.5 | 605430 | J Marcs
| MB 483932 | Link 1 | 2 | 122.5 | 245 | 605430 | J Marcs
| MB 483933 | Link 2 | 2 | 82.5 | 165 | 605430 | J Marcs
| MC 484108 | Hrdwre LHQ Cure Retainer | 1 lot |  | 113.4375 | PRN157367 | McMaster
| 92580A311 | Threaded Rod, 1/2-20 x 12' | 6 | 45.5875 | 273.525 | PRN157695 | McMaster
| MC 484108 | Hdwre Curing Retainer Assy | 1 Lot |  | 100.9375 | PRN157368 | McMaster
| 98950A433 | Threaded Rod, 1/2-20 x12' | 18 | 24.2875 | 437.175 | PRN148953 | McMaster
|  | Curing Mold Alignment Tube | 1 | 1988.75 | 1988.75
83948.825
|  | Discription | techs | rate | hrs/tech | qty parts
|  | Stack short sections | 2 | 97.34 | 20 | 5 | 19468
|  | Weld short stacks $112/hr | 1 | 112 | 6 | 5 | 3360
|  | QC | 1 | 108 | 5 | 6 | 1200
|  | Assembly on transfer table | 2 | 97 | 16 | 1 | 3104
|  | Polish contour with emery cloth | 2 | 97 | 8 | 1 | 1552
|  | Engineer | 1 | 153.59 | 32 | 1 | 1280
|  | Total |  |  |  |  | 29964
| W/C Tooling | [6 empty] | W/C Tooling |  |  |  |  | W/C Tooling
1 | MB 344062 | Side Stiffening Plate | 4 |  | 821.25 | MSV 3201 | VMS | MB 344062 | Side Stiffening Plate | 6 | 205.3125 | 1231.875 | MB 344062 | Side Stiffening Plate | 2 | 205.3125 | 410.625
2 | MB 461117 | Rod | 2 |  | 456.25 | MSV 3201 | VMS | MB 461117 | Rod | 3 | 311.0795 | 933.2386 | MB 461117 | Rod | 2 | 311.0795 | 622.1591
3 | MD 483565 | Winding Isle Key Bar 1 | 8 | 106.25 | 850 | 605071 | Medco | MD 483565 | Winding Isle Key Bar 1 | 11 | 106.25 | 1168.75 | MD 483565 | Winding Isle Key Bar 1 | 4 | 106.25 | 425
4 | MB 483566 | Winding Isle Key Bar 2 | 1 |  | 125 | 605071 | Medco | MB 483566 | Winding Isle Key Bar 2 | 2 | 125 | 250 | MB 483566 | Winding Isle Key Bar 2 | 0 | 125 | 0
5 | MC 483567 | Winding Isle Key Bar - LE | 1 |  | 1125 | 605071 | Medco | MC 483567 | Winding Isle Key Bar - LE | 2 | 1125 | 2250 | MC 483567 | Winding Isle Key Bar - LE | 0 | 1125 | 0
6 | MC 483568 | Winding Isle Key Bar RE | 1 |  | 1106.25 | 605071 | Medco | MC 483568 | Winding Isle Key Bar RE | 2 | 1106.25 | 2212.5 | MC 483568 | Winding Isle Key Bar RE | 0 | 1106.25 | 0
7 | MB 483881 | Winding Isle Key Bar 3 | 1 |  | 118.75 | 605071 | Medco | MB 483881 | Winding Isle Key Bar 3 | 2 | 118.75 | 237.5 | MB 483881 | Winding Isle Key Bar 3 | 0 | 118.75 | 0
8 | MB 483862 | Mandrel Key Bar | 1 |  | 1500 | 605071 | Medco | MB 483862 | Mandrel Key Bar | 2 | 2045.4545 | 4090.9091 | MB 483862 | Mandrel Key Bar | 1 | 2045.4545 | 2045.4545
9 | MC 483835 | Winding Mandrel Lam 2 | 12 | 531.25 | 6375 | 605003 | K I Machine | MC 483835 | Winding Mandrel Lam 2 | 17 | 531.25 | 9031.25 | MC 483835 | Winding Mandrel Lam 2 | 0 | 531.25 | 0
10 | MC 483836 | Winding Mandrel Lam 1 | 56 | 237.5 | 13300 | 605003 | K I Machine | MC 483836 | Winding Mandrel Lam 1 | 77 | 237.5 | 18287.5 | MC 483836 | Winding Mandrel Lam 1 | 20 | 237.5 | 4750
11 | MD 483702 A | Mandrel Support Block | 1 |  | 3662.5 | 605035 | Medco | MD 483702 A | Mandrel Support Block | 2 | 3662.5 | 7325 | MD 483702 A | Mandrel Support Block | 0 | 3662.5 | 0
12 | MD 483839 A | Mandrel Supp. Mid Block | 1 |  | 3218.75 | 605035 | Medco | MD 483839 A | Mandrel Supp. Mid Block | 2 | 3218.75 | 6437.5 | MD 483839 A | Mandrel Supp. Mid Block | 1 | 3218.75 | 3218.75
13 | MD 483857 | Mandel Support Block 2 | 1 |  | 3000 | 605035 | Medco | MD 483857 | Mandel Support Block 2 | 2 | 3000 | 6000 | MD 483857 | Mandel Support Block 2 | 0 | 3000 | 0
14 | MD 483875 | Winding Mandrel Lam 2-B | 4 | 562.5 | 2250 | 605003 | K I Machine | MD 483875 | Winding Mandrel Lam 2-B | 6 | 562.5 | 3375 | MD 483875 | Winding Mandrel Lam 2-B | 0 | 562.5 | 0
15 | MD 483947 | L2 Curing Spacer 2 | 2 | 1343.75 | 2687.5 | 605772 | Hi Tech | MD 483947 | L2 Curing Spacer 2 | 3 | 1343.75 | 4031.25 | MD 483947 | L2 Curing Spacer 2 | 0 | 1343.75 | 0
16 | MD 483948 | L2 Curing Spacer | 7 | 1343.75 | 9406.25 | 605772 | Hi Tech | MD 483948 | L2 Curing Spacer | 14 | 1343.75 | 18812.5 | MD 483948 | L2 Curing Spacer | 4 | 1343.75 | 5375
17 | MD 483949 A | L2 Cure Spacer TRNS 1 | 1 |  | 2147.5 | 606915 | Hi Tech | MD 483949 A | L2 Cure Spacer TRNS 1 | 1 | 2147.5 | 2147.5 | MD 483949 A | L2 Cure Spacer TRNS 1 | 0 | 2147.5 | 0
18 | MD 483950 A | L2 Cure Spacer TRNS 2 | 1 |  | 2987.5 | 606915 | Hi Tech | MD 483950 A | L2 Cure Spacer TRNS 2 | 1 | 2987.5 | 2987.5 | MD 483950 A | L2 Cure Spacer TRNS 2 | 0 | 2987.5 | 0
19 | MD 483951 A | L2 Cure Spacer TRNS 3 | 1 |  | 2207.5 | 606915 | Hi Tech | MD 483951 A | L2 Cure Spacer TRNS 3 | 1 | 2207.5 | 2207.5 | MD 483951 A | L2 Cure Spacer TRNS 3 | 0 | 2207.5 | 0
20 | MD 483952 A | L2 Cure Spacer TRNS 4 | 1 |  | 2987.5 | 606915 | Hi Tech | MD 483952 A | L2 Cure Spacer TRNS 4 | 1 | 2987.5 | 2987.5 | MD 483952 A | L2 Cure Spacer TRNS 4 | 0 | 2987.5 | 0
21 | MD 483953 A | L2 Radial Size Spacer 1 | 12 | 823.75 | 9885 | 606915 | Hi Tech | MD 483953 A | L2 Radial Size Spacer 1 | 16 | 823.75 | 13180 | MD 483953 A | L2 Radial Size Spacer 1 | 4 | 823.75 | 3295
22 | MD 483954 A | L2 Radial Size Spacer 2 | 12 | 823.75 | 9885 | 606915 | Hi Tech | MD 483954 A | L2 Radial Size Spacer 2 | 16 | 823.75 | 13180 | MD 483954 A | L2 Radial Size Spacer 2 | 4 | 823.75 | 3295
23 | MC 483955 A | L1 Radial Size Spacer | 24 | 767.5 | 18420 | 606915 | Hi Tech | MC 483955 A | L1 Radial Size Spacer | 32 | 767.5 | 24560 | MC 483955 A | L1 Radial Size Spacer | 8 | 767.5 | 6140
24 | MB 483956 | Pusher Block Inner Layer | 2 | 272.5 | 545 | 605670 | J Marcs | MB 483956 | Pusher Block Inner Layer | 2 | 272.5 | 545 | MB 483956 | Pusher Block Inner Layer | 0 | 272.5 | 0
25 | MB 483957 | Curing Align Key Bar | 2 | 111.25 | 222.5 | 605670 | J Marcs | MB 483957 | Curing Align Key Bar | 3 | 111.25 | 333.75 | MB 483957 | Curing Align Key Bar | 0 | 111.25 | 0
26 | MD 483958 A | Curing Retainer | 2 | 1187.5 | 2375 | 606709 | Comet | MD 483958 A | Curing Retainer | 3 | 1187.5 | 3562.5 | MD 483958 A | Curing Retainer | 0 | 1187.5 | 0
27 | MB 483959 | Pole Slot Pin | 18 | 43.75 | 787.5 | 605670 | J Marcs | MB 483959 | Pole Slot Pin | 25 | 43.75 | 1093.75 | MB 483959 | Pole Slot Pin | 6 | 43.75 | 262.5
28 | MD 483960 A | Curing Retainer Middle | 1 |  | 1187.5 | 606709 | Comet | MD 483960 A | Curing Retainer Middle | 2 | 1187.5 | 2375 | MD 483960 A | Curing Retainer Middle | 1 | 1187.5 | 1187.5
29 | MC 483969 | L1 Sizing Bar | 6 | 550 | 3300 | 605772 | Hi Tech | MC 483969 | L1 Sizing Bar | 12 | 550 | 6600 | MC 483969 | L1 Sizing Bar | 2 | 550 | 1100
30 | MC 483970 | L2 Sizing Bar 2 | 2 | 550 | 1100 | 605772 | Hi Tech | MC 483970 | L2 Sizing Bar 2 | 4 | 550 | 2200 | MC 483970 | L2 Sizing Bar 2 | 0 | 550 | 0
31 | MC 483971 | L2 Sizing Bar 3 | 2 | 550 | 1100 | 605772 | Hi Tech | MC 483971 | L2 Sizing Bar 3 | 4 | 550 | 2200 | MC 483971 | L2 Sizing Bar 3 | 0 | 550 | 0
32 | MB 483972 | Curing Align Key Bar 2 | 6 | 61.25 | 367.5 | 605670 | J Marcs | MB 483972 | Curing Align Key Bar 2 | 8 | 61.25 | 490 | MB 483972 | Curing Align Key Bar 2 | 2 | 61.25 | 122.5
33 | MB 483973 | Pusher Block Outer Layer | 2 | 272.5 | 545 | 605670 | J Marcs | MB 483973 | Pusher Block Outer Layer | 2 | 272.5 | 545 | MB 483973 | Pusher Block Outer Layer | 0 | 272.5 | 0
34 | MC 483974 | L2 Sizing Bar 1 | 2 | 550 | 1100 | 605772 | Hi Tech | MC 483974 | L2 Sizing Bar 1 | 4 | 550 | 2200 | MC 483974 | L2 Sizing Bar 1 | 2 | 550 | 1100
35 | MB 484162 | Shim, Middle | 2 |  | 273.75 | MSV 3248 | VMS | MB 484162 | Shim, Middle | 3 | 136.875 | 410.625 | MB 484162 | Shim, Middle | 2 | 136.875 | 273.75
36 | MB 484163 | Shim, End | 4 |  | 365 | MSV 3248 | VMS | MB 484163 | Shim, End | 6 | 91.25 | 547.5 | MB 484163 | Shim, End | 0 | 91.25 | 0
37 | MB 484180 | Shim, Strip | 12 |  | 638.75 | MSV 3248 | VMS | MB 484180 | Shim, Strip | 17 | 53.2292 | 904.8958 | MB 484180 | Shim, Strip | 4 | 53.2292 | 212.9167
38 | MD 484191 | L1 Long Retainer | 20 | 68.75 | 1375 | 606420 | J Marcs | MD 484191 | L1 Long Retainer | 28 | 68.75 | 1925 | MD 484191 | L1 Long Retainer | 6 | 68.75 | 412.5
39 | MB 484192 | L1 Short Retainer | 20 | 38.75 | 775 | 606420 | J Marcs | MB 484192 | L1 Short Retainer | 28 | 38.75 | 1085 | MB 484192 | L1 Short Retainer | 6 | 38.75 | 232.5
40 | MB 484193 | L2 Long Retainer | 20 | 82.5 | 1650 | 606420 | J Marcs | MB 484193 | L2 Long Retainer | 28 | 82.5 | 2310 | MB 484193 | L2 Long Retainer | 6 | 82.5 | 495
41 | MB 484194 | L2 Short Retainer | 20 | 46.25 | 925 | 606420 | J Marcs | MB 484194 | L2 Short Retainer | 28 | 46.25 | 1295 | MB 484194 | L2 Short Retainer | 6 | 46.25 | 277.5
42 | MB 484263 | Cradle Wing Assembly | [5 empty] | MB 484263 | Cradle Wing Assembly |  |  |  | MB 484263 | Cradle Wing Assembly
43 | MB 484261 | Fixture Wing | 2 | 868.75 | 1737.5 | 606708 | Medco | MB 484261 | Fixture Wing | 0 | 868.75 | 0 | MB 484261 | Fixture Wing | 0 | 868.75 | 0
44 | MC 484262 | Fixture Cradle | 1 |  | 781.25 | 606708 | Medco | MC 484262 | Fixture Cradle | 0 |  | 0 | MC 484262 | Fixture Cradle | 0 |  | 0
45 | 92185A624 | SHCS, 3/8-16 x 1 1/2 SS | 5/pk |  | 6.75 | PRN158730 | McMaster | 92185A624 | SHCS, 3/8-16 x 1 1/2 SS | 5/pk |  | 6.75 | 92185A624 | SHCS, 3/8-16 x 1 1/2 SS | 5/pk |  | 6.75
46 | 98404A510 | Pin, Quick Rel 1/2 x 3 | 2 |  | 16.2 | PRN158730 | McMaster | 98404A510 | Pin, Quick Rel 1/2 x 3 | 0 |  | 0 | 98404A510 | Pin, Quick Rel 1/2 x 3 | 0 |  | 0
47 | MB 484265 | Roller Support Assy | 2 |  | 821.25 | MSV 3259 | VMS | MB 484265 | Roller Support Assy | 0 |  | 0 | MB 484265 | Roller Support Assy | 0 |  | 0
48 | 10NBC1620TZP | Bearing, Torrington | 4 | 167.75 | 671 | PRN158923 | Motion Indust | 10NBC1620TZP | Bearing, Torrington | 0 | 167.75 | 0 | 10NBC1620TZP | Bearing, Torrington | 0 | 167.75 | 0
49 | U-CLBUB-0.63_DO.88-LO.310 | Bearing, Spacer, MISUMI | 4 | 13.0375 | 52.15 | PRN158923 | Motion Indust | U-CLBUB-0.63_DO.88-LO.310 | Bearing, Spacer, MISUMI | 0 | 13.0375 | 0 | U-CLBUB-0.63_DO.88-LO.310 | Bearing, Spacer, MISUMI | 0 | 13.0375 | 0
50 | U-SRF-0.63-L4.00 | Rotary Shaft, MISUMI | 2 | 15.725 | 15.725 | PRN158923 | Motion Indust | U-SRF-0.63-L4.00 | Rotary Shaft, MISUMI | 0 | 15.725 | 0 | U-SRF-0.63-L4.00 | Rotary Shaft, MISUMI | 0 | 15.725 | 0
51 | ME 493981 | Outer Layer Assy Hrdwr | 1lot |  | 666.5 | PRN158624 | McMaster | ME 493981 | Outer Layer Assy Hrdwr | 1lot |  | 666.5 | ME 493981 | Outer Layer Assy Hrdwr | 1lot |  | 666.5
52 | MB 484068 A | Curing Retainer Top | 6 | 581.25 | 3487.5 | 606110 | Medco | MB 484068 A | Curing Retainer Top | 0 | 581.25 | 0 | MB 484068 A | Curing Retainer Top | 0 | 581.25 | 0
|  | Bronze Wedge Tooling | 2 | 1100 | 2200 |  |  |  | Bronze Wedge Tooling | 0 | 1100 | 0 |  | Bronze Wedge Tooling | 0 | 1100 | 0
[5 empty] | 127610.825 | [6 empty] | 178221.0436 |  |  |  |  | 35926.9053
| Discription | techs | rate | hrs/tech |  |  |  | Discription | techs | rate | hrs/tech |  | Discription | techs | rate | hrs/tech
| QC | 1 | 108 | 360 | 38880 |  |  | QC | 1 | 108 | 336 | 36288 | QC | 1 | 108 | 168 | 18144
Reference from LHQ
Curing Mold
| P/N | Description | Qty | Cost Per | Total | PO | Vendor
| ME 483304 | End Block | 2 | 2495 | 4990 | 602597 | Medco
| ME 483305 D | Lamination | 5600 | 4.49 | 25144 | 603978 | Larsen Mfg
|  | Die | 1 |  | 31250 | 603978 | Larsen Mfg
| MB 483306 | Lifting Bar | 8 | 38 | 304 | 602129 | J Marcs
| MB 483307 | Lifting Bar Spacer | 8 | 86 | 688 | 602129 | J Marcs
| MB 483909 | Upper Ring Insert | 3 |  | 876 | MSV 3226 | VMS
| MB 483928 | Cover Layer 1-1 | 2 | 170 | 340 | 605430 | J Marcs
| MB 483929 | Cover Layer 1-2 | 2 | 124 | 248 | 605430 | J Marcs
| MB 483930 | Cover Layer 2-1 | 2 | 203 | 406 | 605430 | J Marcs
| MB 483931 | Cover Layer 2-2 | 2 | 127 | 254 | 605430 | J Marcs
| MB 483932 | Link 1 | 2 | 98 | 196 | 605430 | J Marcs
| MB 483933 | Link 2 | 2 | 66 | 132 | 605430 | J Marcs
| MC 484108 | Hrdwre LHQ Cure Retainer | 1 lot |  | 90.75 | PRN157367 | McMaster
| 92580A311 | Threaded Rod, 1/2-20 x 12' | 6 | 36.47 | 218.82 | PRN157695 | McMaster
| MC 484108 | Hdwre Curing Retainer Assy | 1 Lot |  | 80.75 | PRN157368 | McMaster
| 98950A433 | Threaded Rod, 1/2-20 x12' | 18 | 19.43 | 349.74 | PRN148953 | McMaster
|  | Curing Mold Alignment Tube | 1 | 1591 | 1591
67159.06
W/C Tooling
| MB 344062 | Side Stiffening Plate | 4 |  | 657 | MSV 3201 | VMS
| MB 461117 | Rod | 2 |  | 365 | MSV 3201 | VMS
| MC 483485 | Key Bar - Side - Long | 4 | 210 | 840 | 604293 | M1 Tool
| MC 483486 | Key Bat - Side - Short | 8 | 66 | 528 | 604293 | M1 Tool
| MD 483565 | Winding Isle Key Bar 1 | 8 | 85 | 680 | 605071 | Medco
| MB 483566 | Winding Isle Key Bar 2 | 1 |  | 100 | 605071 | Medco
| MC 483567 | Winding Isle Key Bar - LE | 1 |  | 900 | 605071 | Medco
| MC 483568 | Winding Isle Key Bar RE | 1 |  | 885 | 605071 | Medco
| MB 483881 | Winding Isle Key Bar 3 | 1 |  | 95 | 605071 | Medco
| MB 483862 | Mandrel Key Bar | 1 |  | 1200 | 605071 | Medco
| MC 483835 | Winding Mandrel Lam 2 | 12 | 425 | 5100 | 605003 | K I Machine
| MC 483836 | Winding Mandrel Lam 1 | 56 | 190 | 10640 | 605003 | K I Machine
| MD 483702 A | Mandrel Support Block | 1 |  | 2930 | 605035 | Medco
| MD 483839 A | Mandrel Supp. Mid Block | 1 |  | 2575 | 605035 | Medco
| MD 483857 | Mandel Support Block 2 | 1 |  | 2400 | 605035 | Medco
| MD 483875 | Winding Mandrel Lam 2-B | 4 | 450 | 1800 | 605003 | K I Machine
| MD 483947 | L2 Curing Spacer 2 | 2 | 1075 | 2150 | 605772 | Hi Tech
| MD 483948 | L2 Curing Spacer | 7 | 1075 | 7525 | 605772 | Hi Tech
| MD 483949 A | L2 Cure Spacer TRNS 1 | 1 |  | 1718 | 606915 | Hi Tech
| MD 483950 A | L2 Cure Spacer TRNS 2 | 1 |  | 2390 | 606915 | Hi Tech
| MD 483951 A | L2 Cure Spacer TRNS 3 | 1 |  | 1766 | 606915 | Hi Tech
| MD 483952 A | L2 Cure Spacer TRNS 4 | 1 |  | 2390 | 606915 | Hi Tech
| MD 483953 A | L2 Radial Size Spacer 1 | 12 | 659 | 7908 | 606915 | Hi Tech
| MD 483954 A | L2 Radial Size Spacer 2 | 12 | 659 | 7908 | 606915 | Hi Tech
| MC 483955 A | L1 Radial Size Spacer | 24 | 614 | 14736 | 606915 | Hi Tech
| MB 483956 | Pusher Block Inner Layer | 2 | 218 | 436 | 605670 | J Marcs
| MB 483957 | Curing Align Key Bar | 2 | 89 | 178 | 605670 | J Marcs
| MD 483958 A | Curing Retainer | 2 | 950 | 1900 | 606709 | Comet
| MB 483959 | Pole Slot Pin | 18 | 35 | 630 | 605670 | J Marcs
| MD 483960 A | Curing Retainer Middle | 1 |  | 950 | 606709 | Comet
| MC 483969 | L1 Sizing Bar | 6 | 440 | 2640 | 605772 | Hi Tech
| MC 483970 | L2 Sizing Bar 2 | 2 | 440 | 880 | 605772 | Hi Tech
| MC 483971 | L2 Sizing Bar 3 | 2 | 440 | 880 | 605772 | Hi Tech
| MB 483972 | Curing Align Key Bar 2 | 6 | 49 | 294 | 605670 | J Marcs
| MB 483973 | Pusher Block Outer Layer | 2 | 218 | 436 | 605670 | J Marcs
| MC 483974 | L2 Sizing Bar 1 | 2 | 440 | 880 | 605772 | Hi Tech
| MB 484162 | Shim, Middle | 2 |  | 219 | MSV 3248 | VMS
| MB 484163 | Shim, End | 4 |  | 292 | MSV 3248 | VMS
| MB 484180 | Shim, Strip | 12 |  | 511 | MSV 3248 | VMS
| MD 484191 | L1 Long Retainer | 20 | 55 | 1100 | 606420 | J Marcs
| MB 484192 | L1 Short Retainer | 20 | 31 | 620 | 606420 | J Marcs
| MB 484193 | L2 Long Retainer | 20 | 66 | 1320 | 606420 | J Marcs
| MB 484194 | L2 Short Retainer | 20 | 37 | 740 | 606420 | J Marcs
| MB 484263 | Cradle Wing Assembly
| MB 484261 | Fixture Wing | 2 | 695 | 1390 | 606708 | Medco
| MC 484262 | Fixture Cradle | 1 |  | 625 | 606708 | Medco
| 92185A624 | SHCS, 3/8-16 x 1 1/2 SS | 5/pk |  | 5.4 | PRN158730 | McMaster
| 98404A510 | Pin, Quick Rel 1/2 x 3 | 2 |  | 12.96 | PRN158730 | McMaster
| MB 484265 | Roller Support Assy | 2 |  | 657 | MSV 3259 | VMS
| 10NBC1620TZP | Bearing, Torrington | 4 | 134.2 | 536.8 | PRN158923 | Motion Indust
| U-CLBUB-0.63_DO.88-LO.310 | Bearing, Spacer, MISUMI | 4 | 10.43 | 41.72 | PRN158923 | Motion Indust
| U-SRF-0.63-L4.00 | Rotary Shaft, MISUMI | 2 | 12.58 | 12.58 | PRN158923 | Motion Indust
| ME 493981 | Outer Layer Assy Hrdwr | 1lot |  | 533.2 | PRN158624 | McMaster
| MB 484067 | Curing Retainer Bottom | 6 | 180 | 1080 | 606110 | Medco
| MB 484068 A | Curing Retainer Top | 6 | 465 | 2790 | 606110 | Medco
| MB 484106 | Curing Retainer Side | 12 | 78.25 | 939 | 606110 | Medco
| MB 484107 | Curing Retainer Brace | 6 | 140 | 840 | 606110 | Medco
|  | Bronze Wedge Tooling | 2 | 1100 | 2200
106755.66
Scale Up
Reuse 3.3 m long tooling, procure additional to make up 4.5 m long tooling

## Reaction and Impre. Tooling
| LHC-MQXF Reaction and Impregnation Tooling | Coil Length |  | Aperture Ratio MQXF/LHQ |  |  |  |  | LHC-MQXF Reaction and Impregnation Tooling | Coil Length | Length Ratio | [5 empty] | LHC-MQXF Reaction and Impregnation Tooling | Coil Length | Length Ratio
| 1 set | 3.3m long |  | 1.25 |  |  |  |  | 1 set | 4.5m long | 1.3636 | [5 empty] | 1 set | 4.5m long | 1.3636
| Description | Reference Drawing # | Quantity | Req/PO# | Vendor | Buyer | Unit Price | Estimated Cost | Description | Reference Drawing # | Quantity | Req/PO# | Vendor | Buyer | Unit Price | Estimated Cost | Description | Reference Drawing # | Quantity | Req/PO# | Vendor | Buyer | Unit Price | Estimated Cost
1 | Mandrel Blocks | 25-2003004-01 | 70 | 234413/606818 | K1 Machine | Evans | 409.375 | 28656.25 | Mandrel Blocks | 25-2003004-01 | 95.4545 | 234413/606818 | K1 Machine | Evans | 409.375 | 39076.7045 | Mandrel Blocks | 25-2003004-01 | 25.4545 | 234413/606818 | K1 Machine | Evans | 409.375 | 10420.4545
2 | Mandrel Blocks | 25-2003004-02 | 70 | 234413/606818 | K1 Machine | Evans | 409.375 | 28656.25 | Mandrel Blocks | 25-2003004-02 | 95.4545 | 234413/606818 | K1 Machine | Evans | 409.375 | 39076.7045 | Mandrel Blocks | 25-2003004-02 | 25.4545 | 234413/606818 | K1 Machine | Evans | 409.375 | 10420.4545
3 | Form Blocks | 25-2003005 | 128 | 234413/606818 | K1 Machine | Evans | 344.375 | 44080 | Form Blocks | 25-2003005 | 174.5455 | 234413/606818 | K1 Machine | Evans | 344.375 | 60109.0909 | Form Blocks | 25-2003005 | 43 | 234413/606818 | K1 Machine | Evans | 344.375 | 14808.125
4 | Form Blocks-Mod | 25-2003022-01 | 6 | 234413/606818 | K1 Machine | Evans | 490.5 | 2943 | Form Blocks-Mod | 25-2003022-01 | 8.1818 | 234413/606818 | K1 Machine | Evans | 490.5 | 4013.1818 | Form Blocks-Mod | 25-2003022-01 | 0 | 234413/606818 | K1 Machine | Evans | 490.5 | 0
5 | Form Blocks-Mod | 25-2003022-02 | 6 | 234413/606818 | K1 Machine | Evans | 490.5 | 2943 | Form Blocks-Mod | 25-2003022-02 | 8.1818 | 234413/606818 | K1 Machine | Evans | 490.5 | 4013.1818 | Form Blocks-Mod | 25-2003022-02 | 0 | 234413/606818 | K1 Machine | Evans | 490.5 | 0
6
7 | Base Plate | 25-2003003 | 1 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 10531.25 | 10531.25 | Base Plate | 25-2003003 | 1.3636 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 14360.7955 | 19582.9029 | Base Plate | 25-2003003 | 1 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 19582.9029 | 19582.9029
8 | Top Plate | 25-2003006 | 1 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 17843.75 | 17843.75 | Top Plate | 25-2003006 | 1.3636 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 24332.3864 | 33180.5269 | Top Plate | 25-2003006 | 1 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 33180.5269 | 33180.5269
9 | Side Rail | 25-2003007 | 4 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 2968.75 | 11875 | Side Rail | 25-2003007 | 5.4545 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 2968.75 | 16193.1818 | Side Rail | 25-2003007 | 2 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 2968.75 | 5937.5
10 | Pusher Bar | 25-2003008-01 | 8 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 431.25 | 3450 | Pusher Bar | 25-2003008-01 | 10.9091 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 431.25 | 4704.5455 | Pusher Bar | 25-2003008-01 | 3 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 431.25 | 1293.75
11 | Pusher Bar | 25-2003008-02 | 4 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 431.25 | 1725 | Pusher Bar | 25-2003008-02 | 5.4545 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 431.25 | 2352.2727 | Pusher Bar | 25-2003008-02 | 2 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 431.25 | 862.5
12 | End Plate | 25-2003009 | 2 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 900 | 1800 | End Plate | 25-2003009 | 2.7273 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 900 | 2454.5455 | End Plate | 25-2003009 | 0 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 900 | 0
13 | End Plate-LE | 25-2003010 | 1 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 968.75 | 968.75 | End Plate-LE | 25-2003010 | 1.3636 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 968.75 | 1321.0227 | End Plate-LE | 25-2003010 | 0 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 968.75 | 0
14 | Midplane Shim | 25-2003011 | 4 | 234414 |  | Evans | 286.5 | 1146 | Midplane Shim | 25-2003011 | 5.4545 | 234414 |  | Evans | 286.5 | 1562.7273 | Midplane Shim | 25-2003011 | 2 | 234414 |  | Evans | 286.5 | 573
15 | Liner | 25-2003012 | 2 | 234414 |  | Evans | 430.25 | 860.5 | Liner | 25-2003012 | 2.7273 | 234414 |  | Evans | 430.25 | 1173.4091 | Liner | 25-2003012 | 1 | 234414 |  | Evans | 430.25 | 430.25
16 | Lead Seal Cover | 25-2003016 | 2 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 150 | 300 | Lead Seal Cover | 25-2003016 | 2.7273 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 150 | 409.0909 | Lead Seal Cover | 25-2003016 | 2 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 150 | 300
17 | End Saddle Link Assy | 252003019-01 | 4 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 485 | 1940 | End Saddle Link Assy | 252003019-01 | 5.4545 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 485 | 2645.4545 | End Saddle Link Assy | 252003019-01 | 0 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 485 | 0
18 | Alignment Pin | 25-2003023 | 12 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 22.5 | 270 | Alignment Pin | 25-2003023 | 16.3636 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 22.5 | 368.1818 | Alignment Pin | 25-2003023 | 5 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 22.5 | 112.5
19 | Alignment Pin Seal | 25-2003024 | 6 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 35 | 210 | Alignment Pin Seal | 25-2003024 | 8.1818 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 35 | 286.3636 | Alignment Pin Seal | 25-2003024 | 3 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 35 | 105
20 | Seal Compression Ring | 25-2003025 | 6 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 43.75 | 262.5 | Seal Compression Ring | 25-2003025 | 8.1818 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 43.75 | 357.9545 | Seal Compression Ring | 25-2003025 | 3 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 43.75 | 131.25
21 | Top Plate | 25-2003026 | 1 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 9593.75 | 9593.75 | Top Plate | 25-2003026 | 1.3636 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 9593.75 | 13082.3864 | Top Plate | 25-2003026 | 0 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 9593.75 | 0
22 | Lead End Plate Assy | 25-2003030 | 1 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 1043.75 | 1043.75 | Lead End Plate Assy | 25-2003030 | 1.3636 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 1043.75 | 1423.2955 | Lead End Plate Assy | 25-2003030 | 0 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 1043.75 | 0
23 | Base Plate | 25-2003033 | 1 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 15356.25 | 15356.25 | Base Plate | 25-2003033 | 1.3636 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 15356.25 | 20940.3409 | Base Plate | 25-2003033 | 0 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 15356.25 | 0
24 | Pole Alignment Key | 25-2003034 | 16 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 47.5 | 760 | Pole Alignment Key | 25-2003034 | 21.8182 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 47.5 | 1036.3636 | Pole Alignment Key | 25-2003034 | 6 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 47.5 | 285
25 | Keyway Filler | 25-2003035 | 12 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 28.75 | 345 | Keyway Filler | 25-2003035 | 16.3636 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 28.75 | 470.4545 | Keyway Filler | 25-2003035 | 5 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 28.75 | 143.75
26 | Lead Seal-Impreg. | 25-199.17-3 | 2 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 75 | 150 | Lead Seal-Impreg. | 25-199.17-3 | 2.7273 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 75 | 204.5455 | Lead Seal-Impreg. | 25-199.17-3 | 1 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 75 | 75
27 | Compression Disc-Impreg | 25-199.18-3 | 2 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 168.75 | 337.5 | Compression Disc-Impreg | 25-199.18-3 | 2.7273 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 168.75 | 460.2273 | Compression Disc-Impreg | 25-199.18-3 | 1 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 168.75 | 168.75
28 | End Saddle Link Assy | 25-2003019-02 | 1 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 485 | 485 | End Saddle Link Assy | 25-2003019-02 | 1.3636 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 485 | 661.3636 | End Saddle Link Assy | 25-2003019-02 | 0 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 485 | 0
| 3/8"-16 Steel SHCS | 91251A622 | 150 | 234608/606703 | McMaster Carr | Johnson | 0.2098 | 31.47 | 3/8"-16 Steel SHCS | 91251A622 | 204.5455 | 234608/606703 | McMaster Carr | Johnson | 0.2098 | 42.9136 | 3/8"-16 Steel SHCS | 91251A622 | 54.5455 | 234608/606703 | McMaster Carr | Johnson | 0.2098 | 11.4436
| 3/4" Steel Flatwasher | 90126A036 | 168 | 234608/606703 | McMaster Carr | Johnson | 0.15571 | 26.16 | 3/4" Steel Flatwasher | 90126A036 | 229.0909 | 234608/606703 | McMaster Carr | Johnson | 0.15571 | 35.6727 | 3/4" Steel Flatwasher | 90126A036 | 61.0909 | 234608/606703 | McMaster Carr | Johnson | 0.15571 | 9.5127
| 3/4"-10 X 8" Steel HHCS | 91247A863 | 232 | 234608/606703 | McMaster Carr | Johnson | 4.61 | 1069.52 | 3/4"-10 X 8" Steel HHCS | 91247A863 | 316.3636 | 234608/606703 | McMaster Carr | Johnson | 4.61 | 1458.4364 | 3/4"-10 X 8" Steel HHCS | 91247A863 | 84.3636 | 234608/606703 | McMaster Carr | Johnson | 4.61 | 388.9164
| 3/4"-10 Steel Hex Nut | 95462A538 | 150 | 234608/606703 | McMaster Carr | Johnson | 0.4116 | 61.74 | 3/4"-10 Steel Hex Nut | 95462A538 | 204.5455 | 234608/606703 | McMaster Carr | Johnson | 0.4116 | 84.1909 | 3/4"-10 Steel Hex Nut | 95462A538 | 54.5455 | 234608/606703 | McMaster Carr | Johnson | 0.4116 | 22.4509
| 3/8"-16 X 1/2" Steel SHCS | 91251A628 | 150 | 234608/606703 | McMaster Carr | Johnson | 0.3096 | 46.44 | 3/8"-16 X 1/2" Steel SHCS | 91251A628 | 204.5455 | 234608/606703 | McMaster Carr | Johnson | 0.3096 | 63.3273 | 3/8"-16 X 1/2" Steel SHCS | 91251A628 | 54.5455 | 234608/606703 | McMaster Carr | Johnson | 0.3096 | 16.8873
| 3/8"-16 X 1+1/8" Stl SHCS | 91251A588 | 20 | 234608/606703 | McMaster Carr | Johnson | 1.178 | 23.56 | 3/8"-16 X 1+1/8" Stl SHCS | 91251A588 | 27.2727 | 234608/606703 | McMaster Carr | Johnson | 1.178 | 32.1273 | 3/8"-16 X 1+1/8" Stl SHCS | 91251A588 | 7.2727 | 234608/606703 | McMaster Carr | Johnson | 1.178 | 8.5673
| 1/4"-20 X 1+3/4" Stl SHCS | 91251A548 | 25 | 234608/606703 | McMaster Carr | Johnson | 0.2012 | 5.03 | 1/4"-20 X 1+3/4" Stl SHCS | 91251A548 | 34.0909 | 234608/606703 | McMaster Carr | Johnson | 0.2012 | 6.8591 | 1/4"-20 X 1+3/4" Stl SHCS | 91251A548 | 9.0909 | 234608/606703 | McMaster Carr | Johnson | 0.2012 | 1.8291
| 1/4"-20 X 1+1/8" Stl SHCS | 91251A560 | 25 | 234608/606703 | McMaster Carr | Johnson | 0.2976 | 7.44 | 1/4"-20 X 1+1/8" Stl SHCS | 91251A560 | 34.0909 | 234608/606703 | McMaster Carr | Johnson | 0.2976 | 10.1455 | 1/4"-20 X 1+1/8" Stl SHCS | 91251A560 | 9.0909 | 234608/606703 | McMaster Carr | Johnson | 0.2976 | 2.7055
| 5/8"-11 X 1/2" Stl Set Screw | 91375A789 | 10 | 234608/606703 | McMaster Carr | Johnson | 0.808 | 8.08 | 5/8"-11 X 1/2" Stl Set Screw | 91375A789 | 13.6364 | 234608/606703 | McMaster Carr | Johnson | 0.808 | 11.0182 | 5/8"-11 X 1/2" Stl Set Screw | 91375A789 | 3.6364 | 234608/606703 | McMaster Carr | Johnson | 0.808 | 2.9382
| 3/32" X 7/8" Oring | 9561K43 | 25 | 234608/606703 | McMaster Carr | Johnson | 0.32 | 8 | 3/32" X 7/8" Oring | 9561K43 | 34.0909 | 234608/606703 | McMaster Carr | Johnson | 0.32 | 10.9091 | 3/32" X 7/8" Oring | 9561K43 | 9.0909 | 234608/606703 | McMaster Carr | Johnson | 0.32 | 2.9091
| 3/16" Oring Cord (Feet) | 9616K14 | 10 | 234608/606703 | McMaster Carr | Johnson | 0.55 | 5.5 | 3/16" Oring Cord (Feet) | 9616K14 | 13.6364 | 234608/606703 | McMaster Carr | Johnson | 0.55 | 7.5 | 3/16" Oring Cord (Feet) | 9616K14 | 3.6364 | 234608/606703 | McMaster Carr | Johnson | 0.55 | 2
| 1/4" Oring Cord (Feet) | 9616K15 | 40 | 234608/606703 | McMaster Carr | Johnson | 0.64 | 25.6 | 1/4" Oring Cord (Feet) | 9616K15 | 54.5455 | 234608/606703 | McMaster Carr | Johnson | 0.64 | 34.9091 | 1/4" Oring Cord (Feet) | 9616K15 | 14.5455 | 234608/606703 | McMaster Carr | Johnson | 0.64 | 9.3091
| 3/8"-16 X 3/4" SS SHCS | 92185A622 | 80 | 234608/606703 | McMaster Carr | Johnson | 0.962 | 76.96 | 3/8"-16 X 3/4" SS SHCS | 92185A622 | 109.0909 | 234608/606703 | McMaster Carr | Johnson | 0.962 | 104.9455 | 3/8"-16 X 3/4" SS SHCS | 92185A622 | 29.0909 | 234608/606703 | McMaster Carr | Johnson | 0.962 | 27.9855
| 3/4"-10 SS Hex Nut | 94804A360 | 150 | 234608/606703 | McMaster Carr | Johnson | 1.46 | 219 | 3/4"-10 SS Hex Nut | 94804A360 | 204.5455 | 234608/606703 | McMaster Carr | Johnson | 1.46 | 298.6364 | 3/4"-10 SS Hex Nut | 94804A360 | 54.5455 | 234608/606703 | McMaster Carr | Johnson | 1.46 | 79.6364
| 3/8"-16 X 1+1/2" SS SHCS | 92185A628 | 150 | 234608/606703 | McMaster Carr | Johnson | 1.32 | 198 | 3/8"-16 X 1+1/2" SS SHCS | 92185A628 | 204.5455 | 234608/606703 | McMaster Carr | Johnson | 1.32 | 270 | 3/8"-16 X 1+1/2" SS SHCS | 92185A628 | 54.5455 | 234608/606703 | McMaster Carr | Johnson | 1.32 | 72
| 5/8"-11 X 1/2" SS Set Screw | 92311A789 | 10 | 234608/606703 | McMaster Carr | Johnson | 0.784 | 7.84 | 5/8"-11 X 1/2" SS Set Screw | 92311A789 | 13.6364 | 234608/606703 | McMaster Carr | Johnson | 0.784 | 10.6909 | 5/8"-11 X 1/2" SS Set Screw | 92311A789 | 3.6364 | 234608/606703 | McMaster Carr | Johnson | 0.784 | 2.8509
| 3/8"-16 X 1+1/8" SS SHCS | 92196A625 | 20 | 234608/606703 | McMaster Carr | Johnson | 0.717 | 14.34 | 3/8"-16 X 1+1/8" SS SHCS | 92196A625 | 27.2727 | 234608/606703 | McMaster Carr | Johnson | 0.717 | 19.5545 | 3/8"-16 X 1+1/8" SS SHCS | 92196A625 | 7.2727 | 234608/606703 | McMaster Carr | Johnson | 0.717 | 5.2145
| 3/4"-10 X 8" SS HHCS | 92198A863 | 77 | 234608/606703 | McMaster Carr | Johnson | 9.16 | 705.32 | 3/4"-10 X 8" SS HHCS | 92198A863 | 105 | 234608/606703 | McMaster Carr | Johnson | 9.16 | 961.8 | 3/4"-10 X 8" SS HHCS | 92198A863 | 28 | 234608/606703 | McMaster Carr | Johnson | 9.16 | 256.48
| 1/4" X .010 SS Tube (Feet) | 89895K44 | 40 | 234608/606703 | McMaster Carr | Johnson | 4.0495 | 161.98 | 1/4" X .010 SS Tube (Feet) | 89895K44 | 54.5455 | 234608/606703 | McMaster Carr | Johnson | 4.0495 | 220.8818 | 1/4" X .010 SS Tube (Feet) | 89895K44 | 14.5455 | 234608/606703 | McMaster Carr | Johnson | 4.0495 | 58.9018
| 3/16" X .030" Cu Tube (Feet) | 5174K2 | 50 | 234608/606703 | McMaster Carr | Johnson | 0.6198 | 30.99 | 3/16" X .030" Cu Tube (Feet) | 5174K2 | 68.1818 | 234608/606703 | McMaster Carr | Johnson | 0.6198 | 42.2591 | 3/16" X .030" Cu Tube (Feet) | 5174K2 | 18.1818 | 234608/606703 | McMaster Carr | Johnson | 0.6198 | 11.2691
| 3/4" Steel Flatwasher | 98019A519 | 300 | 234608/606703 | McMaster Carr | Johnson | 1.49 | 447 | 3/4" Steel Flatwasher | 98019A519 | 409.0909 | 234608/606703 | McMaster Carr | Johnson | 1.49 | 609.5455 | 3/4" Steel Flatwasher | 98019A519 | 109.0909 | 234608/606703 | McMaster Carr | Johnson | 1.49 | 162.5455
| 1/4" X .010 SS Tube (Feet) |  | 80 | PRN159707 | Eagle Stainless | Schmidt | 4.8875 | 391 | 1/4" X .010 SS Tube (Feet) |  | 109.0909 | PRN159707 | Eagle Stainless | Schmidt | 4.8875 | 533.1818 | 1/4" X .010 SS Tube (Feet) |  | 29.0909 | PRN159707 | Eagle Stainless | Schmidt | 4.8875 | 142.1818
[6 empty] | Total |  | 192103.47 | [5 empty] | Total |  | 276029.5252 | [5 empty] | Total |  | 100129.2484
|  |  |  | Discription | techs | rate | hrs/tech |  |  |  | Discription | techs | rate | hrs/tech |  |  |  |  | Discription | techs | rate | hrs/tech
|  |  |  | QC | 1 | 108 | 224 | 24192 |  |  | QC | 1 | 108 | 224 | 24192 |  |  |  | QC | 1 | 108 | 144 | 15552
Reference from LHQ 2 sets
| Description | Drawing # | Quantity | Req/PO# | Vendor | Buyer | Estimated Cost | Actual Cost
2012-08-28
| Mandrel Blocks | 25-2003004-01 | 140 | 234413/606818 | K1 Machine | Evans | 42770 | 45850
| Mandrel Blocks | 25-2003004-02 | 140 | 234413/606818 | K1 Machine | Evans | 45920 | 45850
| Form Blocks | 25-2003005 | 256 | 234413/606818 | K1 Machine | Evans | 94080 | 70528
| Form Blocks-Mod | 25-2003022-01 | 12 | 234413/606818 | K1 Machine | Evans | 10620 | 4708.8
| Form Blocks-Mod | 25-2003022-02 | 12 | 234413/606818 | K1 Machine | Evans | 11520 | 4708.8
| Base Plate | 25-2003003 | 2 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 17366 | 16850
| Top Plate | 25-2003006 | 2 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 14920 | 28550
| Side Rail | 25-2003007 | 8 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 15576 | 19000
| Pusher Bar | 25-2003008-01 | 16 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 10252.8 | 5520
| Pusher Bar | 25-2003008-02 | 8 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 3409.6 | 2760
| End Plate | 25-2003009 | 4 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 4760 | 2880
| End Plate-LE | 25-2003010 | 2 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 3931 | 1550
| Midplane Shim | 25-2003011 | 8 | 234414 |  | Evans | 1833.6 | Requote
| Liner | 25-2003012 | 4 | 234414 |  | Evans | 1376.8 | Requote
| Lead Seal Cover | 25-2003016 | 4 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 1389.6 | 480
| End Saddle Link Assy | 252003019-01 | 8 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 3409.6 | 3104
| Alignment Pin | 25-2003023 | 24 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 2462.4 | 432
| Alignment Pin Seal | 25-2003024 | 12 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 657.6 | 336
| Seal Compression Ring | 25-2003025 | 12 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 657.6 | 420
| Top Plate | 25-2003026 | 2 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 23500 | 15350
| Lead End Plate Assy | 25-2003030 | 2 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 3931 | 1670
| Base Plate | 25-2003033 | 2 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 26726 | 24570
| Pole Alignment Key | 25-2003034 | 32 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 2284.8 | 1216
| Keyway Filler | 25-2003035 | 24 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 1689.6 | 552
| Lead Seal-Impreg. | 25-199.17-3 | 4 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 593.6 | 240
| Compression Disc-Impreg | 25-199.18-3 | 4 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 1233.6 | 540
| End Saddle Link Assy | 25-2003019-02 | 2 | 234414/607056 | Milan's Machining & Mfg Co. | Evans | 2264 | 776
| 3/8"-16 Steel SHCS | 91251A622 | 300 | 234608/606703 | McMaster Carr | Johnson | 62.94 | 62.94
| 3/4" Steel Flatwasher | 90126A036 | 315 | 234608/606703 | McMaster Carr | Johnson | 49.05 | 49.05
| 3/4"-10 X 8" Steel HHCS | 91247A863 | 310 | 234608/606703 | McMaster Carr | Johnson | 1429.1 | 1429.1
| 3/4"-10 Steel Hex Nut | 95462A538 | 300 | 234608/606703 | McMaster Carr | Johnson | 123.48 | 123.48
| 3/8"-16 X 1/2" Steel SHCS | 91251A628 | 300 | 234608/606703 | McMaster Carr | Johnson | 92.88 | 92.88
| 3/8"-16 X 1+1/8" Stl SHCS | 91251A588 | 35 | 234608/606703 | McMaster Carr | Johnson | 41.23 | 41.23
| 1/4"-20 X 1+3/4" Stl SHCS | 91251A548 | 50 | 234608/606703 | McMaster Carr | Johnson | 10.06 | 10.06
| 1/4"-20 X 1+1/8" Stl SHCS | 91251A560 | 50 | 234608/606703 | McMaster Carr | Johnson | 14.88 | 14.88
| 5/8"-11 X 1/2" Stl Set Screw | 91375A789 | 20 | 234608/606703 | McMaster Carr | Johnson | 16.16 | 16.16
| 3/32" X 7/8" Oring | 9561K43 | 25 | 234608/606703 | McMaster Carr | Johnson | 8 | 8
| 3/16" Oring Cord (Feet) | 9616K14 | 20 | 234608/606703 | McMaster Carr | Johnson | 11 | 11
| 1/4" Oring Cord (Feet) | 9616K15 | 80 | 234608/606703 | McMaster Carr | Johnson | 51.2 | 51.2
| 3/8"-16 X 3/4" SS SHCS | 92185A622 | 160 | 234608/606703 | McMaster Carr | Johnson | 153.92 | 153.92
| 3/4"-10 SS Hex Nut | 94804A360 | 300 | 234608/606703 | McMaster Carr | Johnson | 438 | 438
| 3/8"-16 X 1+1/2" SS SHCS | 92185A628 | 300 | 234608/606703 | McMaster Carr | Johnson | 396 | 396
| 5/8"-11 X 1/2" SS Set Screw | 92311A789 | 20 | 234608/606703 | McMaster Carr | Johnson | 15.68 | 15.68
| 3/8"-16 X 1+1/8" SS SHCS | 92196A625 | 40 | 234608/606703 | McMaster Carr | Johnson | 28.68 | 28.68
| 3/4"-10 X 8" SS HHCS | 92198A863 | 154 | 234608/606703 | McMaster Carr | Johnson | 1410.64 | 1410.64
| 1/4" X .010 SS Tube (Feet) | 89895K44 | 80 | 234608/606703 | McMaster Carr | Johnson | 280 | 323.96
| 3/16" X .030" Cu Tube (Feet) | 5174K2 | 100 | 234608/606703 | McMaster Carr | Johnson | 65.68 | 65.68
| 3/4" Steel Flatwasher | 98019A519 | 600 | 234608/606703 | McMaster Carr | Johnson | 894 | 894
| 1/4" X .010 SS Tube (Feet) |  | 160 | PRN159707 | Eagle Stainless | Schmidt | 782 | 782
| 3/4"-10 X 8" SS HHCS | 92198A863 | 154 |  | McMaster Carr | Olderr |  | 709.94
[6 empty] | Total |  | 308780.48
Scale Up
Reuse 3.3 m long tooling, procure additional to make up 4.5 m long tooling

## Testing Summary
Enter # of production tests (not including prototype) | 10
| Labor ($k FY12), fully burdened | M&S ($k FY12), fully burdened | Total
Test Stand Cost (MTF) | 1074.356 | 532.0452 | 1606.4012
Cryostat Construction | 1242.8 | 181.8107 | 1424.6107
First Prototype Operational Costs (MTF) | 136 | 81.8652 | 217.8652
Production Operational Costs (MTF) | 731 | 440.0254 | 1171.0255
Cryostat Disassembly/reassembly | 629 | 0 | 629
Grand Total |  |  | 4419.9025

## Test Stand
Test Stand 4 Upgrade Direct Cost and Labor
Row Labels | Engineer (p-wks) | Designer (p-wks) | Technician (p-wks) | M&S ($K)
Project | 12 |  |  |  |  | Labor | 245 | p-w
Feed Can | 14 | 25.4 | 18 | 117.22 |  |  | 5.543 | FTEs
Cryogenic System | 22.2 | 7 | 24 | 99
Power System | 2.5 |  | 1.5 | 11
Quench Protecton, DAQ upgrades | 15 |  | 35 | 134
Vacuum System |  |  |  | 21.2
Magnetic Measurement System | 14 | 8.4 | 46 | 59.5147
Grand Total | 79.7 | 40.8 | 124.5 | 441.9347
Burdened Material |  |  |  | 532.0452
Weekly FY12 burdened labor rates ($k) | 6 | 4.08 | 3.4 |  | Total ($k)
Grand Total Costs ($k) | 478.2 | 325.176 | 270.98 | 532.0452 | 1606.4012

## Test Stand Details
|  |  |  | DIRECT ESTIMATE ONLY | [10 empty] | FULLY LOADED ESTIMATE
| NEW ITEMS |  |  | LABOR |  |  | MATERIALS |  |  |  | SCHEDULE | [5 empty] | Worksheet "A" Breakdown
Category | System | Sub-System | Task or Item | Engineer (m-wks) | Designer (m-wks) | Technician (m-wks) | Unit | Qty | Price Per Unit ($K) | Total ($K) | Duration (Days) | Estimate Basis | Comments | Estimator | Fully Loaded Labor ($K) | Fully Loaded M&S ($K) | Materials ($K) | Equipment ($K) | Construction ($K)
Facility Modifications and Preparations | Project | Management |  | 12
| Feed Can |  | Dissassemble and Relocate External Piping and Transfer Lines |  |  | 0.6
| Feed Can | Lambda Plate | Remove Lambda Plate "tie-down" rods |  |  | 0.2
| Feed Can | Top Plate | Remove the Top Plate Assembly and store on support structure |  |  | 0.6
| Power System | Flexible Cables | 1500 MCM Flexible Cables - 2 pairs | 2.5 | [5 empty] | 11
| Power System | Flexible Cables | Disconnect existing flexible cables |  |  | 0.6
| Power System | Flexible Cables | Prep 1500 MCM cables and install at VMTF and Stand 4 |  |  | 0.9
| Feed Can | Power Leads | Construct and Install LTS bus section and flag |  |  | 1.2
| Feed Can | Power Leads | Mofidy the Vacuum Sleeve Assembly around the power leads | 1 | 1.2 | 0.4
| Feed Can | Power Leads | Prep 20 kA Power Leads and VTaps |  |  | 2.4
| Feed Can | Power Leads | 20 kA Vapor Cooled Leads | [6 empty] | 76.5
| Feed Can | Lambda Plate | Clean and Prep Lambda Plate surface |  |  | 0.2
| Feed Can | Power Leads | Install Power Leads on top plate |  |  | 1
| Feed Can | Top Plate | Install Top Plate Assembly and tie-down the Lambda plate |  |  | 1.4
| Feed Can | Lambda Plate | Check that the lambda plate sealed |  |  | 1.4
| Feed Can | Horizontal Bed | Modify the test stand supports and install supports | 4 | 12 | 0.8
| Feed Can | Auxilliary Services | Install Feed Box auxilliary services (air, water, etc.) | 2 |  | 6
| Feed Can | Adapter | Adapt Interconnect piping (Feedbox to magnet) | 5 | 8
| Feed Can | Interconnect | Leak checking fixtures | 2 | 4.2 | 1.8
| Feed Can | Adapter | Materials | [6 empty] | 10
| Feed Can | Adapter | Welder | [6 empty] | 12
| Feed Can | Adapter | Machining | [6 empty] | 13.5
| Feed Can | Adapter | Seals | [6 empty] | 2.22
| Feed Can | Adapter | Indium Ribbon | [6 empty] | 3
| Magnetic Measurement System | Measurement Probe | Design, fabricate, assemble, and test larger diameter probe | 6 | 4.2 | 13
| Magnetic Measurement System | Warm Finger Assembly | Design, fabricate, assemble, and test larger diameter assembly | 6 | 4.2 | 17
| Magnetic Measurement System | Warm Finger Assembly | Inner and Outer Tube |  |  |  |  | 100 | 0.16 | 16
| Magnetic Measurement System | Warm Finger Assembly | Bellows |  |  |  |  | 1000 | 0.001 | 1
| Magnetic Measurement System | Warm Finger Assembly | Quench Antenna |  |  |  |  | ??
| Magnetic Measurement System | Warm Finger Assembly | Vacuum Insulation Valve and Pumpout port |  |  |  |  | 500 | 0.002 | 1
| Magnetic Measurement System | Warm Finger Assembly | Lead Wire (Lakeshore) |  |  |  |  | 2.5 | 1 | 2.5
| Magnetic Measurement System | Warm Finger Assembly | Multi-pin connectors |  |  |  |  | 120 | 0.012 | 1.44
| Magnetic Measurement System | Warm Finger Assembly | Heaters |  |  |  |  | 50 | 0.006 | 0.3
| Magnetic Measurement System | Warm Finger Assembly | RTDs |  |  |  |  | 100 | 0.024 | 2.4
| Magnetic Measurement System | Warm Finger Assembly | Spiders, Flangers, Adapters, etc |  |  |  |  | lot |  | 5
| Magnetic Measurement System | Magnetic Measurement Table | Replace toothed belt, photo-eyes, covers on flexible coupling, translation slides | 2 |  | 16
| Magnetic Measurement System | Magnetic Measurement Table | Spares to refurbish measurement table |  |  |  |  | 478.24 | 0.003 | 1.4347
| Magnetic Measurement System | Magnetic Measurement Table | Driveshaft and Probe Bearings |  |  |  |  | 60 | 0.024 | 1.44
| Magnetic Measurement System | Magnetic Measurement Table | Bearing Housings |  |  |  |  | 75 | 0 | 7.5
| Magnetic Measurement System | Magnetic Measurement Table | Flexible Couplings |  |  |  |  | 160 | 0.012 | 1.92
| Magnetic Measurement System | Magnetic Measurement Table | Optical Sensors |  |  |  |  | 90 | 0.012 | 1.08
| Magnetic Measurement System | Magnetic Measurement Table | Material for Probe Assemblies |  |  |  |  | 250 | 0.03 | 7.5
| Magnetic Measurement System | Magnetic Measurement Table | Slot Machining |  |  |  |  | 75 | 0 | 9
| Magnetic Measurement System | Magnetic Measurement Table | Bridge between Measurement Table and Stand 4 |  |  |  |  | 0 | 0 | 0
| Vacuum System | Pumping Cart | Blower | [6 empty] | 10
| Vacuum System | Pumping Cart | Roughing Pump | [6 empty] | 6.5
| Vacuum System | Pumping Cart | Controls | [6 empty] | 3
| Vacuum System | Pumping Cart | Vacuum Gages and readouts | [6 empty] | 1.2
| Vacuum System | Pumping Cart | Cart | [6 empty] | 0.5
| Cryogenic System | Test Stand | Specify and Procure Valves and Instruments | 1
| Cryogenic System | Test Stand | Test Stand Hardening to reduce He losses |  |  | 2
| Cryogenic System | Test Stand | Valves, instruments, pipe, hoses, fitting | [6 empty] | 60
| Cryogenic System | Test Stand | Welder | [6 empty] | 3
| Cryogenic System | Quench Line | Design and analysis | 1.2
| Cryogenic System | Quench Line | Fabrication |  | 3 | 8
| Cryogenic System | Quench Line | Valves, instruments, pipe, hoses, fitting | [6 empty] | 20
| Cryogenic System | Quench Line | Welder | [6 empty] | 6
| Cryogenic System | Relief Discharge Header | Design and analysis | 0.2
| Cryogenic System | Relief Discharge Header | Fabrication |  | 1 | 2
| Cryogenic System | Relief Discharge Header | Valves, instruments, pipe, hoses, fitting | [6 empty] | 2
| Cryogenic System | Relief Discharge Header | Welder | [6 empty] | 1.5
| Cryogenic System | Pumping Line | Design and analysis | 0.8
| Cryogenic System | Pumping Line | Fabrication |  | 3 | 2
| Cryogenic System | Pumping Line | Valves, instruments, pipe, hoses, fitting | [6 empty] | 5
| Cryogenic System | Pumping Line | Welder | [6 empty] | 1.5
| Cryogenic System | Facility | Specify and Procure Valves and Instruments
| Cryogenic System | Facility | Cryo Controls Upgrade and Modifications | 6 |  | 10
| Cryogenic System | Facility | Commissioning | 4
| Cryogenic System | Safety | Documentation | 8
| Cryogenic System | Safety | Review | 1
| Quench Protecton, DAQ upgrades | Current Receiver |  | 1 | [5 empty] | 5
| Quench Protecton, DAQ upgrades | Isolation Amplifiers |  |  |  | 24 |  |  |  | 35
| Quench Protecton, DAQ upgrades | Quench Management System |  | 10 |  | 5 |  |  |  | 50
| Quench Protecton, DAQ upgrades | Slow Scan System |  | 4 |  | 1 |  |  |  | 28
| Quench Protecton, DAQ upgrades | Instrumentation | Replacement, Repair, or calibration |  |  | 4 |  |  |  | 10
| Quench Protecton, DAQ upgrades | Cables and Connectors |  |  |  | 1 |  |  |  | 6

## Operations
Operational Cost Per Test
Row Labels | Labor (p-wks) | M&S ($K)
Setup - Mechanical | 2
Setup- Electrical | 2
Leak Checking | 2.5
Test Support | 12
Dissasembly | 1.5
Consumables - He (4 wks of testing) |  | 24
Consumables - N2 (4 wks of testing) |  | 10
Grand Total | 20 | 34
Burdened Material |  | 40.9326
Technician FY12 burdened weekly labor rate ($k) | 3.4 |  | Total
Production Cost per test | 68 | 40.9326 | 108.9326
Multiply x2 for 1st prototype ($kFY12) | 136 | 81.8652 | 217.8652
Multiply x1.5 for 1st production ($kFY12) | 102 | 61.3989 | 163.3989
Multiply x 1.25 for 2nd production ($kFY12) | 85 | 51.1658 | 136.1658
Production Costs beyond first two tests ($kFY12) | 544 | 327.4608 | 871.4608
Total Production Operational Costs ($kFY12, not including prototype) | 731 | 440.0254 | 1171.0255
Prototype Operational Costs ($kFY12) | 136 | 81.8652 | 217.8652

## Operation Details
Step | Engineer (m-wks) | Designer (m-wks) | Technician (m-wks) | Unit | Qty | Price Per Unit ($K) | Total ($K) | Estimate Basis | Comments | Estimator | Fully Loaded Labor ($K) | Fully Loaded M&S ($K) | Materials ($K) | Equipment ($K) | Construction ($K)
Setup - Mechanical |  |  | 2
Setup- Electrical |  |  | 2
Leak Checking |  |  | 2.5
Test Support |  |  | 12
Dissasembly |  |  | 1.5
Consumables - He (4 wks of testing) | [6 empty] | 24 | IB1 He cost is $12K/week, split 50/50 between SRF and Magnet. The cost for a magnet test is 6*No of test-weeks.
Consumables - N2 (4 wks of testing) | [6 empty] | 10 | IB1 He cost is $5K/week, split 50/50 between SRF and Magnet. The cost for a magnet test is 2.5*No of test-weeks.

## Cryostat - half-length
LARP Nb3Sn Test Cryostat Cost Estimate
2012-05-07
Revised: |  | 2012-05-17 | First draft
|  | 2012-08-29 | Half-length version estimate
Assumed inflation per year |  | 2.4%
Test Cryostat
Description |  | Units | Units reqd | Unit cost | Ext total | Len mult | Inflation | Current total
Vacuum vessel |  | ea | 1 | 44000 | 44000 | 0.75 | 1.3292 | 43864.5239 | (based on Q2P1 - Jessica) |  |  | ~4.5/5.9
MLI (all) |  | ea | 1 | 2500 | 2500 | 0.55 | 1.2981 | 1784.852 | (based on Q3) |  |  | ~4.5/8.2
50K to 70K shield |  | ea | 1 | 8000 | 8000 | 0.55 | 1.2981 | 5711.5265 |  |  |  | ~4.5/8.2
Support |  | ea | 2 | 5500 | 11000 | 1 | 1.2981 | 14278.8164
Invar tie bars |  | ea | 2 | 1650 | 3300 | 0.55 | 1.2981 | 2356.0047 |  |  |  | ~4.5/8.2
Other piping |  | lot | 1 | 1000 | 1000 | 0.55 | 1.2981 | 713.9408 |  |  |  | ~4.5/8.2
Piping supports |  | ea | 2 | 600 | 1200 | 1 | 1.2981 | 1557.6891
Cold mass attach brackets |  | ea | 4 | 580 | 2320 | 1 | 1.2981 | 3011.5322
Cold mass end domes |  | ea | 2 | 2500 | 5000 | 1 | 1.2981 | 6490.3711
Cold mass bellows |  | ea | 3 | 1640 | 4920 | 1 | 1.2981 | 6386.5251
Cold mass extensions |  | ea | 2 | 750 | 1500 | 1 | 1.2981 | 1947.1113
Beam tube |  | ea | 1 | 500 | 500 | 0.55 | 1.2981 | 356.9704 |  |  |  | ~4.5/8.2
Assembly tooling |  | lot | 1 | 50000 | 50000 | 1 | 1 | 50000
Interconnect parts
Interconnect shield bridge |  | ea | 1 | 250 | 250 | 1 | 1.2981 | 324.5186
Interconnect bellows |  | lot | 1 | 7074.5045 | 7074.5045 | 1 | 1.2981 | 9183.2318
Squirm protectors |  | lot | 1 | 1250 | 1250 | 1 | 1.2981 | 1622.5928
Interconnect piping |  | lot | 1 | 500 | 500 | 1 | 1.2981 | 649.0371
Interconnect piping supports |  | ea | 1 | 600 | 600 | 1 | 1.2981 | 778.8445
Total parts cost per completed assembly |  |  |  |  | 144914.5045 |  |  | 151018.0883
Parts + OH | [7 empty] | 181810.6765
|  |  | Inspection and assy/disassy labor |  |  |  | Interconnect bellows |  |  | No. reqd | Unit cost | Ext total | Inflation | Current total
Labor type (assume $85,000/yr, 2,000 hr/yr) | Units | Unit cost | No. reqd | Hrs each | Ext total |  | Cold mass bellows |  |  | 2 | 1600 | 3200 | 1.2981 | 4153.8375
Tech (incoming insp) | hr | 85 | 2 | 100 | 17000 |  | Pumping line bellows |  |  | 1 | 750 | 750 | 1.2981 | 973.5557
Process engr (traveler) | hr | 85 | 1 | 100 | 8500 |  | Cooldown line bellows |  |  | 1 | 500 | 500 | 1.2981 | 649.0371
Tech (supervision) | hr | 85 | 1 | 160 | 13600 |  | Shield bellows |  |  | 2 | 500 | 1000 | 1.2981 | 1298.0742
Tech (assembly) | hr | 85 | 3 | 160 | 40800 |  | Total per triplet |  |  |  |  | 5450 |  | 7074.5045
Weldor | hr | 85 | 1 | 50 | 4250
Tech (inspection) | hr | 85 | 1 | 50 | 4250
Total cost per completed assembly |  |  |  |  | 88400
Estimated EDIA
Name |  | Labor rate | FY2013 | FY2014 | Total
Engineer |  | 312000 | 75% | 25% | 312000
Engineer |  | 312000 | 75% | 25% | 312000
Design drafter |  | 212160 | 75% | 50% | 265200
Design drafter |  | 212160 | 75% | 50% | 265200
Grand total for EDIA |  |  |  |  | 1154400
Grand total (parts, labor, EDIA) |  |  |  |  | 1424610.6765 |  | Recurring cost (per test) |  | 62900

## Cryostat-Full Length
LARP Nb3Sn Test Cryostat Cost Estimate
2012-05-07
Revised: |  | 2012-05-17 | First draft
Assumed inflation per year |  | 2.4%
Test Cryostat
Description |  | Units | Units reqd | Unit cost | Ext total | Len mult | Inflation | Current total
Vacuum vessel |  | ea | 1 | 44000 | 44000 | 1.5 | 1.3292 | 87729.0477 | (based on Q2P1 - Jessica)
MLI (all) |  | ea | 1 | 2500 | 2500 | 1.125 | 1.2981 | 3650.8337
50K to 70K shield |  | ea | 1 | 8000 | 8000 | 1.125 | 1.2981 | 11682.6679
Support |  | ea | 3 | 5500 | 16500 | 1 | 1.2981 | 21418.2245
Invar tie bars |  | ea | 4 | 1650 | 6600 | 1.125 | 1.2981 | 9638.201
Other piping |  | lot | 1 | 1000 | 1000 | 1.125 | 1.2981 | 1460.3335
Piping supports |  | ea | 3 | 600 | 1800 | 1 | 1.2981 | 2336.5336
Cold mass attach brackets |  | ea | 6 | 580 | 3480 | 1 | 1.2981 | 4517.2983
Cold mass end domes |  | ea | 2 | 2500 | 5000 | 1 | 1.2981 | 6490.3711
Cold mass bellows |  | ea | 3 | 1640 | 4920 | 1 | 1.2981 | 6386.5251
Cold mass extensions |  | ea | 2 | 750 | 1500 | 1 | 1.2981 | 1947.1113
Beam tube |  | ea | 1 | 500 | 500 | 1.125 | 1.2981 | 730.1667
Assembly tooling |  | lot | 1 | 50000 | 50000 | 1 | 1 | 50000
Interconnect parts
Interconnect shield bridge |  | ea | 1 | 250 | 250 | 1 | 1.2981 | 324.5186
Interconnect bellows |  | lot | 1 | 7074.5045 | 7074.5045 | 1 | 1.2981 | 9183.2318
Squirm protectors |  | lot | 1 | 1250 | 1250 | 1 | 1.2981 | 1622.5928
Interconnect piping |  | lot | 1 | 500 | 500 | 1 | 1.2981 | 649.0371
Interconnect piping supports |  | ea | 1 | 600 | 600 | 1 | 1.2981 | 778.8445
Total parts cost per completed assembly |  |  |  |  | 155474.5045 |  |  | 220545.5394
Parts + Overhead | [7 empty] | 265514.7749
|  |  | Inspection and assy/disassy labor |  |  |  | Interconnect bellows |  |  | No. reqd | Unit cost | Ext total | Inflation | Current total
Labor type (assume $85,000/yr, 2,000 hr/yr) | Units | Unit cost | No. reqd | Hrs each | Ext total |  | Cold mass bellows |  |  | 2 | 1600 | 3200 | 1.2981 | 4153.8375
Tech (incoming insp) | hr | 85 | 2 | 160 | 27200 |  | Pumping line bellows |  |  | 1 | 750 | 750 | 1.2981 | 973.5557
Process engr (traveler) | hr | 85 | 1 | 160 | 13600 |  | Cooldown line bellows |  |  | 1 | 500 | 500 | 1.2981 | 649.0371
Tech (supervision) | hr | 85 | 1 | 240 | 20400 |  | Shield bellows |  |  | 2 | 500 | 1000 | 1.2981 | 1298.0742
Tech (assembly) | hr | 85 | 3 | 240 | 61200 |  | Total per triplet |  |  |  |  | 5450 |  | 7074.5045
Weldor | hr | 85 | 1 | 80 | 6800
Tech (inspection) | hr | 85 | 1 | 80 | 6800
Total cost per completed assembly |  |  |  |  | 136000
Estimated EDIA
Name |  | Labor rate | FY2013 | FY2014 | Total
Engineer |  | 312000 | 75% | 25% | 312000
Engineer |  | 312000 | 75% | 25% | 312000
Design drafter |  | 212160 | 75% | 50% | 265200
Design drafter |  | 212160 | 75% | 50% | 265200
Grand total for EDIA |  |  |  |  | 1154400
Grand total (parts, labor, EDIA) |  |  |  |  | 1555914.7749 |  | Recurring cost (per test) |  | 95200

## Overheads
Rate Table
Resource Name | Hourly Rate FY12 | Weekly Rate FY12 | Annual Rate FY12 | Comment
Technician | 85 | 3400 | 176800 | Electrical technician rate
Designer | 102 | 4080 | 212160 | Mechanical designer rate
Engineer | 150 | 6000 | 312000 | Average of junior, senior
D/S/C | LABOR | MSA | PASS THRU | 500K | Escalation Table
AD | 96.38% | 20.39% | 1.5% | 101.95 | FY | Labor | M & S
APC | 96.38% | 20.39% | 1.5% | 101.95 | 2012 | Base Year
BSS | 51.64% | 20.39% | 1.5% | 101.95 | 2013 | 0.8% | 2.7%
CD | 67.57% | 20.39% | 1.5% | 101.95 | 2014 | 2.82% | 5.47%
CMSC | 75.6% | 20.39% | 1.5% | 101.95 | 2015 | 5.39% | 8.32%
DIR | 51.64% | 20.39% | 1.5% | 101.95 | 2016 | 8.02% | 11.24%
ES&H | 51.64% | 20.39% | 1.5% | 101.95 | 2017 | 10.72% | 14.24%
FCPA | 75.6% | 20.39% | 1.5% | 101.95 | 2018 | 13.49% | 17.32%
FESS | 51.64% | 20.39% | 1.5% | 101.95 | 2019 | 16.33% | 20.49%
FIN | 51.64% | 20.39% | 1.5% | 101.95 | 2020 | 19.24% | 23.74%
LBNE | 51.64% | 20.39% | 1.5% | 101.95 | 2021 | 22.16% | 27.08%
PPD | 75.6% | 20.39% | 1.5% | 101.95 | 2022 | 25.27% | 30.51%
TD | 85.76% | 20.39% | 1.5% | 101.95 | 2023 | 28.4% | 34.03%
WDRS | 51.64% | 20.39% | 1.5% | 101.95 | 2024 | 31.61% | 37.65%
[5 empty] | 2025 | 34.9% | 41.37%

## QX estimate WBS Final
1 MQXF Structures Production Estimates
DWCheng, 10/25/2012
Assumptions/Comments:
[5 empty] | Magnet Struct. analyses/x-sect not accounted for in engineering time. |  | LQ |  | HQ |  |  |  | LABOR |  |  |  | Material
[5 empty] | 4.4m length "scaling" from 3.7m LQ costs; or 1.2m HQ cost basis |  | 1.2 |  | 3.7 |  |  | days/year | 252 | wks/year | 50.4
[5 empty] | Total inflation from 2007 (LQ) or 2009 (HQ) to 2012 |  | 1.12 |  | 1.08 |  |  |  | P/E | D/EA/ST | Tech
[5 empty] | Yellow subtask M&S costs incorporate scaling and inflation above | [6 empty] | FY12 FTE | 389176.704 | 295611.12 | 233856 | sales tax | 0.0925
[5 empty] | Green subtask M&S costs incorporate procurement burdens |  | 1.25
Not sure of sales tax; not applied
$/FTE rates based on FY12 ALS data
Green subtask days may be partially parallel; values should be examined further if used for scheduling
Red items in Section 1.6 aren't rolled up here, but may provide guidance for Coil Instrumentation task budgeting
Does not include transportation/shipping container or for transport of assembled magnet(s)
[7 empty] | Task Estimate (days) |  |  | Total |  | FTE |  | One-time | One-time | Per-Assy | Per-Assy
[6 empty] | P/E | D/EA/ST | Tech | # T. | Tech Time | P/E | D/EA/ST | Tech | Labor | M&S | Labor | M&S | Comments
| 1.1 Engineering & Detailed Design (One-time cost) |  |  |  |  | 86 | 133 |  |  |  | 0.34127 | 0.52778 | 0 | 288831.252
|  | 1.1.1 Shell Detailed Design |  |  |  | 2 | 5 |  |  |  | 0.0079365 | 0.019841 |  | 8954.004
|  | 1.1.2 Yoke | [11 empty] | 28777.656
|  |  | 1.1.2.1 Yoke Detailed Design |  |  | 2 | 4 |  |  |  | 0.0079365 | 0.015873 |  | 7780.944
|  |  | 1.1.2.2 Yoke Tie-rod Detailed Design |  |  | 2 | 3 |  |  |  | 0.0079365 | 0.011905 |  | 6607.884
|  |  | 1.1.2.3 Yoke bushing Detailed Design |  |  | 2 | 2 |  |  |  | 0.0079365 | 0.0079365 |  | 5434.824
|  |  | 1.1.2.4 Tension rig Detailed Design |  |  | 2 | 5 |  |  |  | 0.0079365 | 0.019841 |  | 8954.004
|  | 1.1.3 Quarter Assy Rig | [11 empty] | 27174.12
|  |  | 1.1.3.1 Engineer Quarter length Assembly rig |  |  | 10 |  |  |  |  | 0.039683 |  |  | 15443.52
|  |  | 1.1.3.2 Detailed Design QL Assembly Rig |  |  |  | 10 |  |  |  |  | 0.039683 |  | 11730.6
|  | 1.1.4 Shell Loading | [11 empty] | 15249.78
|  |  | 1.1.4.1 Bladders Detailed Design |  |  |  | 5 |  |  |  |  | 0.019841 |  | 5865.3
|  |  | 1.1.4.2 Load Key Detailed Design |  |  |  | 5 |  |  |  |  | 0.019841 |  | 5865.3
|  |  | 1.1.4.3 Load Shim Detailed Design |  |  |  | 1 |  |  |  |  | 0.0039683 |  | 1173.06
|  |  | 1.1.4.4 Bladder shim Detailed Design |  |  |  | 1 |  |  |  |  | 0.0039683 |  | 1173.06
|  |  | 1.1.4.5 Bladder key design |  |  |  | 1 |  |  |  |  | 0.0039683 |  | 1173.06
|  | 1.1.5 Coilpack Load Pads Design | [11 empty] | 37731.66
|  |  | 1.1.5.1 Load pad Detailed Design |  |  | 4 | 10 |  |  |  | 0.015873 | 0.039683 |  | 17908.008
|  |  | 1.1.5.2 Load pad bushing Detailed Design |  |  |  | 2 |  |  |  |  | 0.0079365 |  | 2346.12
|  |  | 1.1.5.3 Load pad tie-rod Detailed Design |  |  | 4 | 3 |  |  |  | 0.015873 | 0.011905 |  | 9696.588
|  |  | 1.1.5.4 Tension rod assembly rig Detailed Design |  |  | 2 | 4 |  |  |  | 0.0079365 | 0.015873 |  | 7780.944
|  | 1.1.6 Coilpack Collars Design | [11 empty] | 31123.776
|  |  | 1.1.6.1 Coilpack Collar Detailed Design |  |  | 4 | 10 |  |  |  | 0.015873 | 0.039683 |  | 17908.008
|  |  | 1.1.6.2 Coilpack Collar bushing Detailed Design |  |  |  | 2 |  |  |  |  | 0.0079365 |  | 2346.12
|  |  | 1.1.6.3 Coilpack Collar tie-rod Detailed Design |  |  | 4 | 3 |  |  |  | 0.015873 | 0.011905 |  | 9696.588
|  |  | 1.1.6.4 Tension rod assembly rig Detailed Design |  |  |  | 1 |  |  |  |  | 0.0039683 |  | 1173.06
|  | 1.1.7 Master Load Key Design | [11 empty] | 27292.488
|  |  | 1.1.7.1 Master Load key Detailed Design |  |  | 4 | 15 |  |  |  | 0.015873 | 0.059524 |  | 23773.308
|  |  | 1.1.7.2 Load key Detailed Design |  |  |  | 2 |  |  |  |  | 0.0079365 |  | 2346.12
|  |  | 1.1.7.3 Load key shim Detailed Design |  |  |  | 1 |  |  |  |  | 0.0039683 |  | 1173.06
|  | 1.1.8 Magnet & Coilpack Assembly Tables | [11 empty] | 43849.884
|  |  | 1.1.8.1 Raft engineering |  |  | 15 |  |  |  |  | 0.059524 |  |  | 23165.28
|  |  | 1.1.8.2 Raft detailed design |  |  | 2 | 10 |  |  |  | 0.0079365 | 0.039683 |  | 14819.304
|  |  | 1.1.8.3 Table top detailed design |  |  |  | 5 |  |  |  |  | 0.019841 |  | 5865.3
|  | 1.1.9 Bladder & Shim winch rig | [11 empty] | 20194.944
|  |  | 1.1.9.1 Winch rig engineering |  |  | 7 |  |  |  |  | 0.027778 |  |  | 10810.464
|  |  | 1.1.9.2 Winch rig detailed design |  |  |  | 8 |  |  |  |  | 0.031746 |  | 9384.48
|  | 1.1.10 Magnet Support and Handling Structure | [11 empty] | 48482.94
|  |  | 1.1.10.1 Mag S&H Engineering |  |  | 20 |  |  |  |  | 0.079365 |  |  | 30887.04
|  |  | 1.1.10.2 Mag S&H detailed design |  |  |  | 15 |  |  |  |  | 0.059524 |  | 17595.9
| 1.2 Tooling & Fixtures Fabrication (One-time, or per-unit) | [6 empty] | 19 |  |  | 0.0039683 | 0 | 0.13492 | 33096.352 | 70825
|  | 1.2.1 Quarter Assy Rig (1.1m) | [11 empty] | 6184.352 | 8500
|  |  | 1.2.1.1 Fabricate QL assembly rig | [11 empty] | 8000 |  |  | ??
|  |  | 1.2.1.2 Assemble QL assembly rig |  |  | 1 |  | 5 | 1 | 5 | 0.0039683 |  | 0.019841 | 6184.352 | 500 |  |  | ?? Hardware tooling costs
|  | 1.2.2 Shell Loading | [11 empty] | 4640 | 5000
|  |  | 1.2.2.1 Bladder key and shim fabrication |  |  |  |  | 5 | 1 | 5 |  |  | 0.019841 | 4640 | 5000 |  |  | ??
|  | 1.2.3 Coilpack Load Pads | [11 empty] | 0 | 3000
|  |  | 1.2.3.1 Fabricate Tension rod assembly rig | [11 empty] | 3000
|  | 1.2.4 Coilpack Collars | [11 empty] | 0 | 1000
|  |  | 1.2.4.1 Tension rod assembly rig fabrication | [11 empty] | 1000
|  | 1.2.5 Magnet & Coilpack Assembly Tables | [11 empty] | 5568 | 15000
|  |  | 1.2.5.1 Insertion table components fabrication | [11 empty] | 15000 |  |  | ??
|  |  | 1.2.5.2 Insertion table assembly |  |  |  |  | 3 | 2 | 6 |  |  | 0.02381 | 5568
|  | 1.2.6 Bladder & Shim winch rig | [11 empty] | 3712 | 4000
|  |  | 1.2.6.1 Winch rig fabrication | [11 empty] | 4000
|  |  | 1.2.6.2 Winch rig assembly |  |  |  |  | 2 | 2 | 4 |  |  | 0.015873 | 3712
|  | 1.2.7 Magnet Support and Handling Structure | [11 empty] | 12992 | 20160
|  |  | 1.2.7.1 Mag S&H fabrication | [11 empty] | 20160 |  |  | (6859110) * LQ scaleup factors
|  |  | 1.2.7.2 Mag S&H Assembly |  |  |  |  | 1 | 2 | 2 |  |  | 0.0079365 | 1856
|  |  | 1.2.7.3 Mag S&H Certification & test |  |  |  |  | 3 | 4 | 12 |  |  | 0.047619 | 11136 |  |  |  | Assumes a crew of riggers & prep time
| 1.3 Shell & Yoke Assembly | [6 empty] | 34 |  |  | 0.035714 | 0.027778 | 0.38889 |  |  | 113054.588 | 322970.5
|  | 1.3.1 Shell Fabrication | [13 empty] | 12680.352 | 70000
|  |  | 1.3.1.1 Shell Fabrication | [13 empty] | 70000 | $50k (LQ/HD2) * LQ scale up factors
|  |  | 1.3.1.2 Shell alignment pin machining |  |  |  |  | 8 | 1 | 8 |  |  | 0.031746 |  |  | 7424
|  |  | 1.3.1.3 Shell Inspection |  |  | 1 |  | 4 | 1 | 4 | 0.0039683 |  | 0.015873 |  |  | 5256.352
|  | 1.3.2 Yoke Fabrication | [13 empty] | 3712 | 123876
|  |  | 1.3.2.1 Yoke Fabrication | [13 empty] | 123876 | $31k HQ yokes * HQ scaleup factors
|  |  | 1.3.2.2 Yoke Inspection |  |  |  |  | 2 | 2 | 4 |  |  | 0.015873 |  |  | 3712
|  | 1.3.3 Yoke Tie-rod hardware | [13 empty] | 0 | 37162
|  |  | 1.3.3.1 Yoke Quarter tie-rod fabrication | [14 empty] | See below
|  |  | 1.3.3.2 Yoke half-length tie-rod fabrication | [14 empty] | See below
|  |  | 1.3.3.3 Yoke full-length tie-rod fab. | [13 empty] | 30912 | all rod lengths; $23k * LQ scale up factors
|  |  | 1.3.3.4 Yoke bushing fabrication | [13 empty] | 6000 | ??
|  |  | 1.3.3.5 Yoke tie-rod nuts & washers | [13 empty] | 250
|  | 1.3.4 Yoke Tie-rod tension rig | [13 empty] | 0 | 8000
|  |  | 1.3.4.1 Tension rig fabrication | [13 empty] | 8000 | ??
|  | 1.3.5 High Pressure bladders | [13 empty] | 928 | 13338.4
|  |  | 1.3.5.1 Bladder fabrication (half) | [13 empty] | 5241.6 | 14 LQ half-length bladders * LQ scaleup factors
|  |  | 1.3.5.2 Bladder fabrication (full-length) | [13 empty] | 7996.8 | 14 LQ full-length bladders * LQ scaleup factors
|  |  | 1.3.5.3 Mount High pressure glands and fittings on bladders |  |  |  |  | 1 | 1 | 1 |  |  | 0.0039683 |  |  | 928 | 100
|  | 1.3.6 Load Keys (including alignment keys) | [13 empty] | 4640 | 6000
|  |  | 1.3.6.1 Load Key fabrication | [13 empty] | 5000 | ??
|  |  | 1.3.6.2 Load Shim fabrication |  |  |  |  | 5 | 1 | 5 |  |  | 0.019841 |  |  | 4640 | 1000 | ??
|  | 1.3.7 Shell & Yoke Assembly | [8 empty] | 0.031746 | 0.027778 | 0.30159 |  |  | 91094.236 | 0
1.3.7.1 Quarter length yoke assy (x4)
|  |  |  | 1.3.7.1.1 Deburr & prep yoke laminations |  |  |  | 3 | 2 | 6 |  |  | 0.02381 |  |  | 22272 |  | Raw FTE was mulitplied by 4 for each assy
|  |  |  | 1.3.7.1.2 Assemble & stack yokes with bushings |  |  |  | 2 | 2 | 4 |  |  | 0.015873 |  |  | 14848 |  | Raw FTE was mulitplied by 4 for each assy
|  |  |  | 1.3.7.1.3 Tension yoke stack; tighten nuts |  |  |  | 1 | 2 | 2
1.3.7.1.4 Mount shell vertically on plate
|  |  |  | 1.3.7.1.5 Insert yoke stacks, align with pins, wedge in place |  | 1 |  | 1 | 2 | 2 | 0.0039683 |  | 0.0079365 |  |  | 13601.408 |  | Raw FTE was mulitplied by 4 for each assy
1.3.7.1.6 Connect SG system
|  |  |  | 1.3.7.1.7 Pressurize yokes and insert gap keys |  | 1 | 1 | 1 | 2 | 2 | 0.0039683 | 0.0039683 | 0.0079365 |  |  | 18293.648 |  | Raw FTE was mulitplied by 4 for each assy
1.3.7.2 Shell & Yoke half-length assembly (2x)
|  |  |  | 1.3.7.2.1 Move two quarter length segments onto pneumatic plates |  |  |  | 1 | 2 | 2 |  |  | 0.0079365 |  |  | 3712 |  | Raw FTE was multiplied by 2 for each assy
|  |  |  | 1.3.7.2.2 Remove yoke tension rods and alignment pins |  |  |  | 1 | 2 | 2 |  |  | 0.0079365 |  |  | 3712 |  | Raw FTE was multiplied by 2 for each assy
1.3.7.2.3 Insert alignment engagement pins
|  |  |  | 1.3.7.2.4 Float segments together |  |  |  | 1 | 2 | 2 |  |  | 0.0079365 |  |  | 3712 |  | Raw FTE was multiplied by 2 for each assy
1.3.7.2.5 Insert half-length tension rod
|  |  |  | 1.3.7.2.6 Tension rods and tighten nuts |  |  | 1 | 1 | 2 | 2 |  | 0.0039683 | 0.0079365 |  |  | 6058.12 |  | Raw FTE was multiplied by 2 for each assy
1.3.7.3 Full length Shell Assembly
1.3.7.3.1 Mount two half-length segments on table
1.3.7.3.2 Remove tension rods, alignment pins
|  |  |  | 1.3.7.3.3 Insert alignment engagement pins |  |  |  | 1 | 2 | 2 |  |  | 0.0079365 |  |  | 1856
1.3.7.3.4 Float segments together
1.3.7.3.5 Insert full-length tension rods
|  |  |  | 1.3.7.3.6 Tension rods and tighten nuts |  |  | 1 | 1 | 2 | 2 |  | 0.0039683 | 0.0079365 |  |  | 3029.06
| 1.4 Coilpack Assembly | [6 empty] | 49 |  |  | 0.0039683 | 0.031746 | 0.35317 |  |  | 93520.832 | 338934.5
|  | 1.4.1 Coilpack Load Pads | [13 empty] | 25791.18 | 213296
1.4.1.1 Fabrication
|  |  |  | 1.4.1.1.1 Load pad fabrication | [12 empty] | 203796 | $51k HQ * HQ scaleup factors
|  |  |  | 1.4.1.1.2 Load pad bushing fabrication | [12 empty] | 6000 | ??
|  |  |  | 1.4.1.1.3 Load pad tie-rod fabrication | [12 empty] | 3500 | ??
|  |  | 1.4.1.2 Parts received and inspection |  |  |  | 2 | 5 | 2 | 10 |  | 0.0079365 | 0.039683 |  |  | 11626.12
1.4.1.3 Assembly of 4.4m-long pads (x4)
|  |  |  | 1.4.1.3.1 Deburr, lube, and prep laminations |  |  |  | 3 | 2 | 6 |  |  | 0.02381 |  |  | 5568
|  |  |  | 1.4.1.3.2 Assemble all laminations on bushings |  |  |  | 3 | 2 | 6 |  |  | 0.02381 |  |  | 5568
|  |  |  | 1.4.1.3.3 Insert tension rods and tighten |  |  | 1 | 1 | 2 | 2 |  | 0.0039683 | 0.0079365 |  |  | 3029.06
|  | 1.4.2 Coilpack collars | [13 empty] | 19050.12 | 34974
1.4.2.1 Fabrication
|  |  |  | 1.4.2.1.1 Coilpack Collar fabrication | [12 empty] | 25974 | $6.5k HQ * HQ scaleup factors
|  |  |  | 1.4.2.1.2 Coilpack Collar bushing fabrication | [12 empty] | 5000 | ??
|  |  |  | 1.4.2.1.3 Coilpack Collar tie-rod fabrication | [12 empty] | 4000 | ??
|  |  | 1.4.2.2 Parts received and inspection |  |  |  | 1 | 4 | 1 | 4 |  | 0.0039683 | 0.015873 |  |  | 4885.06
1.4.2.3 Assembly of 4m-long Coilpack Collar (x4)
|  |  |  | 1.4.2.3.1 Deburr, lube, and prep laminations |  |  |  | 3 | 2 | 6 |  |  | 0.02381 |  |  | 5568
|  |  |  | 1.4.2.3.2 Assemble all laminations on bushings |  |  |  | 3 | 2 | 6 |  |  | 0.02381 |  |  | 5568
|  |  |  | 1.4.2.3.3 Insert tension rods and tighten |  |  | 1 | 1 | 2 | 2 |  | 0.0039683 | 0.0079365 |  |  | 3029.06
|  | 1.4.3 Master Load Keys | [13 empty] | 11381.06 | 22877.6
1.4.3.1 Fabrication
|  |  |  | 1.4.3.1.1 Master Load key fabrication | [12 empty] | 22377.6 | $5.5k HQ * HQ scaleup factors
|  |  |  | 1.4.3.1.2 Load key fabrication |  |  |  | 2 | 1 | 2 |  |  | 0.0079365 |  |  | 1856 | 200
|  |  |  | 1.4.3.1.3 Load Shim fabrication |  |  |  | 3 | 1 | 3 |  |  | 0.011905 |  |  | 2784 | 300
|  |  | 1.4.3.2 Inspection |  |  |  | 1 | 3 | 2 | 6 |  | 0.0039683 | 0.02381 |  |  | 6741.06
|  | 1.4.4 Assemble Coilpack | [13 empty] | 37298.472 | 0
|  |  | 1.4.4.1 Mount lower load pad onto assembly table |  |  |  | 1 | 1 | 2 | 2 |  | 0.0039683 | 0.0079365 |  |  | 3029.06
1.4.4.2 Mount lower collar assembly onto lower load pad
|  |  | 1.4.4.3 Shim coils for alignment tuniing (includes iterations as well) |  |  | 1 |  | 3 | 2 | 6 | 0.0039683 |  | 0.02381 |  |  | 7112.352
1.4.4.4 Align side collars
|  |  | 1.4.4.5 Pick up and align two side coils with fixture |  |  |  |  | 2 | 2 | 4 |  |  | 0.015873 |  |  | 3712
|  |  | 1.4.4.6 Insert coils, fasten with angle plates |  |  |  |  | 1 | 2 | 2 |  |  | 0.0079365 |  |  | 1856
|  |  | 1.4.4.7 Maneuver top coil onto coilpack |  |  |  |  | 2 | 2 | 4 |  |  | 0.015873 |  |  | 3712
|  |  | 1.4.4.8 Place top collar on top |  |  |  |  | 1 | 2 | 2 |  |  | 0.0079365 |  |  | 1856
|  |  | 1.4.4.9 Bolt and torque collars |  |  |  | 1 | 3 | 2 | 6 |  | 0.0039683 | 0.02381 |  |  | 6741.06
|  |  | 1.4.4.10 Mount side load pads |  |  |  |  | 1 | 2 | 2 |  |  | 0.0079365 |  |  | 1856
|  |  | 1.4.4.11 Mount upper load pad |  |  |  |  | 2 | 2 | 4 |  |  | 0.015873 |  |  | 3712
|  |  | 1.4.4.12 Bolt and torque load pad assembly |  |  |  |  | 2 | 2 | 4 |  |  | 0.015873 |  |  | 3712
| 1.5 Magnet Assembly | [6 empty] | 18.5 |  |  | 0.037698 | 0 | 0.15079 |  |  | 49935.344 | 0
|  | 1.5.1 Mount Shell & yoke on assembly surface | [5 empty] | 1 | 2 | 2 |  |  | 0.0079365 |  |  | 1856
|  | 1.5.2 Mount & align coilpack on staging table (includes 1st master key assy) |  |  |  | 1 |  | 3 | 2 | 6 | 0.0039683 |  | 0.02381 |  |  | 7112.352
|  | 1.5.3 Insert Coilpack | [5 empty] | 1 | 2 | 2 |  |  | 0.0079365 |  |  | 1856
|  | 1.5.4 Assemble and Insert master key assemblies | [5 empty] | 1.5 | 2 | 3 |  |  | 0.011905 |  |  | 2784
|  | 1.5.5 Prepare for bladder operations | [5 empty] | 1 | 2 | 2 |  |  | 0.0079365 |  |  | 1856
|  | 1.5.6 Bladder ops |  |  |  | 2.5 |  | 2 | 3 | 6 | 0.0099206 |  | 0.02381 |  |  | 9428.88
|  | 1.5.7 Install Axial load rig | [5 empty] | 1 | 2 | 2 |  |  | 0.0079365 |  |  | 1856
|  | 1.5.8 Tension axial rods |  |  |  | 2 |  | 1 | 2 | 2 | 0.0079365 |  | 0.0079365 |  |  | 4944.704
|  | 1.5.9 Final bladder operations |  |  |  | 2 |  | 1 | 2 | 2 | 0.0079365 |  | 0.0079365 |  |  | 4944.704
|  | 1.5.10 Mount Pizza Box & splice | [5 empty] | 2 | 2 | 4 |  |  | 0.015873 |  |  | 3712
|  | 1.5.11 Package magnet and cables for shipment |  |  |  | 1 |  | 3 | 2 | 6 | 0.0039683 |  | 0.02381 |  |  | 7112.352
|  | 1.5.12 Magnet mechanical completeness QA |  |  |  | 1 |  | 1 | 1 | 1 | 0.0039683 |  | 0.0039683 |  |  | 2472.352
| 1.6 Diagnostics and Instrumentation, Protection | [6 empty] | 11 |  |  | 0.09127 | 0.039683 | 0.047619 |  |  | 54369.992 | 1250
|  | 1.6.1 Detail Design Magnet Schematics |  |  |  | 5 | 10 |  |  |  | 0.019841 | 0.039683 |  |  |  | 19452.36
|  | 1.6.2 Detail Design Coil Schematics |  |  |  | 5 | 5 |  |  |  | 0.019841 | 0.019841 |  |  |  | 13587.06 |  | This section not calculated in green task rollup
|  | 1.6.3 Shell Instrumentation | [13 empty] | 13296.704 | 1000
|  |  | 1.6.3.1 SG installation |  |  |  |  | 10 | 1 | 10 |  |  | 0.039683 |  |  | 9280
|  |  | 1.6.3.2 Cabling and connectorizing |  |  |  |  | 1 | 1 | 1 |  |  | 0.0039683 |  |  | 928 | 1000
|  |  | 1.6.3.3 Shell connector QA |  |  | 2 |  |  |  |  | 0.0079365 |  |  |  |  | 3088.704
|  | 1.6.4 VT/Heater Traces | [13 empty] | 18709.776 | 5188 | This section not calculated in green task rollup
|  |  | 1.6.4.1 Detail Design Trace |  |  | 2 | 12 |  |  |  | 0.0079365 | 0.047619 |  |  |  | 17165.424
|  |  | 1.6.4.2 Trace artwork (Possibly one-time cost) | [13 empty] | 2688 | LQ (6891393) * LQ scaleup factors
|  |  | 1.6.4.3 Trace Fabrication | [13 empty] | 2500
|  |  | 1.6.4.4 Trace QA |  |  | 1 |  |  |  |  | 0.0039683 |  |  |  |  | 1544.352
|  | 1.6.5 Coil Instrumentation | [13 empty] | 11440.704 | 1000 | This section not calculated in green task rollup
|  |  | 1.6.5.1 SG Installation |  |  |  |  | 7 | 1 | 7 |  |  | 0.027778 |  |  | 6496
|  |  | 1.6.5.2 Cabling and Connectors |  |  |  |  | 2 | 1 | 2 |  |  | 0.0079365 |  |  | 1856 | 1000
|  |  | 1.6.5.3 Coil QA (post-Instrumentation) |  |  | 2 |  |  |  |  | 0.0079365 |  |  |  |  | 3088.704
|  | 1.6.6 Coilpack QA |  |  |  | 5 |  |  |  |  | 0.019841 |  |  |  |  | 7721.76
|  | 1.6.7 Magnet Connector and wiring placements |  |  |  | 2 |  | 4 |  | 1 | 0.0079365 |  | 0.0039683 |  |  | 4016.704
|  | 1.6.8 Magnet QA (pre-bladder ops) |  |  |  | 2 |  |  |  |  | 0.0079365 |  |  |  |  | 3088.704
|  | 1.6.9 Magnet QA (post-bladder ops) |  |  |  | 7 |  |  |  |  | 0.027778 |  |  |  |  | 10810.464

## LQ
QX Design Budgetary References
LQ
Hardware
|  |  | Date Purchased | PO | Total Cost | LBNL? | Outside | ARO | Qty | Dimensions | Material | Weight
Shell
|  | LQ sections | 2004-03-31 | 6830510 | $48725 + $5k additional costs | No | Scot Industries | 23 weeks | 4 | 17.95" ID x 19.76" OD x 33.46" | 6061-T6 | machined from one long tube then cut later
|  | Strain Gages |  |  | 600 |  |  |  | 32
|  | Assembly plates |  |  |  | yes |  |  | 4
Yokes
|  | LQ quadrants | 2004-03-25 | 6841295 | 53200 |  | Humb. Inst. | 8 weeks | 280 | 8.98"R x 1.93" quad; 4.57 opening | 1018
|  | Yoke Tierod hardware (mat'l) | 2004-04-30 | 6846933 | 13300 |  | Metal Suppl Online | 2 weeks | 20/30 | .25" dia x 12'/.75 dia x 12' | Nitronic 50
|  | Yoke tierod machining | 2004-05-05 | 6848897 | 9000 |  | Myers Precision Grinding
Yoke tierod, quarter length
Yoke tierod, half-length
Load Pads
|  | X & Y Pads | 2004-02-20 | 6841295 | 20400 | No | Humb. Inst. | 10 weeks | 220 |  | 1018
|  | X & Y Pads (stainless) | 2004-02-20 | 6841295 | 10320 | No | Humb. Inst. | 10 weeks | 64 |  | 304 SS
|  | load pad ends (stainless) | 2004-02-20 | 6841295 | 2550 | No | Humb. Inst. | 10 weeks | 16 |  | 304 SS
Master Keys
|  | Yoke side (half-length) | 2004-03-23 | 6843734 | 13600 |  | Humb Inst. | 6 weeks | 8
|  | Pad side (half-length) | 2004-03-23 | 6843734 | 13600 |  | Humb Inst. | 6 weeks | 8
Bladders
|  | Full length (~4m) | 2006-09-13 | 6939615 | 6810 |  | Directed Light |  | 16
|  | Quarter length (~1m) | 2004-04-24 | 6846320 | 6700 |  | Directed Light | 5 weeks | 36
Quarter length loading rig (for quarter-length pre assembly)
HiP fittings
Axial Rods
|  | Rod machining | 2004-09-08 | 6861056 | 4400 | no | Myers Precision Grinding | 4 weeks | 4 | 1" od x 145.5 long | 304 SS
|  | Strain gages |  |  | 80 |  |  |  | 4
Pre-assembly quarter length rods
Pre-assembly axial loading rig
Pre-assembly half-length rods
Axial Endplates
|  | Material | [6 empty] | 2
|  | Plate Machining | [6 empty] | 2
Axial Hardware
Nuts
Spherical washers

## HD3
QX Design Budgetary References
LD1/HD3 Info
Hardware
|  |  | Date Purchased | PO | Total Cost | LBNL? | Outside | ARO | Qty | Dimensions | Material | Weight
Shell
|  | HD2/HD3 | 2002-10-16 | 6812393 | $16895 + $1500 Inspection | No | OMW | 21 weeks | 1 | 24.5" ID x 27.75" OD x 40.32" | 7075-T6
|  | Strain Gages |  |  | 150 |  |  |  | 8
|  | LD-1 | 2007-02-16 | 6959818 | 49000 |  |  | 25 weeks | 1 |  |  | 5000 lbs.
Yokes
|  | HD2/HD3 | 2002-10-25 | 6812971 | 16168 | No | Humb. Inst. | 8 weeks | 42 | 12.25"R x 1.92"; 13" x 6" opening | 1020 Steel
Yoke Tierod hardware
LD-1
Load Pads
|  | Horizontal Pads (3pc) | 2003-07-05 | 6826785 | 14342 | No | Prowest | 10 weeks | 2 |  | SS304/1020
|  | Vertical Pads (3pc) | 2003-07-05 | 6826785 | 9000 | No | Prowest | 10 weeks | 2 |  | SS304/1020
|  | Field Shaper (3pc) | 2003-07-05 | 6826785 | 13660 | No | Prowest | 10 weeks | 2 |  | SS304/1020
Bladders
|  | New Order | 2008-08-31 |  | 7500 | No | Directed Light |  | 32
HiP fittings
Axial Rods
|  | Rod material |  |  | 600 | no | McMaster | 1 day | 4 | 9063K236 | 7075-T6 Al ground rod
|  | Rod machining | 2003-04-23 | 379225 | 790 | no | Horspool & Romine | 4 weeks | 4 | 1-1/2" OD x 58" long | 7075-T6 Al
|  | Strain gages |  |  | 80 |  |  |  | 4
Axial Endplates
|  | Material | 2003-05-15 | 6822651 | 3300 | no | Scot Forge | 6-7 weeks | 2 | 3 x 7.375x 14.25 | Nitronic 40 | ~90 lbs each
|  | Plate Machining | 2003-07-30 |  | 3000 | Yes |  |  | 2
Axial Hardware
Nuts
Spherical washers

## LR
QX Design Budgetary References
LR Info
Hardware
|  |  | Date Purchased | PO | Total Cost | LBNL? | Outside | ARO | Qty | Dimensions | Material | Weight
Shell
|  | LR | 2002-03-15 | 6805637 | 5500 | No | OMW | 21 weeks | 1 | 11" ID x 12" OD x 142" | 6061-T6
|  | Strain Gages |  |  | 300 |  |  |  | 16
Yokes
|  | LR |  |  |  | No | Humb. Inst. |  |  |  | 1020 Steel
Yoke Tierod hardware
Bladders
|  | New Order |  |  |  | No | Directed Light
HiP fittings
Axial Rods
|  | Rod material + machining | 2002-03-22 | 6805780 | 790 | no | Horspool & Romine | 3 weeks | 4 | 1/2" x 150" | 304 SS
|  | Strain gages |  |  | 80 |  |  |  | 4
Nuts