## Sheet2
Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012
Item | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | Total w/o Contingency | Contingency % | Total incl. Contingency | Notes
LARP Related R&D, Const.
R&D and Prototyping
IR Quad R&D | Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY13: 6884000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY14: 7295000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY15: 7889000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY16: 5776000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY17: 1678000 | 29522000 | 0% | 29522000 | SQXF, WP3DS-LQ-HQ-HQM, LHQ, LQXF, test stand upgrades
Crab Cavity Prototype | Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY13: 1437450; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY14: 3014885; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY15: 1920195 | 6372530 | 0% | 6372530 | Prototype thru test in SPS
Feedback Functioning Prototype | 1095350 | 1116430 | 1357538 | 1362104 | 1857308 | 2019940.5 | 706515.5 |  |  |  | 9515186 | 25.26% | 11919057.675 | Assume CERN contributions
R&D, Prototype Subtotal | 9416800 | 11426315 | 11166733 | 7138104 | 3535308 | 2019940.5 | 706515.5 | 0 | 0 | 0 | 45409716 |  | 47813587.675
Construction Project
Project Mgmt | 0 | 1484846.013 | 1729896.887 | 1776496.6464 | 1824417.4944 | 1873743.3456 | 1924392.872 | 1976338.3424 | 2029819.0912 | 1944290.816 | 16564241.508 | 10.63% | 18325020.3803 | Assume FY14 CD-0
IR Quad Construction | 0 | 0 | 3094342.1641 | 15378306.8624 | 17684631.1695 | 26976139.7397 | 25461524.4285 | 10789956.2939 | 5716839.1393 | 724747.4 | 105826487.1974 | 30% | 137574433.3566 | Q1 and Q3 cold masses, total qty.20. Assumes prototypes and test facility upgrades in R&D phase
Crab Cavity Construction |  |  |  | 5744940 | 5860750 | 6098955 | 6075607.5 | 2917890 | 2849030 | 2117385 | 31664557.5 | 35% | 42747152.625
Construction Subtotal | 0 | 1484846.013 | 4824239.0512 | 22899743.5088 | 25369798.6639 | 34948838.0853 | 33461524.8005 | 15684184.6363 | 10595688.2305 | 4786423.216 | 154055286.2054 | 28.95% | 198646606.3619
Total R&D and Construction for LARP Related Deliverables | 9416800 | 12911161.013 | 15990972.0512 | 30037847.5088 | 28905106.6639 | 36968778.5853 | 34168040.3005 | 15684184.6363 | 10595688.2305 | 4786423.216 | 199465002.2054 |  | 246460194.0369
US-LARP Budget
LARP Budget for Projects | Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY13: 8500000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY14: 8500000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY15: 8500000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY16: 8500000 | 34000000 |  | 34000000
Other LARP Budget: -General Accelerator R&D -Toohig and Long Term Visitors -Programmatic Travel and Management | Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY13: 3900000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY14: 3900000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY15: 3900000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY16: 3900000 | 15600000 |  | 15600000
Total LARP Budget | Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY13: 12400000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY14: 12400000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY15: 12400000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY16: 12400000 | 49600000 |  | 49600000
Other Projects
11T Dipole | 2000000 | 2000000 | 6200000 | 13700000 | 5400000 | 5700000 | 15200000 | 5900000 |  |  | 56100000 | 30% | 72930000 | Placeholders until scope is better understood
Diffusor (electron lens) | 959500 | 1190380 | 1112455 | 918170 | 830400 | 1702350 | 3764160 | 5593040 | 3958320 | 2286300 | 22315075 | 30% | 29009597.5
D2 Separators | Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY15: 2843500; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY16: 2843500; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY17: 5038500; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY18: 5038500 | 15764000 | 30% | 20493200
Other Project Subtotal | 2959500 | 3190380 | 10155955 | 17461670 | 11268900 | 12440850 | 18964160 | 11493040 | 3958320 | 2286300 | 94179075 |  | 122432797.5
GAD and Infrastructure
IR Quad - To be Verified | Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY13: 2090000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY14: 3342000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY15: 1397000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY16: 100000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY17: 0 | 6929000 | 0% | 6929000 | Conductor R&D, LQ-HQ-HQM, LHQ Rad Hard, Infrastructure
SRF Related GAD - TBD
Feedback Related GAD - TBD
GAD and Infrastructure Subtotal | 2090000 | 3342000 | 1397000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 6929000 |  | 6929000
US Grand Total | 14466300 | 19443541.013 | 27543927.0512 | 47599517.5088 | 40174006.6639 | 49409628.5853 | 53132200.3005 | 27177224.6363 | 14554008.2305 | 7072723.216 | 300573077.2054 |  | 375821991.5369
CERN IR Quad R&D | Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY13: 2900000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY14: 2540000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY15: 2970000; Total LARP Construction and Related R&D Costs ($AY) 20-Dec-2012 FY16: 1800000 | 10210000 |  | 10210000 | SQXF, HQ, WP3DS
CERN IR Quad Contruction |  |  | 3094342.1641 | 15378306.8624 | 17684631.1695 | 26976139.7397 | 25461524.4285 | 10789956.2939 | 5716839.1393 | 724747.4 | 105826487.1974 |  | 105826487.1974 | Assume equivalent cost to US contribution.
CERN Crab Cavity | [13 empty] | Cryo, RF coupler, RF Power, Installation
CERN Feedback | 181440 | 185076 | 284553 | 291654 | 298944 | 306423 | 2857812.9935 | 2933644.481 |  |  | 7339547.4745 |  | 10463100.9117 | Kicker assemblies, pickup structure, tunnel cables, racks, power, other.
CERN Total | 3081440 | 2725076 | 6348895.1641 | 17469960.8624 | 17983575.1695 | 27282562.7397 | 28319337.422 | 13723600.7749 | 5716839.1393 | 724747.4 | 123376034.6719 |  | 126499588.1091 | Does not include Crab. CERN input needed to produce accurate table.