## Slide 1: LHC Incident
Eric Prebys, FNAL

## Slide 2: Sept 10, 2008: LHC Startup
9:35 – First beam injected
9:58 – beam past CMS to point 6 dump
10:15 – beam to point 1 (ATLAS)
10:26 – First turn!
…and there was much rejoicing

## Slide 3: After initial circulation: captured beam
Everything was going great until something very bad happened on September 19th
  Initially, CERN kept a tight lid on news
Turn Number
Time

## Slide 4: Nature abhors a (news) vacuum…
Italian newspapers were very poetic (at least as translated by “Babel Fish”):
"the black cloud of the bitterness still has not been dissolved on the small forest in which they are dipped the candid buildings of the CERN"
“Lyn Evans, head of the plan, support that it was better to wait for before igniting the machine and making the verifications of the parts.“*
Or you could Google “What really happened at CERN”:
* “Big Bang, il test bloccato fino all primavera 2009”, Corriere dela Sera, Sept. 24, 2008
**
**http://www.rense.com/general83/IncidentatCERN.pdf

## Slide 5: What (really) really happened on September 19th*
Sector 3-4 was being ramped to 9.3 kA, the equivalent of 5.5 TeV
  All other sectors had already been ramped to this level
  Sector 3-4 had previously only been ramped to 7 kA (4.1 TeV)
At 11:18AM, a quench developed in the splice between dipole C24 and quadrupole Q24
  Not initially detected by quench protection circuit
  Power supply tripped at .46 sec
  Discharge switches activated at .86 sec
Within the first second, an arc formed at the site of the quench
  The heat of the arc caused Helium to boil.
  The pressure rose beyond .13 MPa and ruptured into the insulation vacuum.
  Vacuum also degraded in the beam pipe
The pressure at the vacuum barrier reached ~10 bar (design value 1.5 bar). The force was transferred to the magnet stands, which broke.

## Slide 6: Pressure forces on SSS vacuum barrier
Vacuum
1/3 load on cold mass (and support post)
~23 kN
1/3 load on barrier
~46 kN
Pressure
1 bar
Total load on 1 jack ~70 kN
V. Parma

## Slide 7: Collatoral damage: magnet displacements
QQBI.27R3

## Slide 8: Collatoral damage: magnet displacements
QQBI.27R3
V2 line
QQBI.27R3
N line

## Slide 9: Collateral damage: magnet displacements
QBBI.B31R3
Extension by 73 mm
QBQI.27R3
Bellows torn open

## Slide 10: Collateral damage: secondary arcs
QQBI.27R3 M3 line
QBBI.B31R3 M3 line

## Slide 11: Collateral damage: ground supports

## Slide 12: Collateral damage: Beam Vacuum
LSS3
LSS4
OK
Debris
MLI
Soot
The beam pipes were polluted with thousands of pieces of MLI and soot, from one extremity to the other of the sector
clean
MLI
soot
Arc burned through beam vacuum pipe

## Slide 13: Replacement of magnets
15 Quadrupoles (MQ)
  1 not removed (Q19)
  14 removed
    8 cold mass revamped (old CM, partial de-cryostating for cleaning and careful inspection of supports and other components)
    6 new cold masses
    In this breakdown there is consideration about timing (quad cryostating tales long time; variants problems).
42 Dipoles (MBs)
  3 not removed (A209,B20,C20)
  39 removed
    9 Re-used (old cold mass, no decryostating –except one?)
    30 new cold masses
    New cold masses are much faster to prepare than rescuing doubtful dipoles)

## Slide 14: Important questions about Sept. 19
Why did the joint fail?
  Inherent problems with joint design
    No clamps
    Details of joint design
    Solder used
  Quality control problems
Why wasn’t it detected in time?
  There was indirect (calorimetric) evidence of an ohmic heat loss, but these data were not routinely monitored
  The bus quench protection circuit had a threshold of 1V, a factor of >1000 too high to detect the quench in time.
Why did it do so much damage?
  The pressure relief system was designed around an MCI Helium release of 2 kg/s, a factor of ten below what occurred.

## Slide 15: What happened?
Theory: A resistive joint of about 220 n with bad electrical and thermal contacts with the stabilizer
No electrical contact between wedge and U-profile with the bus on at least 1 side of the joint
No bonding at joint with the U-profile and the wedge
A. Verweij
Loss of clamping pressure on the joint, and between joint and stabilizer
Degradation of transverse contact between superconducting cable and stabilizer
Interruption of longitudinal electrical continuity in stabilizer
Problem: this is where the evidence used to be

## Slide 16: Improved quench protection*
Old quench protection circuit triggered at 1V on bus.
New QPS triggers at .3 mV
  Factor of 3000
  Should be sensitive down to 25 nOhms (thermal runaway at 7 TeV)
  Can measure resistances to <1 nOhm
Concurrently installing improved quench protection for “symmetric quenches”
  A problem found before September 19th
  Worrisome at >4 TeV

## Slide 17: Improved pressure relief*
New configuration on four cold sectors: Turn several existing flanges into pressure reliefs (while cold). Also reinforce stands to hold ~3 bar
New configuration on four
warm sectors: new flanges
(12 200mm relief flanges)
(DP: Design Pressure)
L. Tavian

## Slide 18: Bad surprise
With new quench protection, it was determined that joints would only fail if they had bad thermal and bad electrical contact, and how likely is that?
  Very, unfortunately  must verify copper joint
Have to warm up to at least 80K to measure Copper integrity.
Solder used to solder joint had the same melting temperature as solder used to pot cable in stablizer
Solder wicked away from cable

## Slide 19: Complete Repair (2013-2015)
All (10,000!) individual joints were rebuilt
  Clamped
  Inspected
Improved pressure relief was installed to handled “Maximum Credible Incident” (MCI)
  In which both the quadrupole and dipole Helium lines were burned through.
After 2015 turn on, “smooth sailing”.